## DDR#01
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 1
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-05
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 81 / 81 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 0.97917
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 81 / 81 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 44
2019-05-04 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | SPUD MUD |  | HOLE SIZE (IN) |  | 26 |  | BIT No. |  | 1 |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 0
CHECK TIME | 6:00 | 0:00 | MD @ 00:00HR (M) |  | 81 |  | SIZE (IN) |  | 26 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 187.3
DEPTH, MD (M) |  | 81 | TVD @ 00:00HR (M) |  | 81 |  | MANUFACTURER |  | BAKER |  | 26" BIT |  |  | 26 |  |  | 7 5/8 REG |  | 0.55 | 0.5 |  | PITS (BBL) | 941.95
MW IN (SG) |  | 1.06 | DAILY PROGRESS (M) |  | 44 |  | TYPE |  | GTX-CG1 |  | BIT SUB |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 1.06 | 0.3376 |  | ACT. SYS (BBL) | 1129.25
MW OUT (SG) |  |  | INST. ROP (M/HR) |  | 7.3 |  | SERIAL NO. |  | 5259839 |  | 1 x 11" DC |  |  | 11 | 3 |  | 7 5/8 REG |  | 9.07 | 4.036 |  | RESV. SYS (BBL) | 683
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 6.4422 |  | IADC CODE |  | 115 |  | 25 7/8" ST. STB |  |  | 25.875 | 3.0625 |  | 7 5/8 REG |  | 2.43 | 1.0813 |  | KILL MUD (BBL) | 0
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 1-6 |  | NOZZLES |  | 4x20 |  | 1 x 11" DC |  |  | 11 | 3 |  | 7 5/8 REG |  | 9.07 | 4.036 |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 76 | AVG. RPM SURFACE |  | 90-100 |  | DEPTH IN (M) |  | 37 |  | 25 7/8" ST. STB |  |  | 25.875 | 3.0625 |  | 7 5/8 REG |  | 2.64 | 1.1748 |  | TOTAL | 1812.25
PV |  | 14 | AVG. RPM DOWNHOLE |  | 90-100 |  | DEPTH OUT (M) |  | 81 |  | 2 x 9 1/2" DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 18.51 | 5.8952 |  | DIESEL (LTR)
YIELD POINT |  | 29 | FLOWRATE (GPM) |  | 580-810 |  | METERAGE (M) |  | 44 |  | X-OVER |  |  | 9.5 | 3 |  | 4 1/2 IF |  | 0.94 | 0.29938 |  | RIG TANK | 94834
GEL ST. |  | 15/33 | PRESSURE (PSI) |  | 265-590 |  | RPM SURF. |  | 90-100 |  | X-OVER |  |  | 7.25 | 3 |  | 5 1/2 FH |  | 0.3 | 0.095546 |  | CAMP TANK | 14591
WL (ml/30 min.) |  | 9.5 | TORQ. ON-BTM (KLB-FT) |  | 3-6 |  | RPM BTM. |  | 90-100 | [12 empty] | CONSUMED | 5496
CT ( in/32) |  | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  | 1-6 | [12 empty] | RECEIVED
ALK (MUD) |  |  | STRING WT. (TON) - ROT |  | 50 |  | AVG. ROP (M/HR) |  | 6.4422 | [12 empty] | TOTAL | 109425
ALK (FILT.) |  |  | PICK-UP WT. (TON) |  | 51.45 |  | BIT ROT HRS. |  | 6.83 | [12 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  | 50.88 |  | K-REVS IN 24 HRS |  | 37.7 | [12 empty] | RIG STORAGE
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 37.7 | [12 empty] | CAMP STORAGE
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 8.9 | [12 empty] | CONSUMED
Nacl (mg/l) |  | 165 | JAR |  | NMDC |  | JET VELOCITY (M/SEC) |  | 58.2 | [12 empty] | RECEIVED
CHLORIDES (mg/l) |  | 100 | 5.5" HWDPS |  | STAB - 1 |  | TFA (IN²) |  | 1.227 | [12 empty] | TOTAL
HARDNESS (mg/l) |  | 140 | 11'' DCS |  | STAB - 2 |  | HSI |  | 0.2 | [12 empty] | POB
OIL% |  |  | ANY OTHER |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 44.57 |  |  | MPCL | 4
SAND % |  | 2 | BHA ROT. HRS |  | 9.94 |  | BIT No. 1 RR |  | 1/1/WT/A/E/I/NO/BHA |  | BHA WT. IN MUD (TON) | [7 empty] | 15.012 |  |  | MPCL SERV | 22
SOLIDS % |  | 2.99 | ON BOTTOM HRS |  | 6.83 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. (lb/bbl) |  | 20 | CIRC. HRS |  | 16.69 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 2
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 100 | 2 X 100 |  | 30" CONDUCTOR |  |  | 37 | [11 empty] | TOTAL | 112
DAILY WELL COST (US$) |  | 51395.8783 | SHAKER-2 | 1 X 50 | 2 X 50 | [16 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 993116.2555 | SHAKER-3 | 1 X 50 | 2 X 50 | [16 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 4.989% | MUD CLEANER | 3 X 140 | [17 empty] | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR |  |  |  | P-1 - F-1600HL | 7 |  | 12" | 3430 PSI | 97% |  | 0.1385 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS |  |  |  | P-2 - F-1600HL | 7 |  | 12" | 3430 PSI | 97% |  | 0.1385 | [7 empty] | NAGRI | SURFACE
FIRE DRILL |  |  | BLIND RAMS |  |  |  | P-3 - F-1600HL | 7 |  | 12" | 3430 PSI | 97% |  | 0.1385 | [7 empty] | CHINJI
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL
KICK DRILL |  |  | DIVERTER INFO |  | 29 1/2" - 500 psi |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD
TRIP DRILL |  |  | LAST BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 6 | BRINE LOSSES IN 24 HRS |  |  |  |  | BRINE LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43589 | 43589.0208 | 0.5 | DRL | NPT-UP | RR | FUNCTION TESTED NEW VALVE AND DIVERTER, OK.
43589.0208 | 43589.1979 | 4.25 | DRL | PT-P | D | SPUDDED IN WELL MIRAJ-1 AT 0030 HRS ON MAY 04, 2019. DRILLED 26" HOLE FROM 37M TO 58M.
43589.1979 | 43589.2812 | 2 | DRL | PT-P | BHA | POOH & R/BACK 5 1/2" DP STAND. ADDED 1ST 26" ST. STAB & 9 1/2" DC IN BHA. RIH TO BOTTOM.
43589.2812 | 43589.3438 | 1.5 | DRL | PT-P | D | DRILLED 26" HOLE FROM 58M TO 67M.
43589.3438 | 43589.4062 | 1.5 | DRL | PT-P | BHA | POOH & R/BACK 5 1/2" DP STAND. ADDED 2ND 26" ST. STAB IN BHA. RIH TO BOTTOM.
43589.4062 | 43589.5104 | 2.5 | DRL | PT-P | D | DRILLED 26" HOLE FROM 67M TO 81M.
43589.5104 | 43589.5625 | 1.25 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE PRIOR TO POOH.
43589.5625 | 43589.5729 | 0.25 | DRL | PT-P | FC | CHECKED FLOW, OK
43589.5729 | 43589.6875 | 2.75 | DRL | PT-P | POOH | POOH TO SURFACE. L/D 11" DC, 2x ST. STABS & BIT.
43589.6875 | 43589.9792 | 7 | DRL | PT-P | DP | P/U & M/U 26 x 5 1/2" DP STANDS & RACKED BACK. DRIFTED ALL DPS DURING P/UP FROM CAT WALK.
43589.9792 | 43590 | 0.5 | DRL | NPT-UP | RS | HANGED TDS TO ROLL BACK EXCESS DRILL LINE AT DRAW WORK'S DRUM.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-05
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43590 | 43590.125 | 3 | DRL | NPT-UP | RS | ROLLED BACK 100 M DRILL LINE FROM DRAW WORKS TO DRILL LINE SPOOL.
43590.125 | 43590.25 | 3 | DRL | PT-P | BHA | HANDLING MOTORIZED BHA. M/UP USED 26" TC BIT + MOTOR + SPSA.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | HANDLING MOTORIZED BHA.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH TO BOTTOM. DRILLED 26" HOLE FROM 37M TO 81M. POOH TO SURFACE. M/U & R/BACK 5 1/2" DRILL PIPE STANDS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | FUNCTION TEST MOTOR/MWD. M/UP 26" PDC BIT & MOTORIZED BHA. RIH & DRILL 26" HOLE.
REMARKS