## DDR#03
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 3
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-07
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / ADNAN |  |  | MD/TVD @ 00:00HRS: |  | 310 / 310 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 2.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 340 / 340 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 158
2019-05-06 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | SPUD MUD |  | HOLE SIZE (IN) |  | 26 |  | BIT No. |  | 2 RR |  | BHA No. |  |  | 2 | IN (M) |  | 81 |  | OUT (M) |  |  | STRING (BBL) | 9.22
CHECK TIME | 12:00 | 23:45 | MD @ 00:00HR (M) |  | 310 |  | SIZE (IN) |  | 26 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 486.92
DEPTH, MD (M) | 243 | 310 | TVD @ 00:00HR (M) |  | 310 |  | MANUFACTURER |  | BAKER |  | 26" PDC |  |  | 26 |  |  | 7 5/8 REG |  | 0.61 | 0.7 |  | PITS (BBL) | 946
MW IN (SG) | 1.11 | 1.12 | DAILY PROGRESS (M) |  | 158 |  | TYPE |  | TD509S |  | MUD MOTOR |  |  | 11.25 |  |  | 7 5/8 REG |  | 10.47 | 4.659 |  | ACT. SYS (BBL) | 1442.14
MW OUT (SG) | 1.11 | 1.12 | INST. ROP (M/HR) |  | 6.8 |  | SERIAL NO. |  | 5278922 |  | FLOAT SUB |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 0.79 | 0.2516 |  | RESV. SYS (BBL) | 700
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 10.4222 |  | IADC CODE |  | S423 |  | 25 7/8" ST. STB |  |  | 25.875 | 3.0625 |  | 7 5/8 REG |  | 2.64 | 1.1748 |  | KILL MUD (BBL) | 400
FL TEMP. °F |  | 129 | AVG. WOB (TON) |  | 5-8 |  | NOZZLES |  | 9x14 |  | SPSA |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 10.56 | 3.3632 |  | KILL MW (SG) | 1.6
µ FUNNEL (SEC) | 78 | 70 | AVG. RPM SURFACE |  | 80-95 |  | DEPTH IN (M) |  | 81 |  | NMDC |  |  | 9.5 | 3.125 |  | 7 5/8 REG |  | 9.15 | 2.9141 |  | TOTAL | 2542.14
PV | 17 | 13 | AVG. RPM DOWNHOLE |  | 174-189 |  | DEPTH OUT (M) |  |  |  | 25 7/8" ST. STB |  |  | 25.875 | 3.0625 |  | 7 5/8 REG |  | 2.5 | 1.1125 |  | DIESEL (LTR)
YIELD POINT | 31 | 32 | FLOWRATE (GPM) |  | 1045 |  | METERAGE (M) |  | 229 |  | 3 x 11" DC |  |  | 11 | 3 |  | 7 5/8 REG |  | 27.33 | 12.1615 |  | RIG TANK | 103897
GEL ST. | 14/19 | 14/23 | PRESSURE (PSI) |  | 1560-1850 |  | RPM SURF. |  | 80-95 |  | 2 x 9 1/2" DC |  |  | 9.5 | 3.0625 |  | 7 5/8 REG |  | 18.51 | 5.8952 |  | CAMP TANK | 29299
WL (ml/30 min.) | 9.5 | 9.5 | TORQ. ON-BTM (KLB-FT) |  | 8-11 |  | RPM BTM. |  | 174-189 |  | X-OVER |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.93 | 0.29619 |  | CONSUMED | 10195
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | WOB (TON) |  | 5-8 |  | 2 x 8" DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.34 | 4.0942 |  | RECEIVED
ALK (MUD) |  |  | STRING WT. (TON) - ROT |  | 83 |  | AVG. ROP (M/HR) |  | 11.1707 |  | DRILLING JAR |  |  | 8 | 3 |  | 6 5/8 REG |  | 9.58 | 2.1386 |  | TOTAL | 133196
ALK (FILT.) |  |  | PICK-UP WT. (TON) |  | 82 |  | BIT ROT HRS. |  | 20.5 |  | 3 x 8" DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 27.78 | 6.2015 |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 83 |  | K-REVS IN 24 HRS |  | 171 |  | X-OVER |  |  | 7.3125 | 2.8125 |  | 5 1/2 FH |  | 0.81 | 0.18082 |  | RIG STORAGE | 500000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 230 |  | 6 x 5 1/2" HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 56.62 | 2.0813 |  | CAMP STORAGE | 90000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 11.9 | [12 empty] | CONSUMED | 120000
KCl (mg/l) | 5300.6 | 5529.4 | JAR | 30.72 | NMDC | 30.72 | JET VELOCITY (M/SEC) |  | 73.7 | [12 empty] | RECEIVED | 155000
CHLORIDES (mg/l) | 2500 | 2600 | MOTOR | 30.72 | STAB - 1 | 33.98 | TFA (IN²) |  | 1.353 | [12 empty] | TOTAL
HARDNESS (mg/l) | 200 | 180 | 11'' DCS | 40.66 | STAB - 2 | 35.43 | HSI |  | 0.5 | [12 empty] | POB
OIL% |  |  | 9 1/2" DCS | 40.66 | SPSA | 30.72 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 196.62 |  |  | MPCL | 4
SAND % | 0.25 | 1 | BHA ROT. HRS |  | 40.66 |  | BIT No. 2 RR |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 40.6131 |  |  | MPCL SERV | 24
SOLIDS % | 8.86 | 6.86 | ON BOTTOM HRS |  | 27.33 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 31.4951 |  |  | SECURITY | 4
M.B.T. (lb/bbl) | 20 | 20 | CIRC. HRS |  | 21.53 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 58
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 2
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 100 | 2 X 100 |  | 30" CONDUCTOR |  |  | 37 | 224/224 |  | 0.28 | [6 empty] | MWD |  | TOTAL | 117
DAILY WELL COST (US$) |  | 40440.8429 | SHAKER-2 | 1 X 50 | 2 X 50 | [5 empty] | 252/252 |  | 0.34 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 1083896.6836 | SHAKER-3 | 1 X 100 | 2 X 100 | [5 empty] | 281/281 |  | 0.35 | [6 empty] | MWD |  | LAST CSG SIZE
% OF AFE SPENT |  | 5.445% | MUD CLEANER | 3 X 140 | [6 empty] | 309/309 |  | 0.55 | [6 empty] | MWD |  | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR |  |  |  | P-1 - F-1600HL | 7 |  | 12" | 3430 PSI | 97% |  | 0.1385 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS |  |  |  | P-2 - F-1600HL | 7 |  | 12" | 3430 PSI | 97% |  | 0.1385 | [7 empty] | NAGRI | SURFACE
FIRE DRILL |  |  | BLIND RAMS |  |  |  | P-3 - F-1600HL | 7 |  | 12" | 3430 PSI | 97% |  | 0.1385 | [7 empty] | CHINJI
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL
KICK DRILL |  |  | DIVERTER INFO |  | 29 1/2" - 500 psi |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD
TRIP DRILL |  |  | LAST BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 15 | BRINE LOSSES IN 24 HRS |  |  |  |  | BRINE LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-06
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43591 | 43591.2604 | 6.25 | DRL | PT-P | DM | CONT'D DRILLING 26" HOLE FROM 152M TO 207M. REAMED / WASHED DRILLED INTERVAL & RECORDED MWD SURVEY AT EACH STAND DOWN.
43591.2604 | 43591.3021 | 1 | DRL | PT-P | BHA | RACKED BACK 2x 5 1/2" DP STDS & RIH 5x 5 1/2" HWDP SINGLE BY SINGLE.
43591.3021 | 43591.3229 | 0.5 | DRL | PT-P | RS | SERVICED TDS.
43591.3229 | 43591.9167 | 14.25 | DRL | PT-P | DM | RESUMED DRILLING & DRILLED 26" HOLE FROM 207M TO 310M. REAMED / WASHED DRILLED INTERVAL & RECORDED MWD SURVEY AT CONNECTION.
43591.9167 | 43591.9688 | 1.25 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE PRIOR TO WIPER TRIP. RECORDED MWD SURVEY.
43591.9688 | 43592 | 0.75 | DRL | PT-P | WT | CHECKED FLOW, OK. POOH TO 166M FOR WIPER TRIP.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43592 | 43592.0417 | 1 | DRL | PT-P | WT | CONT'D POOH FROM 166M TO 140M. RIH FROM 140M TO BOTTOM AT 310M. HOLE CONDITION, GOOD.
43592.0417 | 43592.25 | 5 | DRL | PT-P | DM | RESUMED DRILLING & DRILLED 26" HOLE FROM 310M TO 340M. REAMED / WASHED DRILLED INTERVAL & RECORDED MWD SURVEY AT CONNECTION.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | NAGRI / CLAYSTONE, SANDSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILL AHEAD 26" HOLE.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D DRILLING 26'' HOLE FROM 152M TO 310M, CIRCULATED TO CLEAN HOLE, CHECKED FLOW, OK. POOH TO 166M FOR WIPER TRIP.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 26" HOLE.
REMARKS