## DDR#07
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 7
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-11
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / ADNAN |  |  | MD/TVD @ 00:00HRS: |  | 580 / 580 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 6.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 580 / 580 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2019-05-10 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | SPUD MUD |  | HOLE SIZE (IN) |  |  |  | BIT No. |  | 2 RR1 |  | BHA No. |  |  | 3 | IN (M) |  | 580 |  | OUT (M) | 580 |  | STRING (BBL)
CHECK TIME | 12:00 | 23:45 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 26 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1260.04
DEPTH, MD (M) | 580 | 580 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | BAKER |  | FLOAT SHOE |  |  | 20 |  |  | BTC |  | 0.86 |  |  | PITS (BBL) | 825
MW IN (SG) | 1.11 | 1.11 | DAILY PROGRESS (M) |  |  |  | TYPE |  | TD509S |  | 1ST JT (K55, 133 #, BTC) |  |  | 20 | 18.73 |  | BTC |  | 11.54 |  |  | ACT. SYS (BBL) | 2085.04
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 5278922 |  | FLOAT COLLAR |  |  | 20 |  |  | BTC |  | 0.96 |  |  | RESV. SYS (BBL) | 700
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | S423 |  | 2ND JT (K-55, 133 #, BTC) |  |  | 20 | 18.73 |  | BTC |  | 11.54 |  |  | KILL MUD (BBL) | 400
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 9x14 |  | 18 x JTS (K-55, 133#, BTC) |  |  | 20 | 18.73 |  | BTC |  | 207 |  |  | KILL MW (SG) | 1.6
µ FUNNEL (SEC) | 75 | 72 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 580 | [12 empty] | TOTAL | 2785.04
PV | 16 | 13 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  | 580 | [12 empty] | DIESEL (LTR)
YIELD POINT | 33 | 29 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 115515
GEL ST. | 18/24 | 15/27 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 26711
WL (ml/30 min.) | 9.5 | 9.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 5832
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  |  | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 142226
ALK (FILT.) |  |  | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9 | 9 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 500000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  |  | 20'' JTS IN HOLE |  |  | 20 | [7 empty] | CAMP STORAGE | 90000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  |  | 20'' JTS REMAINING |  |  | 31 | [7 empty] | CONSUMED | 148100
KCl (mg/l) | 4004.1 | 4004.1 | JAR |  | NMDC |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 248100
CHLORIDES (mg/l) | 2000 | 1900 | MOTOR |  | STAB - 1 |  | TFA (IN²) | [14 empty] | TOTAL
HARDNESS (mg/l) |  | 200 | 11'' DCS |  | STAB - 2 |  | HSI | [14 empty] | POB
OIL% |  |  | 9 1/2" DCS |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 231.9 |  |  | MPCL | 4
SAND % |  |  | BHA ROT. HRS |  |  |  | BIT No. 2 RR |  | 2-2-WT-A-X-I-ER-TD |  | BHA WT. IN MUD (TON) | [7 empty] | 0 |  |  | MPCL SERV | 30
SOLIDS % | 9.89 | 8.9 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 0 |  |  | SECURITY | 5
M.B.T. (lb/bbl) | 25 | 23 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 100 | 2 X 100 |  | 30" CONDUCTOR |  |  | 37 | 483/483 |  | 1.11 | [6 empty] | MWD |  | TOTAL | 125
DAILY WELL COST (US$) |  | 37628 | SHAKER-2 | 1 X 50 | 2 X 50 | [5 empty] | 510/510 |  | 1.25 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 1257058 | SHAKER-3 | 1 X 100 | 2 X 100 | [5 empty] | 539/539 |  | 1.07 | [6 empty] | MWD |  | LAST CSG SIZE
% OF AFE SPENT |  | 6.315% | MUD CLEANER | 3 X 140 | [6 empty] | 554/554 |  | 1.18 | [6 empty] | MWD |  | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR |  |  |  | P-1 - F-1600HL | 7 |  | 12" | 3430 PSI | 97% |  | 0.1385 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS |  |  |  | P-2 - F-1600HL | 7 |  | 12" | 3430 PSI | 97% |  | 0.1385 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS |  |  |  | P-3 - F-1600HL | 7 |  | 12" | 3430 PSI | 97% |  | 0.1385 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL
KICK DRILL |  |  | DIVERTER INFO |  | 29 1/2" - 500 psi |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD
TRIP DRILL |  |  | LAST BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | BRINE LOSSES IN 24 HRS |  |  |  |  | BRINE LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43595 | 43595.1458 | 3.5 | DRL | PT-P | BHA | CONT'D POOH FROM 110M TO 35M. MEANWHILE L/DOWN D. JAR. WHILE B/OUT CONNECTION BETWEEN ST. STAB & NMDC, OBSERVED CONNECTION OVER TORQUED. BROKE OUT CONNECTION AT HIGH TORQUE, UNABLE TO SPIN BACK WITH CHAIN TONG. BROKE OUT WITH ROTARY TONGS. FOUND ST. STAB PIN THREADS & NMDC BOX THREADS DAMAGED.
43595.1458 | 43595.2292 | 2 | DRL | NPT-UP | OTH | P/UP & M/UP LIFTING SUB PIN WITH NMDC DAMAGED BOX CONNECTION. WELDED LIFTING SUB WITH NMDC AND REINFORCED BY WELDING 4 STEEL STRIPS ON BODY.
43595.2292 | 43595.3646 | 3.25 | DRL | PT-P | BHA | CONT'D POOH FROM 35M TO SURFACE. MEANWHILE L/DOWN SCHL PERFORMANCE TOOLS SGL BY SGL FROM CATWALK.
43595.3646 | 43595.5208 | 3.75 | DRL | PT-P | BHA | M/UP 26'' RR PDC BIT WITH PACKED ROTARY BHA. RIH TO 168M.
43595.5208 | 43595.5833 | 1.5 | DRL | PT-P | RIH | CONT'D RIH FROM 168M TO 580M. PRECAUTIONARY WASHED DOWN LAST STAND.
43595.5833 | 43595.6667 | 2 | DRL | PT-P | CIR | CIRCULATED TO CONDITION MUD, KEPT CIRCULATING TILL SHAKERS CLEAN.
43595.6667 | 43595.6771 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43595.6771 | 43595.7292 | 1.25 | DRL | PT-P | POOH | POOH FROM 580M TO 168M. FOUND HOLE CONDITION GOOD.
43595.7292 | 43595.7396 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43595.7396 | 43595.8958 | 3.75 | DRL | PT-P | BHA | CONT'D POOH FROM 168M TO SURFACE. MEANWHILE B/OUT & L/DOWN D.JAR, 3 X STABS, 4 X 11 DC'S & BIT SGL BY SGL FROM CATWALK.
43595.8958 | 43595.9167 | 0.5 | DRL | PT-P | SM | PREPARED RIG FLOOR, HELD PJSM AND DISCUSSED SAFETY ABOUT 20'' CSG JOB.
43595.9167 | 43595.9583 | 1 | DRL | PT-P | RU | R/UP W.FORD TRS GEARS.
43595.9583 | 43596 | 1 | DRL | PT-P | RC | P/UP & M/UP 20'' K-55, 133 PPF, BTC; F/SHOE + 1ST JT + STAB IN F/COLLAR + 2ND JT (SHOE TRACK = 13.36M). RIH TO 24M. MEANWHILE CHECKED AND CONFIRMED INTEGRITY OF FLOATS - OK. APPLIED THREAD LOCKING COMPUND ON FIRST 3 JTS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-11
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43596 | 43596.125 | 3 | DRL | PT-P | RC | CONT'D RIH 20'' CSG FROM 24M TO 150M. FILLED UP CSG EVERY JOINT. INSTALLED CENTRALIZERS AS PER PROGRAM.
43596.125 | 43596.1458 | 0.5 | DRL | PT-P | RC / CIR | BROKE CIRCULATION.
43596.1458 | 43596.25 | 2.5 | DRL | PT-P | RC | CONT'D RIH 20'' CSG FROM 150M TO 232M. FILLED UP CSG EVERY JOINT. INSTALLED CENTRALIZERS AS PER PROGRAM.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | RIH 20'' CSG IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D POOH FROM 110M TO SURFACE. L/DOWN SCHL PERFORMANCE TOOLS, M/UP RR PDC BIT WITH PACKED ROTARY BHA, CONDITION TRIP PRIOR CSG JOB, HELD PJSM, R/UP W.FORD TRS, 20'' CSG JOB IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | 20'' CSG JOB, 20'' CSG CEMENT JOB, WOC
REMARKS |  |  | SCHL DD CREW + TOOLS RELEASED. DOWELL BACK UP UNIT ON LOCATION.
Formulas:
MIRAJ-1 = [DATE]+30