## DDR#08
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 8
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-12
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / ADNAN |  |  | MD/TVD @ 00:00HRS: |  | 580 / 580 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 7.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 580 / 580 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2019-05-11 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | SPUD MUD |  | HOLE SIZE (IN) |  |  |  | BIT No. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 35
CHECK TIME | 12:00 | 23:45 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 630
DEPTH, MD (M) | 580 | 580 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  |  | FLOAT SHOE |  |  | 20 |  |  | BTC |  | 0.86 |  |  | PITS (BBL) | 907
MW IN (SG) | 1.12 | 1.11 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  |  | 1ST JT (K55, 133 #, BTC) |  |  | 20 | 18.73 |  | BTC |  | 11.54 |  |  | ACT. SYS (BBL) | 1572
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  | FLOAT COLLAR |  |  | 20 |  |  | BTC |  | 0.96 |  |  | RESV. SYS (BBL) | 800
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | 47 x JTS (K-55, 133#, BTC) |  |  | 20 | 18.73 |  | BTC |  | 542.69 |  |  | KILL MUD (BBL) | 400
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  |  |  | 1 PUP JT (K-55, 133#, BTC) |  |  | 20 | 18.73 |  | BTC |  | 5.97 |  |  | KILL MW (SG) | 1.6
µ FUNNEL (SEC) | 70 | 60 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | 1 JT (K55, 133 #, BTC) |  |  | 20 | 18.73 |  | BTC |  | 11.54 |  |  | TOTAL | 2372
PV | 19 | 9 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 1 PUP JT (K-55, 133#, BTC) |  |  | 20 | 18.73 |  | BTC |  | 5.97 |  |  | DIESEL (LTR)
YIELD POINT | 33 | 19 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 111634
GEL ST. | 18/24 | 10/19 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 26053
WL (ml/30 min.) |  | 9.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 4539
CT ( in/32) |  | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  |  | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 137687
ALK (FILT.) |  |  | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 90000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 147700
KCl (mg/l) |  | 4004.1 | JAR |  | NMDC |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 97700
CHLORIDES (mg/l) | 1800 | 1900 | MOTOR |  | STAB - 1 |  | TFA (IN²) | [14 empty] | TOTAL
HARDNESS (mg/l) | 240 | 200 | 11'' DCS |  | STAB - 2 |  | HSI | [14 empty] | POB
OIL% |  |  | 9 1/2" DCS |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 579.53 |  |  | MPCL | 4
SAND % |  |  | BHA ROT. HRS |  |  |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 0 |  |  | MPCL SERV | 43
SOLIDS % | 9.9 | 7.9 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 0 |  |  | SECURITY | 5
M.B.T. (lb/bbl) | 25 | 23 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 100 | 2 X 100 |  | 30" CONDUCTOR |  |  | 37 | [11 empty] | TOTAL | 139
DAILY WELL COST (US$) |  | 29340 | SHAKER-2 | 1 X 50 | 2 X 50 |  | 20'' SURFACE/ K-55, 133# |  |  | 579 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 1286398 | SHAKER-3 | 1 X 100 | 2 X 100 | [16 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 6.462% | MUD CLEANER | 3 X 140 | [17 empty] | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR |  |  |  | P-1 - F-1600HL | 7 |  | 12" | 3430 PSI | 97% |  | 0.1385 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS |  |  |  | P-2 - F-1600HL | 7 |  | 12" | 3430 PSI | 97% |  | 0.1385 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS |  |  |  | P-3 - F-1600HL | 7 |  | 12" | 3430 PSI | 97% |  | 0.1385 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL
KICK DRILL |  |  | DIVERTER INFO |  | 29 1/2" - 500 psi |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD
TRIP DRILL |  |  | LAST BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | BRINE LOSSES IN 24 HRS |  |  |  |  | BRINE LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-11
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43596 | 43596.125 | 3 | DRL | PT-P | RC | CONT'D RIH 20'' CSG FROM 24M TO 150M. FILLED UP CSG EVERY JOINT. INSTALLED CENTRALIZERS AS PER PROGRAM.
43596.125 | 43596.1458 | 0.5 | DRL | PT-P | CIR | BROKE CIRCULATION.
43596.1458 | 43596.4375 | 7 | DRL | PT-P | RC | CONT'D RIH 20'' CSG FROM 150M TO 404 M. FILLED UP CSG EVERY JOINT. INSTALLED CENTRALIZERS AS PER PROGRAM.
43596.4375 | 43596.4688 | 0.75 | DRL | PT-P | CIR | M/UP CIRCULATING SWAGE & CIRCULATED FOR BOTTOM UP. NO CUTTINGS / CAVING OBSERVED AT BOTTOM UP.
43596.4688 | 43596.6875 | 5.25 | DRL | PT-P | RC | CONT'D RIH 20'' CSG FRO 404 M TO 579M. M/UP CIRCULATING SWAGE AND WASHED DOWN LAST CSG JT.
43596.6875 | 43596.75 | 1.5 | DRL | PT-P | CIR | CIRCULATED FOR BOTTOM UP. NO CUTTINGS/CAVINGS OBSERVED AT BTM UP.
43596.75 | 43596.9271 | 4.25 | DRL | PT-P | RIH | P/U & M/U STAB IN STINGER ASSEMBLY AND RIH ON 5 1/2''DP FROM SURFACE TO 547M.
43596.9271 | 43596.9688 | 1 | DRL | PT-P | RIH | P/UP 2 X 5 1/2'' DP SGL BY SGL. M/UP CIRCULATING SWAGE, RAN INSIDE CSG AND STAB IN STINGER IN FLOAT COLLAR WITH 6 TON COMPRESSION. CHAINED DOWN AND SECURED 20'' CSG AND DP's. TURNED ON PUMP & CONFIRM STAB IN BY RETURNS AT SHAKER. NO RETURNS OBSVD BETWEEN 5 1/2'' AND 20'' ANNULUS.
43596.9688 | 43597 | 0.75 | DRL | PT-P | CIR | CONT'D CIRCULATION TO CONDITION MUD AND REDUCE MUD RHEOLOGY, MEANWHILE PREPARED MIXED FLUID FOR CMT JOB.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-12
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43597 | 43597.0625 | 1.5 | DRL | PT-P | CIR | CONT'D CIRCULATION TO CONDITION MUD MEANWHILE PREPARED MIX FLUID FOR CMT JOB.
43597.0625 | 43597.0729 | 0.25 | DRL | PT-P | SM | HELD PJSM, DISCUSSED SAFETY ABOUT 20'' CSG CEMENTATION.
43597.0729 | 43597.0938 | 0.5 | DRL | PT-P | P/T | R/UP DOWELL LINES AND CONNECTED SAME WITH RIG PUMPS & DOWELL UNIT. FLUSHED DOWELL LINES WITH FRESH WATER, CLOSED VALVE AND P/TESTED SAME AT 500/4000 PSI, OK.
43597.0938 | 43597.25 | 3.75 | DRL | PT-P | CMC | PUMPED 300 BBL LO-VIS PILL FOLLOWED BY 100 BBL MUDPUSH II SPACER OF 12 PPG. WITH RIG PUMP @ 10 BPM. SWITCHED OVER TO CEMENT UNIT & PUMPED 580 BBL FLY MIXED LEAD SLURRY OF 13.5 PPG @ 5-6 BPM. OBSERVED SPACER CONTAMINATION AFTER PUMPING 480 BBL OF LEAD SLURRY, OBSERVED NEAT CMT SURFACED AFTER PUMPING 580 BBL, STOPPED PUMPING LEAD SLURRY AND SWITCHED OVER TO FLY MIXED 150 BBL TAIL SLURRY OF 15.8 PPG @ 5-6 BPM. DISPLACED CEMENT WITH 5 BBL SPACER + 30 BBL MUD. STOPPED PUMPING & CHECKED BACK FLOW - NO BACK FLOW. DUMPED RETURNS DURING CMT JOB. NO LOSSES OBSERVED DURING JOB.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | 20'' CSG CEMENT JOB CONCLUDED.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH 20'' CSG TO 579M, CIRCULATED FOR BTM UP, RIH STAB IN STINGER ASSEMBLY ON 5 1/2'' DP. STAB IN STINGER IN F/COLLAR AT 565M. CIRCULATION MEANWHILE PREPARED FOR CMT JOB.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | 20'' CSG CEMENT JOB, WOC.
REMARKS
Formulas:
MIRAJ-1 = [SPUD MUD]+30