## DDR # 01
9
MARI PETROLEUM COMPANY LIMITED
[22 empty] | Report No. |  | 1
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-22
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | SAIFULLAH TURK / MEHDI |  |  | MD/TVD @ 00:00HRS: |  | 105 | [6 empty] | DAYS SINCE SPUD: | [6 empty] | 0.58333
RIG REP.: |  | JAVED IQBAL / KHALID |  |  | MD/TVD @ 06:00HRS: |  | 132 | [6 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 64
2017-12-21 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | SPUD MUD |  | HOLE SIZE (IN) |  | 26" |  | BIT No. |  | 1 |  | 2 | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 3.01
CHECK TIME | 6:00 | 23:59 | MD @ 00:00HR (M) |  | 105 |  | SIZE (IN) |  | 26 |  | 26 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 221
DEPTH, MD (M) |  | 105 | TVD @ 00:00HR (M) |  | 105 |  | MANUFACTURER |  | BAKER |  | BAKER | 26"PDC BIT |  |  | 26 |  |  | 75/8 REG |  | 0.57 |  |  | PITS (BBL) | 943
MW IN (SG) |  | 1.06 | DAILY PROGRESS (M) |  | 64 |  | TYPE |  | GTX-CG1 |  | TD509S | BITSUB |  |  | 9.5 | 2.75 |  | 75/8 REG |  | 1.08 | 1.5 |  | ACT. SYS (BBL) | 1143
MW OUT (SG) |  | 1.06 | INST. ROP (M/HR) |  | 6.1 |  | SERIAL NO. |  | 5259839 |  | 5278922 | SHOCK SUB |  |  | 12 | 3 |  | 75/8 REG |  | 4.16 | 2 |  | RESV. SYS (BBL) | 0
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 6.9 |  | IADC CODE |  | 115 |  | S423 | 2X11" DCS |  |  | 11 | 3 |  | 75/8 REG |  | 18.32 | 8 |  | KILL MUD (BBL) | 0
FL TEMP. °F |  | 82.4 | AVG. WOB (TON) |  | 4 |  | NOZZLES |  | 4X20 |  | 9X14 | 26"S.STB |  |  | 26 | 3.125 |  | 75/8 REG |  | 2.34 | 1 |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 75 | AVG. RPM SURFACE |  | 90 |  | DEPTH IN (M) |  | 41 |  | 47 | 1X11" DC |  |  | 11 | 3 |  | 75/8 REG |  | 9.2 | 4 |  | TOTAL | 1143
PV |  | 12 | AVG. RPM DOWNHOLE |  | 90 |  | DEPTH OUT (M) |  | 47 |  |  | 6X9.5" DC |  |  | 9.5 | 3 |  | 75/8 REG |  | 55.58 | 18 |  | DIESEL (LTR)
YIELD POINT |  | 31 | FLOWRATE (GPM) |  | 900 |  | METERAGE (M) |  | 6 |  | 58 | [11 empty] | RIG TANK | 98500
GEL ST. |  | 15/30 | PRESSURE (PSI) |  | 830 |  | RPM SURF. |  |  |  | 90 | [11 empty] | CAMP TANK | 24300
WL (ml/30 min.) |  |  | TORQ. ON-BTM (KLB-FT) |  | 6 |  | RPM BTM. |  |  |  | 90 | [11 empty] | CONSUMED | 3268
CT ( in/32) |  | 2 | TORQ. OFF-BTM (KLB-FT) |  | 3 |  | WOB (TON) |  |  |  | 1-6 | [11 empty] | RECEIVED
ALK (MUD) |  |  | STRING WT. (TON) - ROT |  | 68 |  | AVG. ROP (M/HR) |  |  |  | 6.913 | [11 empty] | TOTAL | 122800
ALK (FILT.) |  |  | PICK-UP WT. (TON) |  | 70 |  | BIT ROT HRS. |  |  |  | 8.39 | [11 empty] | WATER (LTR)
PH |  | 10 | SLACK-OFF WT. (TON) |  | 68 |  | K-REVS IN 24 HRS |  |  |  | 45.3 | [11 empty] | RIG STORAGE
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  |  | 45.3 | [11 empty] | CAMP STORAGE
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  |  | 11.4 | [11 empty] | CONSUMED
Nacl (mg/l) |  | 330 | JAR |  | NMDC |  | JET VELOCITY (M/SEC) |  |  |  | 64.5 | [11 empty] | RECEIVED
CHLORIDES |  | 200 | 3.5" HWDPS |  | STAB - 1 |  | TFA (IN²) |  |  |  | 1.35 | [11 empty] | TOTAL
CALCIUM |  | 120 | 4.75'' DCS |  | STAB - 2 |  | HSI |  |  |  | 3.21 | [11 empty] | POB
OIL% |  |  | ANY OTHER |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  |  | TOTAL LENGTH (M) | [7 empty] | 91.25 |  |  | MPCL | 3
SAND % |  | 0.5 | BHA ROT. HRS |  | 9.21 |  | BIT No. 1 |  | 1/1/WT/A/E/I/-/BHA |  |  | BHA WT. IN MUD (TON) | [7 empty] | 29.325 |  |  | MPCL SERV | 16
SOLIDS % |  | 4 | ON BOTTOM HRS |  | 9.21 | [6 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. |  | 20 | CIRC. HRS |  | 10.5 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) |  | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 22
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 50 | 2 X 50 |  | 20" SURFACE CASING |  |  |  |  | 66 |  | 0.5 | [8 empty] | TOTAL | 105
DAILY WELL COST (US$) |  | 1588896 | SHAKER-2 | 1 X 50 | 2 X 50 |  | 13 3/8" INTERMEDIATE CSG | [15 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 1588896 | SHAKER-3 | 1 X 50 | 2 X 50 |  | 9 5/8" PRODUCTION CSG | [15 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 8.803% | MUD CLEANER | 3 X 200 |  |  | 7" LINER | [15 empty] | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE |  | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR |  |  |  | P-1 - F-1600HL | 6.5 |  | 12" |  | 3980 PSI | 97% |  | 0.119 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS |  |  |  | P-2 - F-1600HL | 6.5 |  | 12" |  | 3980 PSI | 97% |  | 0.119 | [7 empty] | CHINJI
FIRE DRILL |  |  | BLIND RAMS |  |  |  | P-3 - F-1600HL | 6.5 |  | 12" |  | 3980 PSI | 97% |  | 0.119 | [7 empty] | KAMLIAL
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE
KICK DRILL |  |  | DIVERTER INFO |  | 29 1/2" - 500 psi |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | BRINE LOSSES IN 24 HRS |  |  |  |  | BRINE LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2017-12-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
CARRIED OUT FINAL RIG INSPECTION PRIOR TO SPUD. CONDUCTED 16" MAGNET TRIP. M/U & RACKED-BACK DP & DC STANDS (25 NOS.). WELDED DIVERTER FLANGE AND R/U DIVERTER ALONG WITH VENT LINES.
SACRIFICED TWO GOATS - GLORIFIED ALLAH JALASHNAHOO & OFFERED SUPPLICATIONS FOR SAFE & SUCCESSFULL OPERATIONS. SPUDDED WELL DHARIAN-1 @ 10:00 HRS ON DECEMBER 21, 2017.
43090.4167 | 43090.625 | 5 | DRL | PT-P | D | RIH 26"TC BIT WITH SLICK BHA TO 41M & DRILLED 26" HOLE FROM 41M TO 47M TO TO CHECK IF HOLE IS FREE FROM ANY JUNK / DEBRIS. M/UP 26" PDC BIT+ BIT SUB + 12" SHOCK SUB & RIH DOWN TO 47M. RESUMED DRILLING AFTER BIT BREAKING. DRILLED 26" HOLE FROM 47M TO 71M WITH CONTROLLED PARAMETERS.
43090.625 | 43090.6458 | 0.5 | DRL | PT-P | CIR | CIRCULATED HOLE CLEAN PRIOR TO DROP TOTCO.
43090.6458 | 43090.6562 | 0.25 | DRL | PT-P | S | DROPPED TOTCO. PULLED BACK TO 66 M. ALLOWED TO RECORD. OBSERVED WELL FOUND WELL STATIC
43090.6562 | 43090.6875 | 0.75 | DRL | PT-P | POOH | POOH TO SURFACE FOR ADDING S.STAB IN BHA. RECOVERED TOTCO. DEV=0.5° @ 65M
43090.6875 | 43090.7396 | 1.25 | DRL | PT-P | RIH | RIH WITH 26" PDC BIT DOWN TO BOTTOM. ADDED 26" S.STAB.
43090.7396 | 43090.8854 | 3.5 | DRL | PT-P | D | RESUMED DRILLING. DRILLED 26" HOLE DOWN TO 93M.
43090.8854 | 43090.9271 | 1 | DRL | PT-P | BHA | P/U & M/U 3 X 9 1/2" DC JOINT IN BHA.
43090.9271 | 43091 | 1.75 | DRL | PT-P | D | DRILLED 26" HOLE FROM 93M TO 105M
TOTAL |  | 14
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2017-12-22
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43091 | 43091.0938 | 2.25 | DRL | PT-P | D | CONTINUED DRILLING. DRILLED 26" HOLE FROM 105M TO 120M.
43091.0938 | 43091.1146 | 0.5 | DRL | PT-P | CIR | CIRCULATED HOLE CLEAN PRIOR TO DROP TOTCO.
43091.1146 | 43091.1354 | 0.5 | DRL | PT-P | S | P/BACK TO 110M & RECORDED TOTCO DEVIATION SURVEY ON SLICKLINE (DEV: 0.5° @ 110M).
43091.1354 | 43091.1458 | 0.25 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE.
43091.1458 | 43091.1979 | 1.25 | DRL | PT-P | BHA | P/U & M/U 2 X 8" DC JOINT AND DRILLING JAR IN BHA.
43091.1979 | 43091.25 | 1.25 | DRL | PT-P | D | CONTINUED DRILLING. DRILLED 26" HOLE FROM 120M TO 132M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | NAGRI (70% SAND 30% CLAY)
OPERATIONS AT 06:00 HRS |  |  | DRILLING OF 26" HOLE.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | M/UP 5" DP STANDS, PREPARED SPUD MUD, INSPECTED & FUNCTION TESTED RIG & CONDUCTED MAGNET TRIP. SPUD-IN WELL & DRILLED 26" HOLE TO 105M. RECORDED TOTCO DEVIATION SURVEY. ADDED STRING STAB.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 26" HOLE & RECORD TOTCO DEVIATION SURVEY.
REMARKS |  |  | NOTE: 14 hrs consumed in making Stands & R/U Diverter.