## DDR # 10
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 10
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-31
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR RAO / M. MOHSIN ALI |  |  | MD/TVD @ 00:00HRS: |  | 595 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 9.5833
RIG REP.: |  | JAVED IQBAL / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 595 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2017-12-30 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | SPUD MUD |  | HOLE SIZE (IN) |  |  |  | BIT No. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | -
CHECK TIME | 23:59 |  | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 691.8
DEPTH, MD (M) | 595 |  | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER | [14 empty] | PITS (BBL) | 786
MW IN (SG) | 1.12 |  | DAILY PROGRESS (M) |  |  |  | TYPE | [14 empty] | ACT. SYS (BBL) | 1477.8
MW OUT (SG) | 1.12 |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | RESV. SYS (BBL) | 1073
ECD (SG) | - |  | AVG. ROP (M/HR) |  |  |  | IADC CODE | [14 empty] | KILL MUD (BBL) | -
FL TEMP. °F | - |  | AVG. WOB (TON) |  |  |  | NOZZLES | [14 empty] | KILL MW (SG) | -
µ FUNNEL (SEC) | 55 |  | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 2550.8
PV | 14 |  | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT | 19 |  | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 131400
GEL ST. | 14/17 |  | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 18000
WL (ml/30 min.) | 10 |  | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 4200
CT ( in/32) | 2 |  | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  |  | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 149400
ALK (FILT.) |  |  | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9.5 |  | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 300000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 250680
NaCl (mg/l) | 495 |  | JAR |  | NMDC |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 195680
CHLORIDES | 300 |  | 5" HWDPS |  | STAB - 1 |  | TFA (IN²) | [14 empty] | TOTAL | 345000
CALCIUM | 140 |  | 8" DCS |  | STAB - 2 |  | HSI | [14 empty] | POB
OIL% | 2 |  | ANY OTHER |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 3
SAND % | - |  | BHA ROT. HRS |  |  |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 18
SOLIDS % | 4.98 |  | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | -
M.B.T. | 20 |  | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 14
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 35 | 2 X 35 |  | 20" SURFACE CASING |  |  | 594 | 496 |  | 1.01 |  | 132.42 |  |  |  |  | EMS |  | TOTAL | 110
DAILY WELL COST (US$) |  | 69163.9242 | SHAKER-2 | 1 X 35 | 2 X 35 |  | 13 3/8" INTERMEDIATE CSG |  |  |  | 525 |  | 1.26 |  | 139.45 |  |  |  |  | EMS |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 2094156.3802 | SHAKER-3 | 1 X 80 | 2 X 50 |  | 9 5/8" PRODUCTION CSG |  |  |  | 554 |  | 1.44 |  | 142.41 |  |  |  |  | EMS |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 11.6% | MUD CLEANER | 3 X 200 |  |  | 7" LINER |  |  |  | 583 |  | 1.06 |  | 135.73 |  |  |  |  | EMS |  | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | China | 20.75 | 3000 | P-1 - F-1600HL | 6.5 |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | China | 20.75 | 3000 | P-2 - F-1600HL | 6.5 |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | CHINJI | 342
FIRE DRILL | 26-12-2017 |  | BLIND RAMS | China | 20.75 | 3000 | P-3 - F-1600HL | 6.5 |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | KAMLIAL
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  |  |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2017-12-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43099 | 43099.2604 | 6.25 | DRL | PT-P | WOC | WOC. MEANWHILE P/U 5" G-105 DP SINGLE BY SINGLE AND MADE STANDS.
43099.2604 | 43099.3125 | 1.25 | DRL | PT-P | CC | SLACKED OFF 20" CASING WEIGHT SUCCESSFULLY. CUT 30" CONDUCTOR & ROUGH CUT 20" CASING.
43099.3125 | 43099.3958 | 2 | DRL | PT-P | WH | L/DOWN LANDING JOINT, RISER PIPE & N/DOWN DIVERTER.
43099.3958 | 43099.5417 | 3.5 | DRL | PT-P | WH | CUT & L/DOWN 30" CONDUCTOR FROM CELLAR BASE. FINAL CUT 20" CASING AT 0.76M. GRINDED / DRESSED 20" CASING STUB.
43099.5417 | 43099.5833 | 1 | DRL | PT-P | TU | PERFORMED TOP CEMENT JOB & FILLED 0.9 M, 26" X 20" ANNULUS WITH CMT.
43099.5833 | 43099.625 | 1 | DRL | PT-P | WH | INSTALLED, LEVELED & LOCKED (20" SOL X 21 1/4" - 5K) CHH ON 20" CASING STUB.
43099.625 | 43099.6667 | 1 | DRL | PT-P | WH | PRESS TESTED CHH @ 900 PSI & HELD PRESS FOR 15 MIN - FOUND OK. PREPARING TO N/U BOP STACK.
43099.6667 | 43100 | 8 | DRL | PT-P | NUB | N/U 21 1/4" - 5K SPACER SPOOL, DSAF, DRILLING SPOOL, 20 3/4" - 3K DOUBLE RAM & ANNULAR BOP. H/U CHOKE & KILL LINES. MODIFIED & INSTALLED BELL NIPPLE, FLOW LINE & F/UP LINE. CONNECTED BOP HOSES.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2017-12-31
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43100 | 43100.0417 | 1 | DRL | PT-P | NUB | FUNCTION TESTED BOP STACK.
43100.0417 | 43100.0833 | 1 | DRL | PT-P | BOPT | HELD PJSM. FLUSHED BOP STACK WITH WATER. M/U TEST PLUG ASSY & SET TEST PLUG INSIDE CHH.
43100.0833 | 43100.25 | 4 | DRL | NPT-UP | BOPT | TRIED TO P/T ANNULAR BOP - OBSERVED LEAKAGE BETWEEN DOUBLE RAM BOP AND DRILLING SPOOL FLANGE. RETRIEVED TEST PLUG & L/DOWN TEST PLUG ASSY. DISMANTLED FLOW LINE. LOOSENED NUTS & BOLTS OF DOUBLE RAM BOP AND DRILLING SPOOL FLANGE. LIFTED BOP STACK AND REPLACED R-74 GASKET. TIGHTENING NUTS & BOLTS OF DOUBLE RAM BOP AND DRILLING SPOOL FLANGE IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | TIGHTENING NUTS & BOLTS OF DOUBLE RAM BOP AND DRILLING SPOOL FLANGE.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | WOC. CUT 30" CONDUCTOR & ROUGH CUT 20" CASING. L/DOWN LANDING JOINT, RISER PIPE & N/DOWN DIVERTER. CUT & L/DOWN 30" CONDUCTOR FROM CELLAR BASE. FINAL CUT 20" CASING. PERFORM TOP CEMENT JOB. INSTALLED CHH AND P/T @ 900 PSI. N/U BOP STACK.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | PERFORM BOP P/T. RIH PERFORMANCE BHA. DRILL FLOAT COLLAR AND SHOE TRACK. P/T CASING. DRILL FLOAT SHOE, RAT HOLE & 2-3 M OF NEW FORMATION. PERFORM LOT/FIT. DRILL 17 1/2" HOLE SECTION.
REMARKS