## DDR#10
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 10
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-14
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / ADNAN |  |  | MD/TVD @ 00:00HRS: |  | 580 / 580 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 9.9792
RIG REP.: |  | TARIQ BUTT / JAVED MUGHAL / FAYYAZ |  |  | MD/TVD @ 06:00HRS: |  | 580 / 580 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2019-05-13 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | SPUD MUD |  | HOLE SIZE (IN) |  |  |  | BIT No. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 12:00 | 23:45 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 648.48
DEPTH, MD (M) |  | 580 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER | [14 empty] | PITS (BBL) | 420
MW IN (SG) |  | 1.1 | DAILY PROGRESS (M) |  |  |  | TYPE | [14 empty] | ACT. SYS (BBL) | 1068.48
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | RESV. SYS (BBL) | 400
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE | [14 empty] | KILL MUD (BBL) | 400
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES | [14 empty] | KILL MW (SG) | 1.6
µ FUNNEL (SEC) |  | 75 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 1468.48
PV |  | 18 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT |  | 24 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 103396
GEL ST. |  | 14/19 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 24860
WL (ml/30 min.) |  |  | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 4791
CT ( in/32) |  |  | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  |  | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 128256
ALK (FILT.) |  |  | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 470000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 90000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 142100
KCl (mg/l) |  | 2478.7 | JAR |  | NMDC |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 142100
CHLORIDES (mg/l) |  | 1500 | MOTOR |  | STAB - 1 |  | TFA (IN²) | [14 empty] | TOTAL
HARDNESS (mg/l) |  | 240 | 11'' DCS |  | STAB - 2 |  | HSI | [14 empty] | POB
OIL% |  |  | 9 1/2" DCS |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 4
SAND % |  |  | BHA ROT. HRS |  |  |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 20
SOLIDS % |  | 8.92 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 5
M.B.T. (lb/bbl) |  | 25 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 57
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 100 | 2 X 100 |  | 30" CONDUCTOR |  |  | 37 | [11 empty] | TOTAL | 117
DAILY WELL COST (US$) |  | 37874 | SHAKER-2 | 1 X 100 | 2 X 100 |  | 20'' SURFACE/ K-55, 133# |  |  | 579 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 1581761 | SHAKER-3 | 1 X 100 | 2 X 100 | [16 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 7.946% | MUD CLEANER | 3 X 140 | [17 empty] | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 7 |  | 12" | [11 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 7 |  | 12" | [11 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 7 |  | 12" | [11 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-05-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | BRINE LOSSES IN 24 HRS |  |  |  |  | BRINE LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2019-05-28 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-13
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43598 | 43598.0833 | 2 | DRL | PT-P | WH | INSTALLED, LEVELED & LOCKED (20" SOL X 21 1/4" - 5K) CHH ON 20" CASING STUB. P/TESTED CHH @ 900 PSI & HELD PRESS FOR 10 MIN -OK.
43598.0833 | 43598.5 | 10 | DRL | PT-P | NUB | N/UP 21 1/4'', 5K BOP STACK.
43598.5 | 43598.6667 | 4 | DRL | NPT-UP | NUB | CONT'D N/UP 21 1/4'', 5K BOP STACK.
43598.6667 | 43598.75 | 2 | DRL | NPT-UP | BOPT | HELD PJSM, FLUSHED BOP STACK WITH WATER. M/UP TEST PLUG ASSEMBLY, INSTALLED TEST PLUG IN CHH, WHILE P/TESTING OBSERVED LEAKAGE FROM MUD CROSS x TWIN RAM CONNECTION. RETRIEVED TEST PLUG FROM CHH.
43598.75 | 43599 | 6 | DRL | NPT-UP | NDB | LOOSENED NUTS/BOLTS OF CONNECTION, LIFTED BOP STACK TO CHECK POTENTIAL PROBLEM. SERVICED TOP FLANGE GROOVE, REPLACED GASKET RING.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-14
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43599 | 43599.0625 | 1.5 | DRL | NPT-UP | NUB | N/UP 21 1/4'', 5K BOP STACK.
43599.0625 | 43599.25 | 4.5 | DRL | NPT-UP | BOPT | HELD PJSM, FLUSHED BOP STACK WITH WATER. P/UP AND M/UP TEST PLUG ASSEMBLY, INSTALLED TEST PLUG INSIDE 21 1/4'' CHH. P/TESTED ANNULAR BOP AT 300/3000 PSI FOR 5 / 10 MINS OK. P/TESTED HCR & MANUAL VALVES AT CHOKE /KILL LINE AT 300/3000 PSI FOR 5 /10 MINS, OK. P/TESTED 5 1/2 FH FOSV, IBOP, ROTARY HOSE, STAND PIPE MANIFOLD VALVES AT 300/3000 PSI FOR 5 / 10 MINS OK. P/TESTED CO-FLEXIP, MASTER VALVE AT CHOKE MANIFOLD & CHECK VALVE AT KILL LINE & OUTER FLANGE AT CHECK VALVE AT 300/3000 PSI FOR 5 / 10 MINS, OK. RETRIEVED TEST PLUG AND INSTALLED WEAR BUSHING.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | L/DOWN TEST ASSEMBLY IN PROGRESS.
OPERATIONS AT 06:00 HRS |  |  | N/UP BOP IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | WOC, MEANWHILE INSTALLED WELL HEAD AND P/TESTED SAME, N/UP BOP IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | N/UP BOP, BOPT, FIX BELL NIPPLE, FLOW LINE, P/UP & M/UP 5 1/2'' DP STDS, P/UP & RIH WITH SLICK BHA FOR COC.
REMARKS |  |  | FMC WELL HEAD ENGR. RELEASED, CHANGED MUD PUMP LINERS TO 6''.
Formulas:
MIRAJ-1 = [SPUD MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14