## DDR#102
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 102
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-04-02
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | SAIFULLAH TURK / MUHAMMAD AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4007 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 101.5833
RIG REP.: |  | JAVED IQBAL MUGHAL / IMRAN JAWAD |  |  | MD/TVD @ 06:00HRS: |  | 4007 | [5 empty] | DAILY PROGRESS @ 00:00HRS:
2018-04-01 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT No. |  | 6RR1 |  |  |  |  | 13 | IN (M) |  | 4007 |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 15:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 12 1/4" |  |  |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1891
DEPTH, MD (M) |  | 4007 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | SMITH |  | PDC BIT |  |  | 12.25 | 3.25 |  | 6 5/8 REG |  | 0.27 | 0.1 |  | PITS (BBL) | 1055
MW IN (SG) |  | 2.2 | DAILY PROGRESS (M) |  |  |  | TYPE |  | MDSiZ616 |  | BIT SUB |  |  | 8.5 | 3 |  | 6 5/8 REG |  | 1.07 | 0.4 |  | ACT. SYS (BBL) | 2946
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | JN 5197 |  | 2 X 8" DCS |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 18.25 | 4.0752 |  | RESV. SYS (BBL) | 1153
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | - |  | STRING STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.45 | 0.5 |  | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 6 x 18/32" |  | 1 X 8" DCS |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.3 | 2.0767 |  | KILL MW (SG) | 2.3
µ FUNNEL (SEC) |  | 67 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4007 |  | STRING STAB |  |  | 12.125 | 2.8125 |  | 6 5/8 REG |  | 1.95 | 0.5 |  | TOTAL | 4699
PV |  | 44 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 6 X 8" DCS |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 55.41 | 12.373 |  | DIESEL (LTR)
YIELD POINT |  | 36 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | DRILLING JAR |  |  | 7.75 | 3 |  | 6 5/8 REG |  | 5.63 | 1.2572 |  | RIG TANK | 108000
GEL ST. |  | 23/46 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 3 X 8" DC'S |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 27.83 | 6.2144 |  | CAMP TANK | 19000
WL (ml/30 min.) |  | 6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | X/OVER |  |  | 8.125 | 3 |  | 6 5/8 REG |  | 0.74 | 0.16524 |  | CONSUMED | 6000
CT ( in/32) |  | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 6 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 55.96 | 4.1653 |  | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 127000
ALK (FILT.) |  | 0.4 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 91160
KCl (mg/l) |  | 42900.8 | JAR | 0 | NMDC |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 91160
CHLORIDES |  | 20000 | 5" HWDPS | 0 | STAB - 1 | 0 | TFA (IN²) |  | 1.49 | [12 empty] | TOTAL | 495000
CALCIUM |  | 180 | 8" DCS | 0 | STAB - 2 | 0 | HSI | [14 empty] | POB
OIL% |  | 4 | 9 1/2" DCS |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 178.86 |  |  | MPCL | 3
LUBE % |  | 2 | BHA ROT. HRS |  | 0 |  | BIT No. 6RR1 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 23 |  |  | MPCL SERV | 15
SOLIDS % |  | 38.34 | ON BOTTOM HRS |  | 0 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 15 |  |  | SECURITY | 4
M.B.T. |  | 12.5 | CIRC. HRS |  | 0 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 13
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 27
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 140 | 2 X 140 |  | 20" SURFACE CASING |  |  | 594 | 3478 |  | 0.51 |  | 138.13 |  |  | 0.14 |  | MWD |  | TOTAL | 112
DAILY WELL COST (US$) |  | 31105.4013 | SHAKER-2 | 1 X 140 | 2 X 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 3502 |  | 0.66 |  | 136.87 |  |  | 0.19 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 7670432.1125 | SHAKER-3 | 1 X 140 | 2 X 120 |  | 9 5/8" PRODUCTION CSG |  |  |  | 3531 |  | 0.83 |  | 141.02 |  |  | 0.18 |  | MWD |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 42.5% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 3559 |  | 0.78 |  | 132.49 |  |  | 0.14 |  | MWD |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-03-31 | 2018-04-21 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-03-16 | 2018-04-15 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-03-16 | 2018-04-06 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-03-16 | 2018-04-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-04-01 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-03-16 | 2018-04-15 | NEXT BOP TEST DATE |  | 2018-04-15 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-04-01
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43191 | 43191.0104 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43191.0104 | 43191.1667 | 3.75 | DRL | PT-P | BHA | POOH FROM 183M TO SURFACE WHILE L/DOWN COMPLETE BHA FOR INSPECTION.
43191.1667 | 43191.2292 | 1.5 | DRL | PT-P | BOPT | HELD PJSM. M/UP & RIH TEST PLUG ASSY, RETRIEVED WEAR BUSHING & SET TEST PLUG IN 13 5/8" CHS. FLUSHED BOP STACK WITH WATER. WHILE ATTEMPTING TO P/TEST UPPER VARIABLE PIPE RAMS (4 1/2" - 7"), OBSERVED LEAKAGE IN TDS WASH PIPE.
43191.2292 | 43191.2917 | 1.5 | DRL | NPT-UP | RR | REPLACED & P/TESTED TDS WASH PIPE @ 5000 PSI - OK. WHILE REPLACING TDS WASH PIPE; P/TESTED UPPER VARIABLE PIPE RAMS (4 1/2" - 7"), HCR & MANUAL VALVES @ KILL LINE / CHOKE LINE & TDS MANUAL IBOP @ 300 PSI / 6500 PSI FOR 5 MIN / 10 MIN - OK.
43191.2917 | 43191.3958 | 2.5 | DRL | PT-P | BOPT | P/TESTED ANNULAR BOP, ROTARY HOSE / STANDPIPE @ 300 PSI / 5000 PSI FOR 5 MIN / 10 MIN - OK. P/TESTED LOWER PIPE RAM BOP (5" RAMS), KILL LINE CHECK VALVE @ 300 PSI / 6500 PSI FOR 5 MIN / 10 MIN - OK. P/TESTED BLIND RAM BOP + CHECK VALVE BODY + HYD IBOP @ 300 PSI / 6500 PSI FOR 5 MIN /10 MIN. BLIND RAM BOP & CHECK VALVE BODY OK. FOUND HYD IBOP LEAKING. RETRIEVED TEST PLUG & SET WEAR BUSHING. L/D TEST PLUG ASSEMBLY.
43191.3958 | 43191.5 | 2.5 | DRL | NPT-UP | RR | WORKED ON TDS. CARRIED OUT MAINTENANCE CHECK UP OF TDS GEAR BOX - FOUND GEAR BOX OK.
43191.5 | 43191.5208 | 0.5 | DRL | NPT-P | RS | SERVICED TDS.
43191.5208 | 43191.6771 | 3.75 | DRL | PT-P | BHA | M/UP & RIH 12 1/4" PDC BIT # 6 (RR1) WITH PENDULUM BHA TO 178M. WHILE RIH P/UP, DRIFTED & FLUSHED BHA SINGLE BY SINGLE FROM CATWALK.
43191.6771 | 43191.9375 | 6.25 | DRL | PT-P | RIH | RIH FROM 178M TO 1746M. WHILE RIH P/UP 15 X 5" DPS (G-105) FROM CAT WALK & L/DOWN 9 X 5" DPS (G-105) DUE TO WORN OUT TOOL JOINTS. FILLED UP STRING WITH MUD AFTER EVERY 15 STANDS.
43191.9375 | 43192 | 1.5 | DRL | NPT-UP | RR | OPENED TDS PIPE HANDLER & REPLACING TDS HYD IBOP IN PROGRESS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-04-02
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43192 | 43192.0729 | 1.75 | DRL | NPT-UP | RR | REPLACED & P/TESTED TDS HYD IBOP @ 6000 PSI - OK.
43192.0729 | 43192.25 | 4.25 | DRL | PT-P | RIH | RIH FROM 1746M TO 3006M. WHILE RIH L/DOWN 6 X 5" DPS (G-105) DUE TO WORN OUT TOOL JOINTS. FILLED UP STRING WITH MUD AFTER EVERY 15 STANDS
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE & SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH 12 1/4" BIT
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | P/TESTED BOP STACK. M/UP & RIH 12 1/4" PDC BIT # 6 (RR1) WITH INSPECTED BHA TO 1746M. REPLACED TDS HYD IBOP.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH TO BTM & DRILL AHEAD 12 1/4" HOLE.
REMARKS
Formulas:
DHARIAN - 1 = [KCL LIGNOSULPHONATE]+21
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14