## DDR#102
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 102
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-08-14
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIF ULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4052 | 4052 |  |  | M |  |  | DAYS SINCE SPUD: | [6 empty] | 101.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4052 | 4052 |  |  | M |  |  | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2019-08-13 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | BIT NO. |  |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 4052 |  | SIZE (IN) |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1958.8
DEPTH, MD (M) | 4052 | 4052 | TVD @ 00:00HR (M) |  | 4052 |  | MANUFACTURER | [15 empty] | PITS (BBL) | 611.2
MW IN (SG) | 2.27 | 2.27 | DAILY PROGRESS (M) |  |  |  | TYPE | [15 empty] | ACT. SYS (BBL) | 2570
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [15 empty] | RESV. SYS (BBL) | 2120
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE | [15 empty] | KILL MUD (BBL) | 0
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") | [15 empty] | KILL MW (SG) | 0
µ FUNNEL (SEC) | 58 | 60 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [15 empty] | TOTAL | 4690
PV | 44 | 45 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [15 empty] | DIESEL (LTR)
YIELD POINT | 28 | 27 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [15 empty] | RIG TANK | 104191
GEL ST. | 22/31 | 23/32 | PRESSURE (PSI) |  |  |  | RPM SURF. | [15 empty] | CAMP TANK | 19418
WL (ml/30 min) | 5.1 | 5.2 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | CONSUMED | 8053
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [15 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [15 empty] | TOTAL | 123609
ALK (FILT.) | 0.4/2.8 | 0.4/2.7 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | WATER (LTR)
PH | 9.6 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [15 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CAMP STORAGE | 85000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | CONSUMED | 107300
KCl (mg/l) | 45761 | 44807.5 | JAR |  | STAB - 1 | 0 | JET VELOCITY (M/SEC) | [15 empty] | RECEIVED | 142300
CHLORIDES (mg/l) | 25000 | 25000 | 5 1/2" HWDPS |  | STAB - 2 |  | TFA (IN²) | [15 empty] | TOTAL | 535000
HARDNESS (mg/l) | 380 | 400 | 9 1/2" DCS |  | STAB - 3 |  | HSI | [15 empty] | POB
PENETREX % | 2 | 2 | 8" DCS |  | SPSA | 0 | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 0 |  |  | MPCL | 4
OIL % | 4 | 4 | DAILY BHA ROT. HRS |  |  |  | BIT NO. 11 RR1 |  |  | 1-2-WT-A-X-I-BT-DTF |  | BHA WT. IN MUD (TON) | [7 empty] | 0 |  |  | MPCL SERV | 23
SOLIDS % | 43.01 | 43.11 | DAILY ON BOTTOM HRS | [8 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 0 |  |  | SECURITY
M.B.T. (lb/bbl) | 12.5 | 12.5 | DAILY CIRC. HRS | [8 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 48
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 3944 |  | 0.17 |  | 203.5 |  |  | 1.23 |  | MWD |  | TOTAL | 106
DAILY WELL COST (US$) |  | 42541 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 3973 |  | 0.03 |  | 138.51 |  |  | 0.17 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 8519385 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 3997 |  | 0.05 |  | 77.88 |  |  | 0.05 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 42.8% | MUD CLEANER | 3 x 170 | [7 empty] | 4030 |  | 0.22 |  | 70.43 |  |  | 0.16 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.26SG) | [5 empty] | MAASP (PSI) | 171.749
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4042 | 500/500/490 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4042 | 580/600/600 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-07-19 | 2019-08-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50/80 |  | 4042 | 630/625/630/1000 |  |  | CHINJI | 338/338
PIT DRILL | 2019-07-17 | 2019-08-16 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL | 2019-08-04 | 2019-08-18 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-08-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-07-19 | 2019-08-18 | NEXT BOP TEST DATE |  | 2019-08-28 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-13
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43690 | 43690.2812 | 6.75 | DRL | PT-P | RW | CONT'D PUMP OUT OF HOLE FROM 3237M TO 2420M, OBSERVED TIGHT SPOTS AT 2964M, 2735M & 2458M. CLEARED SAME WITH BACK REAMING.
43690.2812 | 43690.2917 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43690.2917 | 43690.6458 | 8.5 | DRL | PT-P | RW | CONT'D PUMP OUT OF HOLE FROM 2420M TO 1000M.
43690.6458 | 43690.6562 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43690.6562 | 43690.8021 | 3.5 | DRL | PT-P | POOH | POOH FROM 1000M TO 237M (BHA TOP).
43690.8021 | 43690.8125 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43690.8125 | 43691 | 4.5 | DRL | PT-P | BHA | POOH BHA FROM 237M TO 5M. WHILE POOH, L/DOWN SGL BY SGL ALL BHA COMPONENTS & RETRIEVED MWD TOOL (9 X 5.5'' HWDP's, 12 X 8''DC's, D.JAR, SPSA, PBL SUB, 12 1/8'' ST. STAB)
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-14
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43691 | 43691.0208 | 0.5 | DRL | PT-P | BHA | B/OUT AND L/DOWN SCHL PD & 12 1/4'' PDC BIT.
43691.0208 | 43691.2396 | 5.25 | DRL | PT-P | BOPT | M/UP TEST ASSEMBLY, RETRIEVED WEAR BUSHING. RIH 3 STDS OF 5 1/2" DP BELOW PLUG & SET TEST PLUG IN 13-5/8" CHS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP @ 400/4500 PSI FOR 5/10 MIN - OK. PRESSURE TESTED ROTARY HOSE & STAND PIPE VALVES @ 400/5000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER (VARIABLE 4 1/2"-7") & LOWER (5 1/2") PIPE RAM, HCR & MANUAL VALVES OF KILL & CHOKE LINE, FOSV, HYD & MANUAL IBOP @ 400/8000 PSI FOR 5/10 MIN. PRESSURE TESTED BLIND/SHEAR RAM AND CO-FLEXIP-MASTER VALVE AT CHOKE MANIFOLD @ 400/8000 PSI FOR 5/10 MIN - OK. RETRIEVED TEST PLUG, INSTALLED WEAR BUSHING. L/DOWN TEST PLUG ASSEMBLY.
43691.2396 | 43691.25 | 0.25 | DRL | PT-P | BHA | P/UP AND M/UP 12 1/4'' RR PDC BIT + 12 1/8'' NBS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | P/UP & M/UP 12 1/4'' RR PDC BIT + 12 1/8'' NBS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D PUMP OUT OF HOLE FROM 3237M TO 2402M, CLEARED TIGHT SPOTS AT 2964M, 2735M & 2458M WITH B/REAMING, FLOW CHECKED-WELL STATIC. CONT'D PUMP OUT OF HOLE FROM 2420M TO 1000M, POOH FROM 1000M TO 5M, WHILE POOH L/DOWN ALL BHA COMPONENTS SGL BY SGL.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | L/DOWN SCHL PD & PDC BIT, PERFORM BOP TEST AS PER POLICY, P/UP AND M/UP 12 1/4'' RR PDC BIT + ROTARY BHA. RIH TO BTM AT 4052M, RESUME DRILLING.
REMARKS
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14