## DDR#103
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 103
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-08-15
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIF ULLAH / MASOOD / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4052 | 4052 |  |  | M |  |  | DAYS SINCE SPUD: | [6 empty] | 102.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4052 | 4052 |  |  | M |  |  | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2019-08-14 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  | 10RR |  | BHA NO. |  |  | 21 | IN (M) |  | 4052 |  | OUT (M) |  |  | STRING (BBL) | 172
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 12.25" |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1694.6
DEPTH, MD (M) | 4052 | 4052 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  | NOV |  | PDC BIT |  |  | 12.25 |  |  |  |  | 0.43 |  |  | PITS (BBL) | 688
MW IN (SG) | 2.27 | 2.27 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  | TK66M |  | NEAR BIT STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 1.66 | 0.37068 |  | ACT. SYS (BBL) | 2554.6
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | E 243361 |  | PONY DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 4.38 | 0.97805 |  | RESV. SYS (BBL) | 2201
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.49 | 0.55601 |  | KILL MUD (BBL) | 0
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  |  | 6 X13 |  | L. SAVER SUB |  |  | 8.25 | 3.25 |  | 6 5/8 REG |  | 0.33 | 0.073689 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 58 | 59 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  | 4052 |  | SPSA |  |  | 8.5 | 3.25 |  | 6 5/8 REG |  | 9.47 | 2.1146 |  | TOTAL | 4755.6
PV | 44 | 45 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  |  | U. SAVER SUB |  |  | 8.25 | 3.25 |  | 6 5/8 REG |  | 0.46 | 0.10272 |  | DIESEL (LTR)
YIELD POINT | 27 | 26 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.49 | 0.55601 |  | RIG TANK | 99897
GEL ST. | 24/33 | 22/33 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  |  | NMDC |  |  | 8.25 | 3.25 |  | 6 5/8 REG |  | 5.97 | 1.3331 |  | CAMP TANK | 18704
WL (ml/30 min) | 5.2 | 5.2 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | PBL SUB |  |  | 8.1875 | 3.5 |  | 6 5/8 REG |  | 3.49 | 0.77931 |  | CONSUMED | 5008
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  |  | 9 x DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 83.08 | 18.5516 |  | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  |  |  |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.57 | 2.137 |  | TOTAL | 118601
ALK (FILT.) | 0.4/2.8 | 0.4/2.7 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  |  |  |  | 3 X DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 27.62 | 6.1675 |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  |  |  |  | X/O |  |  | 7.625 | 2.875 |  | 5 1/2 FH |  | 0.76 | 0.16971 |  | RIG STORAGE | 455000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  |  |  | 9 X HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.95 | 3.1236 |  | CAMP STORAGE | 85000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | CONSUMED | 83000
KCl (mg/l) | 45761 | 44807.5 | JAR |  | STAB - 1 | 0 | JET VELOCITY (M/SEC) | [15 empty] | RECEIVED | 88000
CHLORIDES (mg/l) | 25000 | 25000 | 5 1/2" HWDPS |  | STAB - 2 |  | TFA (IN²) |  |  | 0.78 | [12 empty] | TOTAL | 540000
HARDNESS (mg/l) | 400 | 400 | 9 1/2" DCS |  | STAB - 3 |  | HSI | [15 empty] | POB
PENETREX % | 2 | 2 | 8" DCS |  | SPSA | 0 | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 237.15 |  |  | MPCL | 5
OIL % | 4 | 4 | DAILY BHA ROT. HRS |  |  |  | BIT NO. 10RR |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 27 |  |  | MPCL SERV | 23
SOLIDS % | 43.01 | 43.11 | DAILY ON BOTTOM HRS | [8 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 16 |  |  | SECURITY
M.B.T. (lb/bbl) | 12.5 | 12.5 | DAILY CIRC. HRS | [8 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 3944 |  | 0.17 |  | 203.5 |  |  | 1.23 |  | MWD |  | TOTAL | 108
DAILY WELL COST (US$) |  | 47724 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 3973 |  | 0.03 |  | 138.51 |  |  | 0.17 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 8567109 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 3997 |  | 0.05 |  | 77.88 |  |  | 0.05 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 43.04% | MUD CLEANER | 3 x 170 | [7 empty] | 4030 |  | 0.22 |  | 70.43 |  |  | 0.16 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.26SG) | [5 empty] | MAASP (PSI) | 171.749
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4042 | 500/500/490 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4042 | 580/600/600 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-07-19 | 2019-08-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50/80 |  | 4042 | 630/625/630/1000 |  |  | CHINJI | 338/338
PIT DRILL | 2019-07-17 | 2019-08-16 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL | 2019-08-04 | 2019-08-18 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-08-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-07-19 | 2019-08-18 | NEXT BOP TEST DATE |  | 2019-08-28 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-14
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43691 | 43691.0208 | 0.5 | DRL | PT-P | BHA | B/OUT AND L/DOWN SCHL PD & 12 1/4'' PDC BIT.
43691.0208 | 43691.2396 | 5.25 | DRL | PT-P | BOPT | M/UP TEST ASSEMBLY, RETRIEVED WEAR BUSHING. RIH 3 STDS OF 5 1/2" DP BELOW PLUG & SET TEST PLUG IN 13-5/8" CHS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP @ 400/4500 PSI FOR 5/10 MIN - OK. PRESSURE TESTED ROTARY HOSE & STAND PIPE VALVES @ 400/5000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER (VARIABLE 4 1/2"-7") & LOWER (5 1/2") PIPE RAM, HCR & MANUAL VALVES OF KILL & CHOKE LINE, FOSV, HYD & MANUAL IBOP @ 400/8000 PSI FOR 5/10 MIN. PRESSURE TESTED BLIND/SHEAR RAM AND CO-FLEXIP-MASTER VALVE AT CHOKE MANIFOLD @ 400/8000 PSI FOR 5/10 MIN - OK. RETRIEVED TEST PLUG, INSTALLED WEAR BUSHING. L/DOWN TEST PLUG ASSEMBLY.
43691.2396 | 43691.3646 | 3 | DRL | PT-P | BHA / E/C | P/UP AND M/UP 12 1/4'' RR PDC BIT + 12 1/8'' NBS + 8" PONY DC+ SPSA (MWD)+12-1/8" S.STAB+ PONY NMDC RIH DOWN TO 27M. FUNCTION TESTED MWD. RECORDED 1350 PSI @ 600 GPM. FOUND MWD TOOL WORKING GOOD.
43691.3646 | 43691.4271 | 1.5 | DRL | PT-P | E/C | M/UP PBL SUB + 5.5" DP JOINT. M/UP TDS. RIH DOWN TO 40M. CIRCULATED @ 600 GPM RECORDED 1300 PSI SPP. ACTIVATED PBL SUB BY DROPPING 2.5" DART INSIDE STRING. RECORDED 200 PSI SPP @ 600 GPM. (PORTS OPENED) DEACTIVATED PBL SUB BY DROPPING TWO STEEL BALLS INSIDE STRING. CIRCULATED @ 50GPM. DE-ACTIVATED @ 2900 PSI SPP. CIR & RECORDED 1200 PSI SPP @ 650 GPM. PULLED BACK PBL SUB TO ROTARY TABLE. FOUND PORTS CLOSED. STOPPED CIRCULATION. BROKE OUT CATCHER SUB. RECOVERED DART & TWO STEEL BALS. M/UP CATCHER SUB. CIRCULATED @ 650 GPM. RECORDED 1400 PSI SPP & PORTS CLOSED. L/DOWN 5.5" DP JOINT.
43691.4271 | 43691.5729 | 3.5 | DRL | PT-P | BHA | RESUMED RIH AS PER BHA DOWN TO 238M, MEANWHILE P/UP INSPECTED BHA COMPONENTS SGL BY SGL FROM CATWALK. FLUSHED SAME.
43691.5729 | 43691.5833 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43691.5833 | 43691.9479 | 8.75 | DRL | PT-P | RIH | CONT'D RIH FROM 237M TO 2379M. FILLED UP STRING EVERY 10 STANDS. BROKE CIRCULATION EVERY 20 STANDS.
43691.9479 | 43691.9896 | 1 | DRL | PT-P | RR | REPLACED WASHPIPE PRIOR RUN IN OPEN HOLE, P/TESTED SAME AT 2000 PSI, OK.
43691.9896 | 43692 | 0.25 | DRL | PT-P | RIH | CONT'D RIH FROM 2379M TO 2437M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43692 | 43692.1771 | 4.25 | DRL | PT-P | RIH / RW | CONT'D RIH FROM 2437M TO 3153M. FILLED UP STRING EVERY 10 STANDS. (WHILE RIH OBSERVED OBSTRUCTION AT 2533M, 2564M, 2633M, 2657M, 2798M & 3062M. CONNECTED TDS & REAMED DOWN TO CLEAR SAME.)
43692.1771 | 43692.2188 | 1 | DRL | PT-P | RW | PRECAUTIONARY CIRCULATED / WASHED DOWN FROM 3153M TO 3267M.
43692.2188 | 43692.2396 | 0.5 | DRL | PT-P | RIH | CONT'D RIH FROM 3267M TO 3447M ON ELEVATOR. OBSERVED OBSTRUCTION AT 3447M.
43692.2396 | 43692.25 | 0.25 | DRL | PT-P | RW | CONNECTED TDS, REAMED DOWN FROM 3447M TO 3455M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | REAMING DOWN IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | B/OUT 12 1/4'' PDC BIT + SCHL PD, P/UP 12 1/4'' RR PDC BIT + NB STAB + MWD TOOLS, F/TESTED SAME, OK, P/UP REMAINING BHA AND PBL SUB, F/TESTED PBL SUB ON SURFACE, OK. RIH TO 238M, FLOW CHECKED- WELL STATIC, CONT'D RIH FROM 238M TO 2437M. FILLED UP STRING EVERY 10 STANDS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE RIH TO BTM AT 4052M, RESUME DRILLING, DRILL AHEAD 12 1/4'' HOLE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14