## DDR#104
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 104
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-08-16
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIF ULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4052 | 4052 |  |  | M |  |  | DAYS SINCE SPUD: | [6 empty] | 103.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4062 | 4062 |  |  | M |  |  | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2019-08-15 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  | 10RR |  | BHA NO. |  |  | 21 | IN (M) |  | 4052 |  | OUT (M) |  |  | STRING (BBL) | 250
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 12.25" |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1575.8
DEPTH, MD (M) | 4052 | 4052 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  | NOV |  | PDC BIT |  |  | 12.25 |  |  |  |  | 0.43 |  |  | PITS (BBL) | 692
MW IN (SG) | 2.29 | 2.29 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  | TK66M |  | NEAR BIT STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 1.66 | 0.37068 |  | ACT. SYS (BBL) | 2517.8
MW OUT (SG) | 2.29 | 2.29 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | E 243361 |  | PONY DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 4.38 | 0.97805 |  | RESV. SYS (BBL) | 2232
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.49 | 0.55601 |  | KILL MUD (BBL) | 0
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  |  | 6 X13 |  | L. SAVER SUB |  |  | 8.25 | 3.25 |  | 6 5/8 REG |  | 0.33 | 0.073689 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 60 | 58 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  | 4052 |  | SPSA |  |  | 8.5 | 3.25 |  | 6 5/8 REG |  | 9.47 | 2.1146 |  | TOTAL | 4749.8
PV | 45 | 44 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  |  | U. SAVER SUB |  |  | 8.25 | 3.25 |  | 6 5/8 REG |  | 0.46 | 0.10272 |  | DIESEL (LTR)
YIELD POINT | 30 | 28 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.49 | 0.55601 |  | RIG TANK | 93983
GEL ST. | 24/34 | 23/34 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  |  | PONY NMDC |  |  | 8.25 | 3.25 |  | 6 5/8 REG |  | 5.97 | 1.3331 |  | CAMP TANK | 18069
WL (ml/30 min) | 5.8 | 5.7 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | PBL SUB |  |  | 8.1875 | 3.5 |  | 6 5/8 REG |  | 3.49 | 0.77931 |  | CONSUMED | 6549
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  |  | 9 x DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 83.08 | 18.5516 |  | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  |  |  |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.57 | 2.137 |  | TOTAL | 112052
ALK (FILT.) | 0.4/2.8 | 0.4/2.7 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  |  |  |  | 3 X DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 27.62 | 6.1675 |  | WATER (LTR)
PH | 9.5 | 9.8 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  |  |  |  | X/O |  |  | 7.625 | 2.875 |  | 5 1/2 FH |  | 0.76 | 0.16971 |  | RIG STORAGE | 455000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  |  |  | 9 X HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.95 | 3.1236 |  | CAMP STORAGE | 86000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | CONSUMED | 205400
KCl (mg/l) | 44807.5 | 46714.2 | JAR | 13.4 | STAB - 1 | 13.4 | JET VELOCITY (M/SEC) | [15 empty] | RECEIVED | 206400
CHLORIDES (mg/l) | 24500 | 25000 | 5 1/2" HWDPS | 13.4 | STAB - 2 | 13.4 | TFA (IN²) |  |  | 0.78 | [12 empty] | TOTAL | 541000
HARDNESS (mg/l) | 400 | 380 | 9 1/2" DCS |  | STAB - 3 | 13.4 | HSI | [15 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 13.4 | SPSA | 13.4 | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 237.15 |  |  | MPCL | 6
OIL % | 4 | 4 | DAILY BHA ROT. HRS |  | 13.4 |  | BIT NO. 10RR |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 27 |  |  | MPCL SERV | 23
SOLIDS % | 43.13 | 43.21 | DAILY ON BOTTOM HRS |  | 0 | [6 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 16 |  |  | SECURITY
M.B.T. (lb/bbl) | 12.5 | 12.5 | DAILY CIRC. HRS |  | 16.7 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 3944 |  | 0.17 |  | 203.5 |  |  | 1.23 |  | MWD |  | TOTAL | 109
DAILY WELL COST (US$) |  | 48030 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 3973 |  | 0.03 |  | 138.51 |  |  | 0.17 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 8615139 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 3997 |  | 0.05 |  | 77.88 |  |  | 0.05 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 43.28% | MUD CLEANER | 3 x 170 | [7 empty] | 4030 |  | 0.22 |  | 70.43 |  |  | 0.16 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.26SG) | [5 empty] | MAASP (PSI) | 103.0494
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4049 | 450/450/450 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4049 | 580/575/580 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-07-19 | 2019-08-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50/80 |  | 4049 | 650/650/650/1100 |  |  | CHINJI | 338/338
PIT DRILL | 2019-07-17 | 2019-08-16 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL | 2019-08-04 | 2019-08-18 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-08-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-07-19 | 2019-08-18 | NEXT BOP TEST DATE |  | 2019-08-28 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 8 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43692 | 43692.1771 | 4.25 | DRL | PT-P | RIH / RW | CONT'D RIH FROM 2437M TO 3153M. FILLED UP STRING EVERY 10 STANDS. (WHILE RIH OBSERVED OBSTRUCTION AT 2533M, 2564M, 2633M, 2657M, 2798M & 3062M. CONNECTED TDS & REAMED DOWN TO CLEAR SAME.)
43692.1771 | 43692.2188 | 1 | DRL | PT-P | RW | PRECAUTIONARY CIRCULATED / WASHED DOWN FROM 3153M TO 3267M.
43692.2188 | 43692.2396 | 0.5 | DRL | PT-P | RIH | CONT'D RIH FROM 3267M TO 3447M ON ELEVATOR. OBSERVED OBSTRUCTION AT 3447M.
43692.2396 | 43692.5729 | 8 | DRL | PT-P | RW | CONNECTED TDS, REAMED DOWN FROM 3447M TO 3878M. OBSERVED LEAKAGE FROM DP-SAVER SUB CONNECTION.
43692.5729 | 43692.6042 | 0.75 | DRL | NPT-UP | RR | RACKED BACK 1 STAND & REPLACED SAVER SUB.
43692.6042 | 43693 | 9.5 | DRL | PT-P | RW | REAMED DOWN FROM 3878M TO 3956M. (OBSERVED HARD REAMING AT 3901-3905M, 3924M-3926M. WHILE REAMING AT 3901M, OBSERVED HI-TORQUE & ROTARY STALLED. P/U STRING, FOUND STRING STUCK. WORKED ON STUCK STRING, RELEASED STRING BY APPLYING 40 TONS OVERPULL).
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-16
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43693 | 43693.125 | 3 | DRL | PT-P | RW | REAMED DOWN FROM 3956M TO 4042M. OBSERVED HARD REAMING AT 3965M, 3971M-3975M, 3990M.
43693.125 | 43693.1354 | 0.25 | DRL | PT-P | RW | CONT'D REAM DOWN FROM 4042M AND TAGGED BTM AT 4052M. RECORDED SCR PRIOR DRILLING COMMENCEMENT.
43693.1354 | 43693.25 | 2.75 | DRL | PT-P | D | DRILLED 12 1/4'' HOLE FROM 4052M TO 4062M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12 1/4'' HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH TO 3153M MEANWHILE REAMED DOWN TIGHT HOLE SECTIONS, PRECAUTIONARY CIRCULATED / WASHED DOWN FROM 3153M TO 3267M, CONT'D RIH TO 3447M, OBSERVED OBSTRUCTION, REAMED DOWN FROM 3477M TO 3956M, WHILE REAMING AT 3901M, ROTARY STALLED AND STRING GOT STUCK, WORKED ON STRING AND RELEASED AT 40 TON O/PULL.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE REAM/WASH DOWN TO BTM AT 4052M, RESUME DRILLING, DRILL AHEAD 12 1/4'' HOLE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14