## DDR#107
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 107
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-04-07
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | SAIFULLAH TURK / MUHAMMAD AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4037 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 106.5833
RIG REP.: |  | JAVED IQBAL MUGHAL / IMRAN JAWAD |  |  | MD/TVD @ 06:00HRS: |  | 4037 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 11
2018-04-06 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 12.25 |  | BIT No. |  | 6RR2 |  |  |  |  | 14 | IN (M) |  | 4007 |  | OUT (M) |  |  | STRING (BBL) | 241
CHECK TIME | 14:59 | 23:59 | MD @ 00:00HR (M) |  | 4037 |  | SIZE (IN) |  | 12 1/4" |  |  |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1601
DEPTH, MD (M) | 4034 | 4037 | TVD @ 00:00HR (M) |  | 4037 |  | MANUFACTURER |  | SMITH |  | PDC BIT |  |  | 12.25 | 3.25 |  | 6 5/8 REG |  | 0.27 | 0.1 |  | PITS (BBL) | 865
MW IN (SG) | 2.25 | 2.25 | DAILY PROGRESS (M) |  | 11 |  | TYPE |  | MDSiZ616 |  | BIT SUB |  |  | 8.5 | 3 |  | 6 5/8 REG |  | 1.07 | 0.4 |  | ACT. SYS (BBL) | 2707
MW OUT (SG) | 2.25 | 2.25 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | JN 5197 |  | 2 X 8" DCS |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 18.25 | 4.0752 |  | RESV. SYS (BBL) | 1088
ECD (SG) | 2.27 |  | AVG. ROP (M/HR) |  | 0.79 |  | IADC CODE |  | - |  | STRING STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.45 | 0.54708 |  | KILL MUD (BBL) | 600
FL TEMP. °F | 157 | 159 | AVG. WOB (TON) |  | 8 - 10 |  | NOZZLES |  | 6 x 18/32" |  | 1 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.3 | 2.0767 |  | KILL MW (SG) | 2.3
µ FUNNEL (SEC) | 61 | 63 | AVG. RPM SURFACE |  | 120 |  | DEPTH IN (M) |  | 4007 |  | STRING STAB |  |  | 12.125 | 2.8125 |  | 6 5/8 REG |  | 1.95 | 0.43543 |  | TOTAL | 4395
PV | 40 | 41 | AVG. RPM DOWNHOLE |  | 120 |  | DEPTH OUT (M) |  | - |  | 9 X 8" DCS |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 83.24 | 18.5874 |  | DIESEL (LTR)
YIELD POINT | 39 | 40 | FLOWRATE (GPM) |  | 600 |  | METERAGE (M) |  | 30 |  | DRILLING JAR |  |  | 8 | 3 |  | 6 5/8 REG |  | 5.35 | 1.1946 |  | RIG TANK | 87000
GEL ST. | 35/48 | 28/51 | PRESSURE (PSI) |  | 3450 - 3550 |  | RPM SURF. |  | 120 |  | 1 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.26 | 2.0677 |  | CAMP TANK | 16500
WL (ml/30 min.) | 5.9 | 5.9 | TORQ. ON-BTM (KLB-FT) |  | 5 - 7 |  | RPM BTM. |  | 120 |  | X/OVER |  |  | 8.125 | 3 |  | 6 5/8 REG |  | 0.74 | 0.16524 |  | CONSUMED | 14000
CT ( in/32) | 3 | 3 | TORQ. OFF-BTM (KLB-FT) |  | 3 - 5 |  | WOB (TON) |  | 7 - 10 |  | 7 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 65.26 | 4.8575 |  | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  | 163 |  | AVG. ROP (M/HR) |  | 0.82395 | [12 empty] | TOTAL | 103500
ALK (FILT.) | 0.5 | 0.5 | PICK-UP WT. (TON) |  | 165 |  | BIT ROT HRS. |  | 36.41 | [12 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 150 |  | K-REVS IN 24 HRS |  | 101.75 | [12 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 265.34 | [12 empty] | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 35.5 | [12 empty] | CONSUMED | 273810
KCl (mg/l) | 44235 | 44235 | JAR | 62.16 | NMDC |  | JET VELOCITY (M/SEC) |  | 39.8 | [12 empty] | RECEIVED | 273810
CHLORIDES | 20000 | 20000 | 5" HWDPS | 68.1 | STAB - 1 | 68.1 | TFA (IN²) |  | 1.49 | [12 empty] | TOTAL | 445000
CALCIUM | 180 | 180 | 8" DCS | 68.1 | STAB - 2 | 68.1 | HSI |  | 0.8 | [12 empty] | POB
OIL% | 4 | 4 | 9 1/2" DCS |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 197.14 |  |  | MPCL | 3
LUBE % | 2 | 2 | BHA ROT. HRS |  | 68.1 |  | BIT No. 6RR2 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 24.845 |  |  | MPCL SERV | 15
SOLIDS % | 40.36 | 40.36 | ON BOTTOM HRS |  | 36.41 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 18.8797 |  |  | SECURITY | 4
M.B.T. | 15 | 15 | CIRC. HRS |  | 75.58 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 X 100 | 1 X 140 |  | 20" SURFACE CASING |  |  | 594 | 3478 |  | 0.51 |  | 138.13 |  |  | 0.14 |  | MWD |  | TOTAL | 106
DAILY WELL COST (US$) |  | 53892.076 | SHAKER-2 | 2 X 140 | 1 X 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 3502 |  | 0.66 |  | 136.87 |  |  | 0.19 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 7918824.4336 | SHAKER-3 | 2 X 80 | 1 X 140 |  | 9 5/8" PRODUCTION CSG |  |  |  | 3531 |  | 0.83 |  | 141.02 |  |  | 0.18 |  | MWD |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 43.87% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 3559 |  | 0.78 |  | 132.49 |  |  | 0.14 |  | MWD |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-03-31 | 2018-04-21 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 4011 |  | 610 / 690 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 4011 |  | 625 / 700 |  | CHINJI | 342
FIRE DRILL | 2018-03-16 | 2018-04-15 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-03-16 | 2018-04-06 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-03-16 | 2018-04-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-04-01 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 20 | MUD LOSSES IN 24 HRS |  |  | 133 |  | MUD LOSSES |  |  |  | 133 |  | SAKESAR
STRETCHER DRILL | 2018-03-16 | 2018-04-15 | NEXT BOP TEST DATE |  | 2018-04-15 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 17 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-04-06
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43196 | 43196.1667 | 4 | DRL | PT-P | D | DRILLED 12 1/4" HOLE FROM 4026M TO 4029M. REAMED TWICE AT CONNECTION, OBSERVED HIGH ERRATIC TORQUE & FREQUENT TDS STALLING WHILE REAMING.
43196.1667 | 43196.1771 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43196.1771 | 43196.2083 | 0.75 | DRL | PT-P | RW | ATTEMPTED TO POOH FOR SHORT WIPER TRIP TO CHECK HOLE CONDITION & OBSERVED TIGHT SPOT. PUMPED OUT / BACK REAMED FROM 4029M TO 3943M.
43196.2083 | 43196.2292 | 0.5 | DRL | NPT-P | RS | SERVICED TDS.
43196.2292 | 43196.2708 | 1 | DRL | PT-P | RIH | RIH / WASHED DOWN FROM 3943M TO BTM @ 4029M.
43196.2708 | 43196.7292 | 11 | DRL | PT-P | D | DRILLED 12 1/4" HOLE FROM 4029M TO 4037M. MEANWHILE INCREASED MWT FROM 2.23 S.G TO 2.25 S.G. OBSERVED PARTIAL LOSSES WHILE DRILLING @ 4037M. STOPPED DRILLING & P/BACK TO 4028M. LOST 15 BBL MUD.
43196.7292 | 43196.7396 | 0.25 | DRL | NPT-UP | FC | MONITORED WELL & OBSERVED NO STATIC LOSS.
43196.7396 | 43196.7812 | 1 | DRL | NPT-UP | SP | CIRCULATED @ 580 GPM & LOST 10 BBLS IN 5 MIN. RIH TO BTM, STOPPED CIRCULATION & SPOTTED 30 BBL LCM PILL OF 150 PPB @ BTM. P/BACK TO 4028M. LOST 35 BBL MUD DURING SPOTTING & DISPLACEMENT.
43196.7812 | 43196.8229 | 1 | DRL | NPT-UP | SP | SPOTTED 50 BBL LCM PILL OF 150 PPB @ 4028M. LOST 33 BBL MUD DURING SPOTTING & DISPLACEMENT.
43196.8229 | 43196.8646 | 1 | DRL | NPT-UP | RW | P/BACK FROM 4028M TO 3943M. WHILE POOH CLEARED TIGHT SPOT FROM 4013M - 4009M WITH BACK REAMING & PUMPED OUT FROM 4009M - 3980M. LOST 30 BBL MUD.
43196.8646 | 43196.875 | 0.25 | DRL | NPT-UP | FC | MONITORED WELL & OBSERVED NO STATIC LOSS.
43196.875 | 43197 | 3 | DRL | NPT-UP | CIR | CIRCULATING & REDUCING MWT FROM 2.25 S.G TO 2.22 S.G @ LOW GPM TO AVOID LOSSES. LOST 10 BBL MUD.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-04-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43197 | 43197.25 | 6 | DRL | NPT-UP | CIR | CONT'D CIRCULATING & REDUCING MWT FROM 2.25 S.G TO 2.22 S.G @ LOW GPM.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE & SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | CIRCULATING & REDUCING MWT
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 12 1/4" HOLE FROM 4026M TO 4029M. CONDUCTED SHORT WIPER TRIP FROM 4029M TO 3943M & OBSERVED HOLE NOT IN VERY GOOD CONDITION. DRILLED 12 1/4" HOLE FROM 4029M TO 4037M & INCREASED MWT FROM 2.23 S.G TO 2.25 S.G. OBSERVED PARTIAL LOSSES WHILE DRILLING @ 4037M. STOPPED DRILLING, SPOTTED LCM PILLS & P/BACK TO 3943M. CIRCULATING & REDUCING MWT IS IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | REDUCE MWT TO 2.22 S.G. RIH TO BTM & CIRCULATE @ HIGH GPM TO CHECK LOSSES. IN EVENT OF NO LOSS, DRILL AHEAD 12 1/4" HOLE.
REMARKS |  |  | TOTAL MUD LOST = 133 BBL.
Formulas:
DHARIAN - 1 = [DATE]+21
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14