## DDR#108
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 108
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-04-08
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | SAIFULLAH TURK / MUHAMMAD AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4041 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 107.5833
RIG REP.: |  | JAVED IQBAL MUGHAL / IMRAN JAWAD |  |  | MD/TVD @ 06:00HRS: |  | 4046 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 4
2018-04-07 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 12.25 |  | BIT No. |  | 6RR2 |  |  |  |  | 14 | IN (M) |  | 4007 |  | OUT (M) |  |  | STRING (BBL) | 249
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4041 |  | SIZE (IN) |  | 12 1/4" |  |  |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1592
DEPTH, MD (M) | 4037 | 4041 | TVD @ 00:00HR (M) |  | 4041 |  | MANUFACTURER |  | SMITH |  | PDC BIT |  |  | 12.25 | 3.25 |  | 6 5/8 REG |  | 0.27 | 0.1 |  | PITS (BBL) | 947
MW IN (SG) | 2.22 | 2.22 | DAILY PROGRESS (M) |  | 4 |  | TYPE |  | MDSiZ616 |  | BIT SUB |  |  | 8.5 | 3 |  | 6 5/8 REG |  | 1.07 | 0.4 |  | ACT. SYS (BBL) | 2788
MW OUT (SG) | 2.22 | 2.22 | INST. ROP (M/HR) |  | 0.7 |  | SERIAL NO. |  | JN 5197 |  | 2 X 8" DCS |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 18.25 | 4.0752 |  | RESV. SYS (BBL) | 860
ECD (SG) | 2.24 | 2.24 | AVG. ROP (M/HR) |  | 0.67 |  | IADC CODE |  | - |  | STRING STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.45 | 0.54708 |  | KILL MUD (BBL) | 600
FL TEMP. °F | 156 | 158 | AVG. WOB (TON) |  | 8 - 10 |  | NOZZLES |  | 6 x 18/32" |  | 1 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.3 | 2.0767 |  | KILL MW (SG) | 2.3
µ FUNNEL (SEC) | 63 | 65 | AVG. RPM SURFACE |  | 120 |  | DEPTH IN (M) |  | 4007 |  | STRING STAB |  |  | 12.125 | 2.8125 |  | 6 5/8 REG |  | 1.95 | 0.43543 |  | TOTAL | 4248
PV | 41 | 42 | AVG. RPM DOWNHOLE |  | 120 |  | DEPTH OUT (M) |  | - |  | 9 X 8" DCS |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 83.24 | 18.5874 |  | DIESEL (LTR)
YIELD POINT | 38 | 40 | FLOWRATE (GPM) |  | 580 |  | METERAGE (M) |  | 34 |  | DRILLING JAR |  |  | 8 | 3 |  | 6 5/8 REG |  | 5.35 | 1.1946 |  | RIG TANK | 77500
GEL ST. | 31/45 | 25/50 | PRESSURE (PSI) |  | 3200 - 3300 |  | RPM SURF. |  | 120 |  | 1 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.26 | 2.0677 |  | CAMP TANK | 16000
WL (ml/30 min.) | 5.9 | 5.8 | TORQ. ON-BTM (KLB-FT) |  | 5 - 7 |  | RPM BTM. |  | 120 |  | X/OVER |  |  | 8.125 | 3 |  | 6 5/8 REG |  | 0.74 | 0.16524 |  | CONSUMED | 10000
CT ( in/32) | 3 | 3 | TORQ. OFF-BTM (KLB-FT) |  | 2 - 4 |  | WOB (TON) |  | 7 - 10 |  | 7 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 65.26 | 4.8575 |  | RECEIVED
ALK (MUD) | 0.3 | 0.4 | STRING WT. (TON) - ROT |  | 162 |  | AVG. ROP (M/HR) |  | 0.8034 | [12 empty] | TOTAL | 93500
ALK (FILT.) | 0.5 | 0.6 | PICK-UP WT. (TON) |  | 165 |  | BIT ROT HRS. |  | 42.32 | [12 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 155 |  | K-REVS IN 24 HRS |  | 42.29 | [12 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 307.63 | [12 empty] | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 33.5 | [12 empty] | CONSUMED | 287250
KCl (mg/l) | 44235 | 46447 | JAR | 85.35 | NMDC |  | JET VELOCITY (M/SEC) |  | 37.6 | [12 empty] | RECEIVED | 287250
CHLORIDES | 20000 | 21000 | 5" HWDPS | 91.29 | STAB - 1 | 91.29 | TFA (IN²) |  | 1.49 | [12 empty] | TOTAL | 495000
CALCIUM | 180 | 180 | 8" DCS | 91.29 | STAB - 2 | 91.29 | HSI |  | 0.7 | [12 empty] | POB
OIL% | 4 | 4 | 9 1/2" DCS |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 197.14 |  |  | MPCL | 3
LUBE % | 2 | 2 | BHA ROT. HRS |  | 91.29 |  | BIT No. 6RR2 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 24.845 |  |  | MPCL SERV | 15
SOLIDS % | 39.35 | 39.31 | ON BOTTOM HRS |  | 42.32 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 18.8797 |  |  | SECURITY | 4
M.B.T. | 15 | 15 | CIRC. HRS |  | 98.83 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 22
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 X 100 | 1 X 140 |  | 20" SURFACE CASING |  |  | 594 | 3478 |  | 0.51 |  | 138.13 |  |  | 0.14 |  | MWD |  | TOTAL | 102
DAILY WELL COST (US$) |  | 42301.5848 | SHAKER-2 | 2 X 140 | 1 X 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 3502 |  | 0.66 |  | 136.87 |  |  | 0.19 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 7961126.0184 | SHAKER-3 | 2 X 80 | 1 X 140 |  | 9 5/8" PRODUCTION CSG |  |  |  | 3531 |  | 0.83 |  | 141.02 |  |  | 0.18 |  | MWD |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 44.11% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 3559 |  | 0.78 |  | 132.49 |  |  | 0.14 |  | MWD |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-03-31 | 2018-04-21 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 4037 |  | 450 / 560 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 4037 |  | 450 / 560 |  | CHINJI | 342
FIRE DRILL | 2018-03-16 | 2018-04-15 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-03-16 | 2018-04-06 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-03-16 | 2018-04-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-04-01 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 13 | MUD LOSSES IN 24 HRS |  |  | 133 |  | MUD LOSSES |  |  |  | 133 |  | SAKESAR
STRETCHER DRILL | 2018-03-16 | 2018-04-15 | NEXT BOP TEST DATE |  | 2018-04-15 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 1 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-04-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43197 | 43197.5 | 12 | DRL | NPT-UP | CIR | CIRCULATED & REDUCED MWT FROM 2.25 S.G TO 2.22 S.G @ LOW GPM. RECIPROCATED STRING DURING CIRCULATION.
43197.5 | 43197.5208 | 0.5 | DRL | NPT-UP | CIR | CIRCULATED @ 620 GPM TO CHECK FOR LOSSES & OBSERVED NO LOSS.
43197.5208 | 43197.7396 | 5.25 | DRL | NPT-UP | RW | REAMED / WASHED DOWN FROM 3943M TO BTM @ 4037M. HARD REAMED FROM 4011M - 4015M & 4020M - 4025M.
43197.7396 | 43198 | 6.25 | DRL | PT-P | D | RESUMED DRILLING & DRILLED 12 1/4" HOLE FROM 4037M TO 4041M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-04-08
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43198 | 43198.25 | 6 | DRL | PT-P | D | CONT'D DRILLED 12 1/4" HOLE FROM 4041M TO 4046M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE & SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12 1/4" HOLE
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | REDUCED MWT TO 2.22 S.G. REAMED DOWN FROM 3943M TO BTM @ 4037M. DRILLED 12 1/4" HOLE FROM 4037M TO 4041M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 12 1/4" HOLE.
REMARKS
Formulas:
DHARIAN - 1 = [DATE]+21
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14