## DDR # 11
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 11
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-01-01
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR RAO / M. MOHSIN ALI |  |  | MD/TVD @ 00:00HRS: |  | 595 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 10.5833
RIG REP.: |  | JAVED IQBAL / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 595 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2017-12-31 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | SPUD MUD |  | HOLE SIZE (IN) |  | 17.5 |  | BIT No. |  | 3 |  | BHA No. |  |  | 3 | IN (M) |  | 595 |  | OUT (M) |  |  | STRING (BBL) | -
CHECK TIME | 23:59 |  | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 17.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 684.57
DEPTH, MD (M) | 595 |  | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | NOV |  | 17 1/2" PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 |  |  | PITS (BBL) | 702
MW IN (SG) | 1.3 |  | DAILY PROGRESS (M) |  |  |  | TYPE |  | TFH519S |  | MUD MOTOR |  |  | 9.75 | 7.85 |  | 7 5/8 REG |  | 9.87 | 2.9 |  | ACT. SYS (BBL) | 1386.57
MW OUT (SG) | 1.3 |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E244694 |  | FLOAT SUB |  |  | 9.5 | 2.5 |  | 7 5/8 REG |  | 0.62 | 0.2 |  | RESV. SYS (BBL) | 1412
ECD (SG) | - |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | S422 |  | STRING STAB |  |  | 17.375 | 2.9375 |  | 7 5/8 REG |  | 2.43 | 0.8 |  | KILL MUD (BBL) | -
FL TEMP. °F | - |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 5X18/32" |  | LOWER SAVER SUB |  |  | 9.5 | 3.5 |  | 7 5/8 REG |  | 0.61 | 0.2 |  | KILL MW (SG) | -
µ FUNNEL (SEC) | 60 |  | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 595 |  | SLIM PULSE |  |  | 9.375 | 5 |  | 7 5/8 REG |  | 9.4 | 2.7 |  | TOTAL | 2798.57
PV | 20 |  | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | UPPER SAVER SUB |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 0.44 | 0.1 |  | DIESEL (LTR)
YIELD POINT | 26 |  | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | NMDC |  |  | 8.875 | 3.5 |  | 7 5/8 REG |  | 8.94 | 2.4 |  | RIG TANK | 128800
GEL ST. | 7/12 |  | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 9 1/2" FILTER SUB |  |  | 9.5 | 3.875 |  | 7 5/8 REG |  | 2.21 | 0.7 |  | CAMP TANK | 17300
WL (ml/30 min.) | 6 |  | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 9 1/2" DRILL COLLAR |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 27.63 | 8.8 |  | CONSUMED | 3300
CT ( in/32) | 1 |  | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | X/O |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 0.93 | 0.1 |  | RECEIVED
ALK (MUD) |  |  | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  |  |  | 8" DRILL COLLAR |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 18.57 | 4.5 |  | TOTAL | 146100
ALK (FILT.) |  |  | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  |  |  | DRILLING JAR |  |  | 7.625 | 3 |  | 6 5/8 REG |  | 5.14 | 0.9 |  | WATER (LTR)
PH | 10 |  | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  |  |  | 8" DRILL COLLAR |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 18.39 | 4.5 |  | RIG STORAGE | 200000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  |  | X/O |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 0.74 | 0.1 |  | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  |  | 5" HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 56.18 | 4.1 |  | CONSUMED | 288054
KCl (mg/l) | 50527.6 |  | JAR |  | NMDC |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 183054
CHLORIDES | 23500 |  | 5" HWDPS |  | STAB - 1 |  | TFA (IN²) |  | 1.2425 | [12 empty] | TOTAL | 240000
CALCIUM | 160 |  | 8" DCS |  | STAB - 2 |  | HSI | [14 empty] | POB
OIL% | - |  | ANY OTHER |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 162.46 |  |  | MPCL | 3
SAND % | 0.5 |  | BHA ROT. HRS |  |  |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 27 |  |  | MPCL SERV | 18
SOLIDS % | 9.23 |  | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 19 |  |  | SECURITY | -
M.B.T. | 10 |  | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 14
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 35 | 2 X 35 |  | 20" SURFACE CASING |  |  | 594 | 496 |  | 1.01 |  | 132.42 |  |  |  |  | EMS |  | TOTAL | 111
DAILY WELL COST (US$) |  | 121310.9092 | SHAKER-2 | 1 X 35 | 2 X 35 |  | 13 3/8" INTERMEDIATE CSG |  |  |  | 525 |  | 1.26 |  | 139.45 |  |  |  |  | EMS |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 2215467.2893 | SHAKER-3 | 1 X 80 | 2 X 50 |  | 9 5/8" PRODUCTION CSG |  |  |  | 554 |  | 1.44 |  | 142.41 |  |  |  |  | EMS |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 12.27% | MUD CLEANER | 3 X 200 |  |  | 7" LINER |  |  |  | 583 |  | 1.06 |  | 135.73 |  |  |  |  | EMS |  | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 20.75 | 3000 | P-1 - F-1600HL | 6.5 |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 20.75 | 3000 | P-2 - F-1600HL | 6.5 |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | CHINJI | 342
FIRE DRILL | 26-12-2017 |  | BLIND RAMS | CHINA | 20.75 | 3000 | P-3 - F-1600HL | 6.5 |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | KAMLIAL
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2017-12-31 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2018-01-14 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2017-12-31
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43100 | 43100.0417 | 1 | DRL | PT-P | NUB | FUNCTION TESTED BOP STACK.
43100.0417 | 43100.0833 | 1 | DRL | PT-P | BOPT | HELD PJSM. FLUSHED BOP STACK WITH WATER. M/U TEST PLUG ASSY & SET TEST PLUG INSIDE CHH.
43100.0833 | 43100.2917 | 5 | DRL | NPT-UP | BOPT | TRIED TO P/T ANNULAR BOP - OBSERVED LEAKAGE BETWEEN DOUBLE RAM BOP AND DRILLING SPOOL FLANGE. RETRIEVED TEST PLUG & L/DOWN TEST PLUG ASSY. DISMANTLED BELL NIPPLE AND FLOW LINE. LOOSENED NUTS & BOLTS OF DOUBLE RAM BOP AND DRILLING SPOOL FLANGE. LIFTED BOP STACK AND REPLACED R-74 RING GASKET. TIGHTENED NUTS & BOLTS OF DOUBLE RAM BOP AND DRILLING SPOOL FLANGE.
43100.2917 | 43100.3333 | 1 | DRL | NPT-UP | BOPT | MADE SEVERAL ATTEMPTS TO P/T SAME - NEGATIVE.
43100.3333 | 43100.4583 | 3 | DRL | NPT-UP | BOPT | DISMANTLED BELL NIPPLE AND FLOW LINE. LOOSENED NUTS & BOLTS OF DOUBLE RAM BOP AND DRILLING SPOOL FLANGE. LIFTED BOP STACK AND REMOVED R-74 RING GASKET & INSTALLED RX-74 RING GASKET. SLACKED BOP STACK ON DRILLING SPOOL. TIGHTENED NUTS & BOLTS OF DOUBLE RAM BOP AND DRILLING SPOOL FLANGE.
43100.4583 | 43100.6042 | 3.5 | DRL | NPT-UP | BOPT | P/T (20-3/4 X 3000 BOP STACK) AND DRILLING SPOOL @ 300 / 2700 PSI FOR 5 / 10 MIN - OK. P/T ANNULAR BOP @ 300 / 2500 PSI FOR 5 / 10 MIN - OK. P/T PIPE RAMS, BLIND RAMS, KILL/CHOKE LINE & IBOP/ROTARY HOSE/STAND PIPE MANIFOLD @ 300 / 2700 PSI FOR 5 / 10 MIN - OK.
43100.6042 | 43100.6667 | 1.5 | DRL | NPT-UP | NUB | INSTALLED BELL NIPPLE AND FLOW LINE.
43100.6667 | 43100.7083 | 1 | DRL | NPT-UP | RR | REPLACED WASH PIPE AND P/T @ 2000 PSI - OK.
43100.7083 | 43100.75 | 1 | DRL | NPT-UP | WB | TRIED TO RUN AND SET 21" WEAR BUSHING IN CHH IN SEVERAL ATTEMPTS. GRINDED GUIDE PINS.
43100.75 | 43100.7708 | 0.5 | DRL | NPT-UP | WB | RUN AND SET 21" WEAR BUSHING IN CHH. TIGHTENED TIE DOWN BOLTS. L/D SETTING TOOL ASSY.
43100.7708 | 43100.8958 | 3 | DRL | PT-P | BHA | P/U & M/U RR 17 1/2" MILL TOOTH BIT WITH SLB MUD MOTOR. P/U & M/U STRING STAB, MWD TOOLS & NMDC.
43100.8958 | 43100.9167 | 0.5 | DRL | NPT-UP | BHA | MADE SEVERAL ATTEMPTS TO ADJUST ADJUSTABLE BEND HOUSING TO 1.15° - NO SUCCESS.
43100.9167 | 43101 | 2 | DRL | PT-P | BHA | ADJUSTED ADJUSTABLE BEND HOUSING TO 1.15° AND SHALLOW FUNCTION TESTED MWD AT 550 GPM & 550 PSI. B/O RR 17 1/2" MILL TOOTH BIT. M/U NEW 17 1/2" PDC BIT AND RIH BHA FROM SURFACE TO 32 M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-01
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43101 | 43101.1146 | 2.75 | DRL | PT-P | BHA | CONTINUED RIH BHA FROM 32 M TO 162 M.
43101.1146 | 43101.1979 | 2 | DRL | PT-P | RIH | RIH FROM 162 M TO 580 M. WASHED DOWN LAST 2 STANDS. TAGGED TOP OF FLOAT COLLAR @ 580 M.
43101.1979 | 43101.25 | 1.25 | DRL | PT-P | DC | DRILLED FLOAT COLLAR & SHOE TRACK FROM 580 M TO 588 M.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | DRILLING OF SHOE TRACK.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RESOLVED LEAKAGE PROBLEM, INSTALLED BOP STACK AND PERFORMED BOP P/T. RIH 17 1/2" PERFORMANCE BHA FROM SURFACE TO 32M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | P/T CASING. DRILL FLOAT SHOE, RAT HOLE & 2-3 M OF NEW FORMATION. PERFORM LOT/FIT. DRILL 17 1/2" HOLE SECTION.
REMARKS
Formulas:
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14