## DDR#11
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 11
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-15
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / ADNAN |  |  | MD/TVD @ 00:00HRS: |  | 580 / 580 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 10.9792
RIG REP.: |  | TARIQ BUTT / JAVED MUGHAL / FAYYAZ |  |  | MD/TVD @ 06:00HRS: |  | 580 / 580 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2019-05-14 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | SPUD MUD |  | HOLE SIZE (IN) |  |  |  | BIT No. |  | 3 |  | BHA No. |  |  | 4 | IN (M) |  | 580 |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 12:00 | 23:45 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 17 1/2'' |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 648.48
DEPTH, MD (M) |  | 580 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | HUGHES |  | 17 1/2'' TC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.4 |  |  | PITS (BBL) | 438
MW IN (SG) |  | 1.1 | DAILY PROGRESS (M) |  |  |  | TYPE |  | GTX-CG1 |  | BIT SUB |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 1.07 |  |  | ACT. SYS (BBL) | 1086.48
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 5202655 |  | 6 X 9 1/2'' DC's |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 55.27 | 17.6075 |  | RESV. SYS (BBL) | 400
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 115 |  | X/O |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.93 | 0.29627 |  | KILL MUD (BBL) | 400
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 3X 20, 1 X 18 |  | 3 X 8'' DC's |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 27.6 | 6.163 |  | KILL MW (SG) | 1.6
µ FUNNEL (SEC) |  | 75 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 580 |  | 8'' D. JAR |  |  | 7.9375 | 3.0625 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | TOTAL | 1486.48
PV |  | 18 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 3 X 8'' DC's |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 27.62 | 6.1675 |  | DIESEL (LTR)
YIELD POINT |  | 24 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | X/O |  |  | 7.3125 | 2.8125 |  | 5 1/2 FH |  | 0.81 | 0.25804 |  | RIG TANK | 125330
GEL ST. |  | 14/19 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 6 X 5 1/2'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 56.62 | 2.0819 |  | CAMP TANK | 24179
WL (ml/30 min.) |  |  | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 3747
CT ( in/32) |  |  | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED | 25000
ALK (MUD) |  |  | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 149509
ALK (FILT.) |  |  | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 480000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 85000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 99400
KCl (mg/l) |  | 2478.7 | JAR |  | NMDC |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 109400
CHLORIDES (mg/l) |  | 1500 | MOTOR |  | STAB - 1 |  | TFA (IN²) |  | 1.1688 | [12 empty] | TOTAL
HARDNESS (mg/l) |  | 240 | 11'' DCS |  | STAB - 2 |  | HSI | [14 empty] | POB
OIL% |  |  | 9 1/2" DCS |  | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 179.88 |  |  | MPCL | 5
SAND % |  |  | BHA ROT. HRS |  |  |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 29 |  |  | MPCL SERV | 24
SOLIDS % |  | 8.92 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 22 |  |  | SECURITY | 5
M.B.T. (lb/bbl) |  | 25 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 58
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 100 | 2 X 100 |  | 30" CONDUCTOR |  |  | 37 | [11 empty] | TOTAL | 123
DAILY WELL COST (US$) |  | 105061 | SHAKER-2 | 1 X 100 | 2 X 100 |  | 20'' SURFACE/ K-55, 133# |  |  | 579 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 1686822 | SHAKER-3 | 1 X 100 | 2 X 100 | [16 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 8.474% | MUD CLEANER | 3 X 140 | [17 empty] | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 | [7 empty] | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-05-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | BRINE LOSSES IN 24 HRS |  |  |  |  | BRINE LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2019-05-28 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-14
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43599 | 43599.0625 | 1.5 | DRL | NPT-UP | NUB | N/UP 21 1/4'', 5K BOP STACK.
43599.0625 | 43599.2708 | 5 | DRL | NPT-UP | BOPT | HELD PJSM, FLUSHED BOP STACK WITH WATER. P/UP AND M/UP TEST PLUG ASSEMBLY, INSTALLED TEST PLUG INSIDE 21 1/4'' CHH. P/TESTED ANNULAR BOP AT 300/3000 PSI FOR 5 / 10 MINS OK. P/TESTED HCR & MANUAL VALVES AT CHOKE /KILL LINE AT 300/3000 PSI FOR 5 /10 MINS, OK. P/TESTED 5 1/2 FH FOSV, IBOP, ROTARY HOSE, STAND PIPE MANIFOLD VALVES AT 300/3000 PSI FOR 5 / 10 MINS OK. P/TESTED CO-FLEXIP, MASTER VALVE AT CHOKE MANIFOLD & CHECK VALVE AT KILL LINE & OUTER FLANGE AT CHECK VALVE AT 300/3000 PSI FOR 5 / 10 MINS, OK. RETRIEVED TEST PLUG AND INSTALLED WEAR BUSHING. L/DOWN TEST PLUG ASSEMBLY.
43599.2708 | 43599.4167 | 3.5 | DRL | NPT-UP | NUB | FIXED BELL NIPPLE & FLOW LINE.
43599.4167 | 43600 | 14 | DRL | PT-P | DP | P/UP 5 1/2'' DP SGL BY SGL FROM CATWALK. M/UP AND RACK BACK STANDS (TOTAL STDS R/BACK = 52)
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43600 | 43600.0729 | 1.75 | DRL | PT-P | DP | CONT'D P/UP 5 1/2'' DP SGL BY SGL FROM CATWALK. M/UP & RACK BACK SAME. (TOTAL STDS R/BACK = 57 / TOTAL STDS IN DERRICK = 84 /2400M.)
43600.0729 | 43600.2292 | 3.75 | DRL | PT-P | BHA | P/UP AND M/UP NEW 17 1/2'' TC BIT (HUGHES, GTX-CG1, IADC: 115, 3 X20 + 1 X 18) + BIT SUB. RIH AS PER BHA DOWN TO 180M. WHILE RIH P/UP 4 X 9 1/2'' DC , 8'' D. JAR, 2 X 8'' DC & 1X 5 1/2'' HWDP. FLUSHED SAME.
43600.2292 | 43600.25 | 0.5 | DRL | PT-P | RIH | RIH FROM 180M TO 350M.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | N/UP BOP, BOPT, FIX BELL NIPPLE & FLOW LINE, P/UP & M/UP 5 1/2'' DP STDS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE P/UP AND R/BACK 5 1/2'' DP's, P/UP AND M/UP NEW 17 1/2'' TC BIT, RIH WITH SLICK BHA FOR COC, CSG TEST, DRILL OUT FLOATS/ SHOE TRACK, DRILL OUT SHOE/ NEW FORMATION, DISPLACE MUD, FIT, DRILL 17 1/2'' HOLE. POOH TO CHANGE BHA.
REMARKS |  |  | SCHL DD ARRIVED ON LOCATION. CHECKED AND FOUND MAST CENTRE WITH ROTARY. P/TESTED CHOKE MANIFOLD.
Formulas:
MIRAJ-1 = [SPUD MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14