## DDR#110
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 110
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-08-22
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4269 | 4269 |  |  | M |  |  | DAYS SINCE SPUD: | [6 empty] | 109.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4276 | 4276 |  |  | M |  |  | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 22
2019-08-21 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | RUN NO. |  |  | 19 |  | BHA NO. |  |  | 21 | IN (M) |  | 4052 |  | OUT (M) |  |  | STRING (BBL) | 285.5
CHECK TIME | 6:30 | 23:59 | MD @ 00:00HR (M) |  | 4269 |  | BIT NO. |  |  | 10RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1636.2
DEPTH, MD (M) | 4254 | 4269 | TVD @ 00:00HR (M) |  | 4269 |  | SIZE (IN) |  |  | 12.25" |  | PDC BIT |  |  | 12.25 |  |  |  |  | 0.43 |  |  | PITS (BBL) | 767
MW IN (SG) | 2.27 | 2.27 | DAILY PROGRESS (M) |  | 22 |  | MANUFACTURER |  |  | NOV |  | NEAR BIT STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 1.66 | 0.37068 |  | ACT. SYS (BBL) | 2688.7
MW OUT (SG) | 2.27 | 2.27 | INST. ROP (M/HR) |  | - |  | TYPE |  |  | TK66M |  | PONY DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 4.38 | 0.97805 |  | RESV. SYS (BBL) | 1951
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 1.63 |  | SERIAL NO. |  |  | E 243361 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.49 | 0.55601 |  | KILL MUD (BBL) | 0
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 7-10 |  | IADC CODE |  |  |  |  | L. SAVER SUB |  |  | 8.25 | 3.25 |  | 6 5/8 REG |  | 0.33 | 0.073689 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 61 | 58 | AVG. RPM SURFACE |  | 135 |  | NOZZLES (1/32") |  |  | 6 X13 |  | SPSA |  |  | 8.5 | 3.25 |  | 6 5/8 REG |  | 9.47 | 2.1146 |  | TOTAL | 4639.7
PV | 44 | 45 | AVG. RPM DOWNHOLE |  | 135 |  | DEPTH IN (M) |  |  | 4052 |  | U. SAVER SUB |  |  | 8.25 | 3.25 |  | 6 5/8 REG |  | 0.46 | 0.10272 |  | DIESEL (LTR)
YIELD POINT | 29 | 28 | FLOWRATE (GPM) |  | 640-670 |  | DEPTH OUT (M) |  |  |  |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.49 | 0.55601 |  | RIG TANK | 95663
GEL ST. | 22/35 | 23/36 | PRESSURE (PSI) |  | 3600-4250 |  | METERAGE (M) |  |  | 217 |  | PONY NMDC |  |  | 8.25 | 3.25 |  | 6 5/8 REG |  | 5.97 | 1.3331 |  | CAMP TANK | 13888
WL (ml/30 min) | 5.8 | 5.9 | TORQ. ON-BTM (KLB-FT) |  | 5-6 |  | RPM SURF. |  |  | 130-140 |  | PBL SUB |  |  | 8.1875 | 3.5 |  | 6 5/8 REG |  | 3.49 | 0.77931 |  | CONSUMED | 13748
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 4-6 |  | RPM BTM. |  |  | 130-140 |  | 9 x DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 83.08 | 18.5516 |  | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 178 |  | WOB (TON) |  |  | 7-10 |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.57 | 2.137 |  | TOTAL | 109551
ALK (FILT.) | 0.4/2.7 | 0.4/2.8 | PICK-UP WT. (TON) |  | 186 |  | AVG. ROP (M/HR) |  |  | 2.0068 |  | 3 X DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 27.62 | 6.1675 |  | WATER (LTR)
PH | 9.5 | 9.8 | SLACK-OFF WT. (TON) |  | 166 |  | BIT ROT HRS. |  |  | 108.13 |  | X/O |  |  | 7.625 | 2.875 |  | 5 1/2 FH |  | 0.76 | 0.16971 |  | RIG STORAGE | 250000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  | 107.18 |  | 9 X HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.95 | 3.1236 |  | CAMP STORAGE | 84000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  | 869.05 | [12 empty] | CONSUMED | 356100
KCl (mg/l) | 43854 | 44807 | JAR | 149.66 | STAB - 1 | 149.66 | ANN. VEL. (M/MIN) |  |  | 58.89 | [12 empty] | RECEIVED | 358100
CHLORIDES (mg/l) | 24000 | 25000 | 5 1/2" HWDPS | 149.66 | STAB - 2 | 149.66 | JET VELOCITY (M/SEC) |  |  | 81.286 | [12 empty] | TOTAL | 334000
HARDNESS (mg/l) | 400 | 410 | 9 1/2" DCS |  | STAB - 3 | 149.66 | TFA (IN²) |  |  | 0.78 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 149.66 | SPSA | 149.66 | HSI |  |  | 3.91 |  | TOTAL LENGTH (M) | [7 empty] | 237.15 |  |  | MPCL | 7
OIL % | 4 | 4.1 | DAILY BHA ROT. HRS |  | 20.56 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 27 |  |  | MPCL SERV | 30
SOLIDS % | 43.4 | 43.21 | DAILY ON BOTTOM HRS |  | 13.5 | [6 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 16 |  |  | SECURITY
M.B.T. (lb/bbl) | 12.5 | 12.5 | DAILY CIRC. HRS |  | 20.9 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 57
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 28
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4165 |  | 0.7 |  | 252.45 |  |  | 0.04 |  | MWD |  | TOTAL | 128
DAILY WELL COST (US$) |  | 55757 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4195 |  | 0.82 |  | 251.25 |  |  | 0.12 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 8965651 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4226 |  | 1.07 |  | 256.44 |  |  | 0.26 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 45.04% | MUD CLEANER | 3 x 170 | [7 empty] | 4248 |  | 1.07 |  | 249.8 |  |  | 0.17 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.27SG) | [5 empty] | MAASP (PSI) | 171.749
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4243 | 520/500/500 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4243 | 600/590/590 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-08-19 | 2019-09-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50/80 |  | 4243 | 700/690/700/1050 |  |  | CHINJI | 338/338
PIT DRILL | 2019-07-17 | 2019-08-16 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL | 2019-08-04 | 2019-08-18 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-08-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-08-19 | 2019-09-18 | NEXT BOP TEST DATE |  | 2019-08-28 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 18 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43698 | 43698.6667 | 16 | DRL | PT-P | D | DRILLED 12 1/4" HOLE FROM 4247M TO 4269M. WASHED / REAMED DRILLED INTERVAL & RECORDED MWD SURVEY AT CONNECTION.
43698.6667 | 43698.7396 | 1.75 | DRL | PT-P | CIR | CIRCULATED BOTTOMS UP TO CLEAN HOLE.
43698.7396 | 43698.75 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43698.75 | 43698.8542 | 2.5 | DRL | PT-P | WT | PERFORMED WIPER TRIP. PUMPED OUT FROM 4269M TO 3990M. OBSERVED TIGHT SPOTS @ 4171M, 4159M, 4154M, 4124M, 4092M, 4066M, 4057M, 4040M, 4032M, 4027M & 4024M. CLEARED WITH RECIPROCATION. (BACK REAMED FROM 4253M TO 4245M).
43698.8542 | 43699 | 3.5 | DRL | PT-P | WT | RIH FROM 3990M TO 4256M. (WASHED / REAMED DOWN FROM 4057-4058M, 4070-4078M, 4078-4097M, 4109-4125M, 4153-4159M, 4162-4172M, 4214-4240M, HARD REAMED AT 4082M & 4162M. OBSERVED ROTARY STALLING SEVERAL TIMES).
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-22
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43699 | 43699.0208 | 0.5 | DRL | PT-P | RW | REAMED DOWN FROM 4256M TO 4269M.
43699.0208 | 43699.25 | 5.5 | DRL | PT-P | D | CONT'D DRILLING 12 1/4" HOLE FROM 4269M TO 4276M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12 1/4'' HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED DOWN TO 4269M, CIRCULATION PRIOR WIPER TRIP, FLOW CHECKED- WELL STATIC, PERFORMED WIPER TRIP: PUMPED OUT FROM 4269M TO 3990M, CLEARED TIGHT SPOTS WITH BACK REAMING / STRING RECIPROCATION. WASHED / REAMED DOWN FROM 3990M TO 4256M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | REAM /WASH DOWN TO BTM AT 4269M, RESUME DRILLING, DRILL AHEAD 12 1/4'' HOLE.
REMARKS |  |  | PTIS ON LOCATION FOR INSPECTION OF 9 5/8'' CSG.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14