## DDR#118
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 117.9792
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-08-30
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4455 | 4455 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 117.9792
RIG REP.: |  | TARIQ BUTT / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 4455 | 4455 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-08-29 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 19 |  | BHA NO. |  |  | 21 | IN (M) |  | 4052 |  | OUT (M) | 4455 |  | STRING (BBL) | 10.7
CHECK TIME | 6:30 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 10RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 2106.4
DEPTH, MD (M) | 4455 | 4455 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 12.25" |  | PDC BIT |  |  | 12.25 |  |  |  |  | 0.43 |  |  | PITS (BBL) | 716
MW IN (SG) | 2.27 | 2.27 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | NOV |  | NEAR BIT STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 1.66 | 0.37068 |  | ACT. SYS (BBL) | 2833.1
MW OUT (SG) | 2.27 | 2.27 | INST. ROP (M/HR) |  |  |  | TYPE |  |  | TK66M |  | PONY DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 4.38 | 0.97805 |  | RESV. SYS (BBL) | 1333
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | E 243361 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.49 | 0.55601 |  | KILL MUD (BBL) | 0
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | L. SAVER SUB |  |  | 8.25 | 3.25 |  | 6 5/8 REG |  | 0.33 | 0.073689 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 60 | 58 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 6x 13 |  | SPSA |  |  | 8.5 | 3.25 |  | 6 5/8 REG |  | 9.47 | 2.1146 |  | TOTAL | 4166.1
PV | 44 | 44 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4052 |  | U. SAVER SUB |  |  | 8.25 | 3.25 |  | 6 5/8 REG |  | 0.46 | 0.10272 |  | DIESEL (LTR)
YIELD POINT | 27 | 26 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  | 4455 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.49 | 0.55601 |  | RIG TANK | 120647
GEL ST. | 17/30 | 17/29 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  | 403 |  | PONY NMDC |  |  | 8.25 | 3.25 |  | 6 5/8 REG |  | 5.97 | 1.3331 |  | CAMP TANK | 24331
WL (ml/30 min) | 5 | 5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | PBL SUB |  |  | 8.1875 | 3.5 |  | 6 5/8 REG |  | 3.49 | 0.77931 |  | CONSUMED | 6688
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | 9 x DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 83.08 | 18.5516 |  | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) |  |  |  |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.57 | 2.137 |  | TOTAL | 144978
ALK (FILT.) | 0.4/2.7 | 0.4/2.7 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) |  |  |  |  | 3 X DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 27.62 | 6.1675 |  | WATER (LTR)
PH | 9.7 | 9.8 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. |  |  | 222.26 |  | X/O |  |  | 7.625 | 2.875 |  | 5 1/2 FH |  | 0.76 | 0.16971 |  | RIG STORAGE | 440000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  | - |  | 9 X HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.95 | 3.1236 |  | CAMP STORAGE | 64000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  | 1788.41 | [12 empty] | CONSUMED | 115100
KCl (mg/l) | 44808 | 44807.5 | JAR | 288.39 | STAB - 1 | 288.39 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 100100
CHLORIDES (mg/l) | 25000 | 25000 | 5 1/2" HWDPS | 288.39 | STAB - 2 | 288.39 | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 504000
HARDNESS (mg/l) | 410 | 400 | 9 1/2" DCS |  | STAB - 3 | 288.39 | TFA (IN²) |  |  | 0.78 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 288.39 | SPSA | 288.39 | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 237.15 |  |  | MPCL | 6
OIL % | 4.1 | 4.1 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 27 |  |  | MPCL SERV | 19
SOLIDS % | 43.11 | 43.11 | DAILY ON BOTTOM HRS | [8 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 16 |  |  | SECURITY
M.B.T. (lb/bbl) | 11 | 11 | DAILY CIRC. HRS |  | 4.05 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 54
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4340 |  | 1.33 |  | 254.87 |  |  | 0.26 |  | MWD |  | TOTAL | 112
DAILY WELL COST (US$) |  | 37712.25 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4368 |  | 1.53 |  | 246.46 |  |  | 0.31 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 9378532.7763 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4398 |  | 1.7 |  | 245.61 |  |  | 0.71 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 47.11% | MUD CLEANER | 3 x 170 | [7 empty] | 4427 |  | 1.65 |  | 244.55 |  |  | 0.38 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.27SG) | [5 empty] | MAASP (PSI) | 171.749
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4392 | 450/400/400 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4392 | 550/500/500 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-08-19 | 2019-09-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50/80 |  | 4392 | 620/560/560/1050 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-08-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-08-19 | 2019-09-18 | NEXT BOP TEST DATE |  | 2019-08-28 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43706 | 43706.0104 | 0.25 | DRL | PT-P | CIR | CIRCULATED AT 650 GPM TO WASH BHA.
43706.0104 | 43706.1042 | 2.25 | DRL | PT-P | RW | PUMPED OUT FROM 2579M TO 2378M (INSIDE 13 3/8 CSG SHOE).
43706.1042 | 43706.1146 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43706.1146 | 43706.2292 | 2.75 | DRL | PT-P | RW | PUMPED OUT FROM 2378M TO 2036M.
43706.2292 | 43706.25 | 0.5 | DRL | NPT-UP | DP | SHIFTED 17x BENT DP STDS FROM ONE SIDE TO OTHER SIDE OF DERRICK BOARD. (BENT STDS TO BE L/D SINGLE BY SINGLE DURING POOH)
43706.25 | 43706.5417 | 7 | DRL | PT-P | RW | PUMPED OUT FROM 2036M TO 1008M.
43706.5417 | 43706.6354 | 2.25 | DRL | PT-P | POOH | POOH FROM 1008M TO 237M (TOP OF BHA) ON ELEVATORS.
43706.6354 | 43706.6458 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43706.6458 | 43706.7188 | 1.75 | DRL | NPT-UP | DP | RIH 19x 5 1/2" BENT DP STDS TO 780M. BROKE CIRCULATION AT 780M.
43706.7188 | 43706.8958 | 4.25 | DRL | NPT-UP | DP | POOH & L/D 57x 5 1/2" DPS SINGLE BY SINGLE (19 STDS).
43706.8958 | 43706.9167 | 0.5 | DRL | NPT-P | RS | SERVICED STUCK HYD IBOP. GREASED & F/T HYDRAULIC IBOP, OK.
43706.9167 | 43707 | 2 | DRL | NPT-UP | RR | REPLACEMENT OF STUCK MANUAL IBOP IN PROGRESS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43707 | 43707.0312 | 0.75 | DRL | NPT-UP | RR | REPLACED STUCK MANUAL IBOP.
43707.0312 | 43707.2292 | 4.75 | DRL | PT-P | BHA | POOH BHA FROM 237M TO 19M. WHILE POOH, L/D 9x 5 1/2" HWDP, 12x 8" DC, JAR, PBL SUB, PONY NMDC, ST. STAB. FOUND PIN OF TOP ST. STAB BROKEN. (BIT, N.B STAB, PONY DC, ST. STAB, LOWER SAVER SUB, SPSA & UPPER SAVER SUB = 19.22M FISH LIH)
43707.2292 | 43707.25 | 0.5 | DRL | PT-P | WB | M/U COMB TOOL ASSY AND RETRIEVED WEAR BUSHING FOR BOP PRESSURE TEST.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | BOP PRESSURE TEST IS IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | PUMPED OUT FROM 2579M TO 1008M. POOH ON ELEVATORS FROM 1008M TO 237M (TOP OF BHA). RIH 19x 5 1/2" BENT DP STDS. POOH & L/D THE SAME. WORKED ON HYD & MANUAL IBOP.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | PERFORM BOP PRESSURE TEST. RIH WITH FISHING ASSY TO RECOVER FISH.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14