## DDR#119
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 118.9792
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-08-31
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4455 | 4455 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 118.9792
RIG REP.: |  | TARIQ BUTT / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 4455 | 4455 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-08-30 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 20 |  | BHA NO. |  |  | 22 | IN (M) |  | 4455 |  | OUT (M) |  |  | STRING (BBL) | 166.1
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 6 RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1900.4
DEPTH, MD (M) | 4455 | 4455 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 12.25 |  | TRI CONE BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.33 | 0.2 |  | PITS (BBL) | 715
MW IN (SG) | 2.27 | 2.27 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | BAKER |  | BIT SUB |  |  | 8.3125 | 3 |  | 6 5/8 REG |  | 1.04 | 0.23223 |  | ACT. SYS (BBL) | 2781.5
MW OUT (SG) | 2.27 | 2.27 | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MXL-3 |  | 1 x 8" DC |  |  | 7.8125 | 2.875 |  | 6 5/8 REG |  | 9.27 | 2.07 |  | RESV. SYS (BBL) | 1378
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 5221807 |  | 12 1/8" ST. STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 2.25 | 0.50242 |  | KILL MUD (BBL) | 0
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  | 137 |  | 5 x 8" DC |  |  | 7.8125 | 2.8125 |  | 6 5/8 REG |  | 46.38 | 10.3566 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 55 | 56 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | OPEN JETS |  | D. JAR |  |  | 7.9375 | 3.125 |  | 6 5/8 REG |  | 9.6 | 2.1437 |  | TOTAL | 4159.5
PV | 44 | 44 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4455 |  | 3 x 8" DC |  |  | 7.8125 | 2.8125 |  | 6 5/8 REG |  | 27.72 | 6.1898 |  | DIESEL (LTR)
YIELD POINT | 27 | 27 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | X/O |  |  | 7.625 | 2.8125 |  | 5 1/2 FH |  | 0.79 | 0.17641 |  | RIG TANK | 116817
GEL ST. | 19/30 | 19/30 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | 9 x HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.97 | 3.1243 |  | CAMP TANK | 23644
WL (ml/30 min) | 5 | 5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 4517
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 140461
ALK (FILT.) | 0.4/2.7 | 0.4/2.7 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
PH | 9.8 | 9.8 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 65000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 100000
KCl (mg/l) | 44808 | 44807.5 | JAR |  | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 111000
CHLORIDES (mg/l) | 25000 | 25000 | 5 1/2" HWDPS |  | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 515000
HARDNESS (mg/l) | 410 | 400 | 9 1/2" DCS |  | STAB - 3 |  | TFA (IN²) | [15 empty] | POB
PENETREX % | 2 | 2 | 8" DCS |  | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 182.35 |  |  | MPCL | 6
OIL % | 4 | 4 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 17.7796 |  |  | MPCL SERV | 19
SOLIDS % | 43.21 | 43.21 | DAILY ON BOTTOM HRS | [8 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 9.504 |  |  | SECURITY
M.B.T. (lb/bbl) | 11 | 11 | DAILY CIRC. HRS |  | 1.95 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 56
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4340 |  | 1.33 |  | 254.87 |  |  | 0.26 |  | MWD |  | TOTAL | 111
DAILY WELL COST (US$) |  | 33624.7071 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4368 |  | 1.53 |  | 246.46 |  |  | 0.31 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 9412157.4834 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4398 |  | 1.7 |  | 245.61 |  |  | 0.71 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 47.28% | MUD CLEANER | 3 x 170 | [7 empty] | 4427 |  | 1.65 |  | 244.55 |  |  | 0.38 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.27SG) | [5 empty] | MAASP (PSI) | 171.749
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4392 | 450/400/400 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4392 | 550/500/500 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-08-19 | 2019-09-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50/80 |  | 4392 | 620/560/560/1050 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-08-30 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-08-19 | 2019-09-18 | NEXT BOP TEST DATE |  | 2019-09-13 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43707 | 43707.0312 | 0.75 | DRL | NPT-UP | RR | REPLACED STUCK MANUAL IBOP.
43707.0312 | 43707.2292 | 4.75 | DRL | PT-P | BHA | POOH BHA FROM 237M TO 19M. WHILE POOH, L/D 9x 5 1/2" HWDP, 12x 8" DC, JAR, PBL SUB, PONY NMDC, ST. STAB. FOUND PIN OF TOP ST. STAB BROKEN. (BIT, N.B STAB, PONY DC, ST. STAB, LOWER SAVER SUB, SPSA & UPPER SAVER SUB = 19.22M FISH LIH)
43707.2292 | 43707.25 | 0.5 | DRL | PT-P | WB | M/U COMB TOOL ASSY AND RETRIEVED WEAR BUSHING FOR BOP PRESSURE TEST.
43707.25 | 43707.4479 | 4.75 | DRL | PT-P | BOPT | RIH 3 STDS OF 5 1/2" DP BELOW PLUG & SET TEST PLUG IN 13-5/8" CHS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP, ROTARY HOSE & STAND PIPE MASTER VALVES @ 300/4000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER (VARIABLE 4 1/2"-7") PIPE RAM, LOWER (5 1/2") PIPE RAM, HCR & MANUAL VALVES OF KILL & CHOKE LINE, FOSV, HYD & MANUAL IBOP @ 500/8000 PSI FOR 5/10 MIN - OK. PRESSURE TESTED BLIND/SHEAR RAM AND CO-FLEXIP-MASTER VALVE AT CHOKE MANIFOLD @ 500/8000 PSI FOR 5/10 MIN - OK. RETRIEVED TEST PLUG & R/B 3x 5 1/2" DP STDS. INSTALLED WEAR BUSHING & L/D TEST PLUG ASSY.
43707.4479 | 43707.625 | 4.25 | DRL | NPT-UP | BHA | P/U & M/U RR 12 1/4" TC BIT (OPEN JETS) & RIH DOWN TO 182M. WHILE RIH, P/U INSPECTED 9x 8" DC & 9x 5 1/2" HWDP SINGLE BY SINGLE.
43707.625 | 43707.9167 | 7 | DRL | NPT-UP | RIH | RIH FROM 182M TO 2380M & M/U CIRC. HEAD FOR CIRCULATION. WHILE RIH, FILL UP STRING EVERY 10 STANDS.
43707.9167 | 43707.9583 | 1 | DRL | NPT-UP | RS | CUT & SLIPPED 103 FT DRILL LINE MEANWHILE CIRCULATED.
43707.9583 | 43708 | 1 | DRL | NPT-UP | RIH | CONT'D RIH FROM 2380M TO 2495M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-08-31
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43708 | 43708.25 | 6 | DRL | NPT-UP | RIH | CONT'D RIH FROM 2495M TO 3900M. WHILE RIH, OBSERVED TIGHT SPOTS AT 2578M, 2829M, 2929-2935M, 2980M, 3027M, 3034M, 3266M, 3513M, 3532M, 3636M & 3869M. CLEARED THE SAME WITH RECIPROCATION. WASHED DOWN IN INTERVALS (2720-2725M), (2871-2873M), (2983-2984M) & (3586-3590M).
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | REPLACED MANUAL IBOP. POOH BHA FROM 237M TO 19M, FOUND PIN OF TOP ST.STAB BROKEN & 19.22M FISH LIH. P/T BOP AS PER PROGRAM. P/U & RIH RR 12 1/4" TC BIT DOWN TO 2495M. CUT & SLIPPED DRILL LINE INSIDE CSG SHOE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH & TAG TOP OF FISH. POOH & RIH WITH FISHING ASSY TO RECOVER FISH.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14