## DDR # 12
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 12
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-01-02
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR / MOHSIN / M. AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 668 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 11.5833
RIG REP.: |  | JAVED IQBAL / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 702 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 73
2018-01-01 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 17.5 |  | BIT No. |  | 3 |  | BHA No. |  |  | 4 | IN (M) |  | 595 |  | OUT (M) |  |  | STRING (BBL) | 33.86
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 668 |  | SIZE (IN) |  | 17.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 664.45
DEPTH, MD (M) | 598 | 668 | TVD @ 00:00HR (M) |  | 668 |  | MANUFACTURER |  | NOV |  | 17 1/2" PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 | 0.35 |  | PITS (BBL) | 667
MW IN (SG) | 1.3 | 1.3 | DAILY PROGRESS (M) |  | 73 |  | TYPE |  | TFH519S |  | MUD MOTOR |  |  | 9.75 | 7.85 |  | 7 5/8 REG |  | 9.87 | 2.9 |  | ACT. SYS (BBL) | 1365.31
MW OUT (SG) | 1.3 | 1.3 | INST. ROP (M/HR) |  | 3.07 |  | SERIAL NO. |  | E244694 |  | FLOAT SUB |  |  | 9.5 | 2.5 |  | 7 5/8 REG |  | 0.62 | 0.2 |  | RESV. SYS (BBL) | 801
ECD (SG) | 1.3076 | 1.3076 | AVG. ROP (M/HR) |  | 7.36 |  | IADC CODE |  | S422 |  | STRING STAB |  |  | 17.375 | 2.9375 |  | 7 5/8 REG |  | 2.43 | 0.8 |  | KILL MUD (BBL) | -
FL TEMP. °F | 104 | 104 | AVG. WOB (TON) |  | 2 - 5 |  | NOZZLES |  | 5X18/32" |  | LOWER SAVER SUB |  |  | 9.5 | 3.5 |  | 7 5/8 REG |  | 0.61 | 0.2 |  | KILL MW (SG) | -
µ FUNNEL (SEC) | 63 | 64 | AVG. RPM SURFACE |  | 40 - 90 |  | DEPTH IN (M) |  | 595 |  | SLIM PULSE |  |  | 9.375 | 5 |  | 7 5/8 REG |  | 9.4 | 2.7 |  | TOTAL | 2166.31
PV | 24 | 26 | AVG. RPM DOWNHOLE |  | 100 - 180 |  | DEPTH OUT (M) |  |  |  | UPPER SAVER SUB |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 0.44 | 0.1 |  | DIESEL (LTR)
YIELD POINT | 30 | 29 | FLOWRATE (GPM) |  | 800 - 900 |  | METERAGE (M) |  | 73 |  | NMDC |  |  | 8.875 | 3.5 |  | 7 5/8 REG |  | 8.94 | 2.4 |  | RIG TANK | 124200
GEL ST. | 12/27 | 14/30 | PRESSURE (PSI) |  | 1600 - 1700 |  | RPM SURF. |  | 40 - 90 |  | 9 1/2" FILTER SUB |  |  | 9.5 | 3.875 |  | 7 5/8 REG |  | 2.21 | 0.71392 |  | CAMP TANK | 16600
WL (ml/30 min.) | 5 | 5 | TORQ. ON-BTM (KLB-FT) |  | 3 - 5 |  | RPM BTM. |  | 100 - 180 |  | 3 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 27.63 | 8.9256 |  | CONSUMED | 5300
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 2 - 3 |  | WOB (TON) |  | 2 - 5 |  | X/OVER |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 0.93 | 0.30043 |  | RECEIVED
ALK (MUD) | 0.4 | 0.6 | STRING WT. (TON) - ROT |  | 76 |  | AVG. ROP (M/HR) |  | 7.3589 |  | 2 X 8" DCS |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 18.57 | 4.1467 |  | TOTAL | 140800
ALK (FILT.) | 0.2 | 0.3 | PICK-UP WT. (TON) |  | 76 |  | BIT ROT HRS. |  | 9.92 |  | DRILLING JAR |  |  | 7.625 | 3 |  | 6 5/8 REG |  | 5.14 | 1.1478 |  | WATER (LTR)
PH | 10 | 10 | SLACK-OFF WT. (TON) |  | 75 |  | K-REVS IN 24 HRS |  | 88.4 |  | 2 X 8" DCS |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 18.39 | 4.1065 |  | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 88.4 |  | X/OVER |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 0.74 | 0.16524 |  | CAMP STORAGE | 50000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 21.55 |  | 6 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 56.18 | 4.1816 |  | CONSUMED | 0
KCl (mg/l) | 51480.9 | 51480.9 | JAR | 18.07 | NMDC | 18.07 | JET VELOCITY (M/SEC) |  | 61.8 | [12 empty] | RECEIVED | 172426
CHLORIDES | 24000 | 24000 | 5" HWDPS | 104.27 | STAB - 1 | 18.07 | TFA (IN²) |  | 1.2425 | [12 empty] | TOTAL | 450000
CALCIUM | 160 | 160 | 8" DCS | 117.57 | STAB - 2 |  | HSI |  | 0.8 | [12 empty] | POB
OIL% | 1 | 1 | 9 1/2" DCS | 117.57 | SPSA | 18.07 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 162.46 |  |  | MPCL | 4
SAND % | 0.5 | 0.5 | BHA ROT. HRS |  | 117.57 |  | BIT No. 3 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 27 |  |  | MPCL SERV | 18
SOLIDS % | 9.72 | 9.72 | ON BOTTOM HRS |  | 9.92 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 19 |  |  | SECURITY | -
M.B.T. | 18 | 18 | CIRC. HRS |  | 18.41 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 14
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 35 | 2 X 35 |  | 20" SURFACE CASING |  |  | 594 | 597 |  | 1.51 |  | 143.34 |  |  | 1.03 |  | MWD |  | TOTAL | 110
DAILY WELL COST (US$) |  | 58899.9108 | SHAKER-2 | 1 X 80 | 2 X 80 |  | 13 3/8" INTERMEDIATE CSG |  |  |  | 624 |  | 1.71 |  | 143.44 |  |  | 0.22 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 2274392.8252 | SHAKER-3 | 1 X 80 | 2 X 80 |  | 9 5/8" PRODUCTION CSG |  |  |  | 654 |  | 1.73 |  | 141.29 |  |  | 0.07 |  | MWD |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 12.6% | MUD CLEANER | 3 X 170 |  |  | 7" LINER | [14 empty] | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 423
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | RONGSHENG | 20.75 | 3000 | P-1 - F-1600HL | 6 1/2" |  | 12" | 3980 PSI | 97% |  | 0.119 |  | 30 / 40 |  | 598 |  | 200 / 300 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | RONGSHENG | 20.75 | 3000 | P-2 - F-1600HL | 6 1/2" |  | 12" | 3980 PSI | 97% |  | 0.119 |  | 30 / 40 |  | 598 |  | 200 / 300 |  | CHINJI | 342
FIRE DRILL | 2017-12-26 | 2018-01-09 | BLIND RAMS | RONGSHENG | 20.75 | 3000 | P-3 - F-1600HL | 6 1/2" |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | KAMLIAL
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE
KICK DRILL |  |  | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2017-12-31 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2018-01-14 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-01
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43101 | 43101.1146 | 2.75 | DRL | PT-P | BHA | CONT'D RIH BHA FROM 32M TO 162M.
43101.1146 | 43101.1979 | 2 | DRL | PT-P | RIH | RIH FROM 162M TO 580M. WASHED DOWN LAST 02 STANDS. TAGGED TOP OF CEMENT / F/COLLAR @ 580M.
43101.1979 | 43101.2917 | 2.25 | DRL | PT-P | DC | DRILLED F/COLLAR & HARD CMT IN SHOE TRACK FROM 580M TO 590M WITH LOW PARAMETERS.
43101.2917 | 43101.3333 | 1 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE. MEANWHILE H/UP CMT UNIT LINE TO CHOKE MANIFOLD FOR FIT.
43101.3333 | 43101.3542 | 0.5 | DRL | PT-P | CT | CLOSED PIPE RAMS & P/TESTED 20" CASING IN INCREMENTS TO 1500 PSI FOR 5 MIN - OK. BLED-OFF PRESSURE THRU CHOKE & OPENED PIPE RAMS.
43101.3542 | 43101.4062 | 1.25 | DRL | PT-P | DFS | DRILLED REMAINING SHOE TRACK CEMENT, F/SHOE @ 594M & 1M RAT HOLE TO 595M. MEANWHILE DISPLACED HOLE WITH 5% KCL LIGNOSULPHONATE MUD.
43101.4062 | 43101.4479 | 1 | DRL | PT-P | DCD | COMMENCED 2ND PHASE DRILLING & DRILLED 17 1/2" HOLE FROM 595M TO 598M WITH CONTROLLED PARAMETERS.
43101.4479 | 43101.4792 | 0.75 | DRL | PT-P | CIR | CIRCULATED, CLEANED HOLE & HOMOGENIZED MUD COLUMN PRIOR CONDUCTING FORMATION INTEGRITY TEST (FIT).
43101.4792 | 43101.5 | 0.5 | DRL | PT-P | P/T | HELD PJSM. P/TESTED CMT LINE AT 2000 PSI FOR 10 MIN - OK.
43101.5 | 43101.5208 | 0.5 | DRL | PT-P | FIT | CONDUCTED FIT WITH 1.30 S.G MUD & 423 PSI SURFACE PRESSURE (1.80 S.G EMW), OK.
43101.5208 | 43101.5833 | 1.5 | DRL | PT-P | DCD | DRILLED 17 1/2" HOLE FROM 598M TO 610M WITH CONTROLLED PARAMETERS (TO GET STABS OUT IN OPEN HOLE).
43101.5833 | 43101.9167 | 8 | DRL | PT-P | DM | DRILLED 17 1/2" HOLE FROM 610M TO 663M IN ROTARY MODE. REAMED, CIRCULATED & RECORDED MWD SURVEYS AT EACH CONNECTION.
43101.9167 | 43102 | 2 | DRL | PT-P | DM | DRILLED 17 1/2" HOLE FROM 663M TO 668M IN SLIDE MODE TO BREAK HOLE INCLINATION BUILD UP TREND.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-02
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43102 | 43102.0833 | 2 | DRL | PT-P | DM | DRILLED 17 1/2" HOLE FROM 668M TO 673M IN SLIDE MODE TO BREAK HOLE INCLINATION BUILD UP TREND.
43102.0833 | 43102.25 | 4 | DRL | PT-P | DM | DRILLED 17 1/2" HOLE FROM 673M TO 702M IN ROTARY MODE. REAMED, CIRCULATED & RECORDED MWD SURVEYS AT EACH CONNECTION.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | CHINJI (60 CLAYSTONE, 30% SANDSTONE & 10% SILTSTONE).
OPERATIONS AT 06:00 HRS |  |  | DRILLING OF 17 1/2" HOLE SECTION.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED F/COLLAR & SHOE TRACK. P/TESTED 20" CASING. DRILLED REMAINING SHOE TRACK, F/SHOE, RAT HOLE & 17 1/2" NEW HOLE TO 598M MEANWHILE DISPLACED HOLE WITH 5% KCL LIGNOSULPHONATE MUD. CONDUCTED FIT. DRILLED 17 1/2" HOLE SECTION IN ROTARY & SLIDE MODE FROM 598M TO 668M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 17 1/2" HOLE SECTION.
REMARKS
Formulas:
DHARIAN - 1 = [DATE]+14
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14