## DDR#12
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 12
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-16
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / ADNAN |  |  | MD/TVD @ 00:00HRS: |  | 586 / 586 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 11.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 590 / 590 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 6
2019-05-15 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | SPUD MUD |  | HOLE SIZE (IN) |  | 17 1/2'' |  | BIT No. |  | 3 |  | BHA No. |  |  | 4 | IN (M) |  | 580 |  | OUT (M) | 590 |  | STRING (BBL) | 34
CHECK TIME | 12:00 | 23:45 | MD @ 00:00HR (M) |  | 586 |  | SIZE (IN) |  | 17 1/2'' |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 580.45
DEPTH, MD (M) | 580 | 580 | TVD @ 00:00HR (M) |  | 586 |  | MANUFACTURER |  | HUGHES |  | 17 1/2'' TC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.4 |  |  | PITS (BBL) | 616
MW IN (SG) | 1.35 | 1.35 | DAILY PROGRESS (M) |  | 6 |  | TYPE |  | GTX-CG1 |  | BIT SUB |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 1.07 |  |  | ACT. SYS (BBL) | 1230.45
MW OUT (SG) |  | 1.35 | INST. ROP (M/HR) |  | 3.25 |  | SERIAL NO. |  | 5202655 |  | 6 X 9 1/2'' DC's |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 55.27 | 17.6075 |  | RESV. SYS (BBL) | 585
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 1.86 |  | IADC CODE |  | 115 |  | X/O |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.93 | 0.29627 |  | KILL MUD (BBL) | 400
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 6 |  | NOZZLES |  | 3X 20, 1 X 18 |  | 3 X 8'' DC's |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 27.6 | 6.163 |  | KILL MW (SG) | 1.6
µ FUNNEL (SEC) | 60 | 58 | AVG. RPM SURFACE |  | 100 |  | DEPTH IN (M) |  | 580 |  | 8'' D. JAR |  |  | 7.9375 | 3.0625 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | TOTAL | 1815.45
PV | 20 | 18 | AVG. RPM DOWNHOLE |  | 100 |  | DEPTH OUT (M) |  | 590 |  | 3 X 8'' DC's |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 27.62 | 6.1675 |  | DIESEL (LTR)
YIELD POINT | 27 | 28 | FLOWRATE (GPM) |  | 680 |  | METERAGE (M) |  | 6 |  | X/O |  |  | 7.3125 | 2.8125 |  | 5 1/2 FH |  | 0.81 | 0.25804 |  | RIG TANK | 145183
GEL ST. |  | 06/17 | PRESSURE (PSI) |  | 800 |  | RPM SURF. |  | 100 |  | 6 X 5 1/2'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 56.62 | 2.0819 |  | CAMP TANK | 23567
WL (ml/30 min.) | 6 | 6 | TORQ. ON-BTM (KLB-FT) |  | 5-6 |  | RPM BTM. |  | 100 | [12 empty] | CONSUMED | 5759
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  | 6-8 | [12 empty] | RECEIVED | 25000
ALK (MUD) |  | 0.4 | STRING WT. (TON) - ROT |  | 82 |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 168750
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  | 85 |  | BIT ROT HRS. |  | 3.23 | [12 empty] | WATER (LTR)
PH | 10 | 9.5 | SLACK-OFF WT. (TON) |  | 81 |  | K-REVS IN 24 HRS |  | 18.15 | [12 empty] | RIG STORAGE | 500000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 18.15 | [12 empty] | CAMP STORAGE | 85000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 17.8 | [12 empty] | CONSUMED | 243800
KCl (mg/l) | 46142 | 46714 | JAR | 11.01 | NMDC |  | JET VELOCITY (M/SEC) |  | 54.76 | [12 empty] | RECEIVED | 263800
CHLORIDES (mg/l) | 22000 | 22000 | MOTOR |  | STAB - 1 |  | TFA (IN²) |  | 1.1688 | [12 empty] | TOTAL
HARDNESS (mg/l) | 220 | 220 | 11'' DCS |  | STAB - 2 |  | HSI |  | 0.515 | [12 empty] | POB
OIL% |  |  | 9 1/2" DCS | 11.01 | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 179.88 |  |  | MPCL | 5
LUBRICANT % |  | 1 | BHA ROT. HRS |  | 11 |  | BIT No. 3 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 29 |  |  | MPCL SERV | 25
SOLIDS % | 10.83 | 10.84 | ON BOTTOM HRS |  | 3.23 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 22 |  |  | SECURITY | 2
M.B.T. (lb/bbl) | 7.5 | 7.5 | CIRC. HRS |  | 12.9 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 56
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 30" CONDUCTOR |  |  | 37 | [11 empty] | TOTAL | 118
DAILY WELL COST (US$) |  | 83723 | SHAKER-2 | 1 X 120 | 2 X 120 |  | 20'' SURFACE/ K-55, 133# |  |  | 579 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 1770545 | SHAKER-3 | 1 X 100 | 2 X 100 | [16 empty] | LAST CSG SIZE | 20''
% OF AFE SPENT |  | 8.895% | MUD CLEANER | 3 X 140 | [17 empty] | LOT (EMW) | 1.95
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 494
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 30 |  | 583 |  | 30/35 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 40 |  | 583 |  | 50/60 |  | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 50 |  | 583 |  | 90/100 |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-05-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | BRINE LOSSES IN 24 HRS |  |  |  |  | BRINE LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2019-05-28 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43600 | 43600.0729 | 1.75 | DRL | PT-P | DP | CONT'D P/UP 5 1/2'' DP SGL BY SGL FROM CATWALK. M/UP & RACK BACK SAME. (TOTAL STDS R/BACK = 57 / TOTAL STDS IN DERRICK = 84 /2400M.)
43600.0729 | 43600.2292 | 3.75 | DRL | PT-P | BHA | P/UP AND M/UP NEW 17 1/2'' TC BIT (HUGHES, GTX-CG1, IADC: 115, 3 X20 + 1 X 18) + BIT SUB. RIH AS PER BHA DOWN TO 180M. WHILE RIH P/UP 4 X 9 1/2'' DC , 8'' D. JAR, 2 X 8'' DC & 1X 5 1/2'' HWDP. FLUSHED SAME.
43600.2292 | 43600.2604 | 0.75 | DRL | PT-P | RIH | RIH FROM 180M TO 400M.
43600.2604 | 43600.2812 | 0.5 | DRL | PT-P | RS | SERVICED TDS
43600.2812 | 43600.3229 | 1 | DRL | PT-P | RIH | RIH HOLE WITH CIRCULATION & TAGGED F.COLLAR @ 565M.
43600.3229 | 43600.3646 | 1 | DRL | PT-P | CIR | CIRCULATED TO CONDITION MUD.
43600.3646 | 43600.3958 | 0.75 | DRL | PT-P | CT | PJSM. FLUSHED CHOKE MANIFOLD. CLOSED PIPE RAM & PRESSURE TESTED CASING @ 1500 PSI. HELD FOR 10 MIN. OK. BLED OFF PRESSURE THROUGH CHOKE MANIFOLD TO MUD TANKS. OPENED BOP.
43600.3958 | 43600.5312 | 3.25 | DRL | PT-P | DFS / DC | DRILLED F.COLLAR & CEMENT BELOW F.COLLAR DOWN TO 576M
43600.5312 | 43600.5729 | 1 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE.
43600.5729 | 43600.5938 | 0.5 | DRL | PT-P | CT | PJSM. FLUSHED CHOKE MANIFOLD. CLOSED PIPE RAM & PRESSURE TESTED CASING @ 1500 PSI. HELD FOR 10 MIN. OK. BLED OFF PRESSURE THROUGH CHOKE MANIFOLD TO MUD TANKS. OPENED BOP.
43600.5938 | 43600.7083 | 2.75 | DRL | PT-P | DISP / DC | DISPLACED HOLE VOLUME WITH 1.35 SG 3% KCL MODIFIED LIGNOSULPHONATE MUD, MEANWHILE CONT'D DRILL OUT CMT FROM 576M TO 578M. DUMPED SURFACE MUD, RETURN MUD. CLEANED MUD DITCHES AS NEW MUD SURFACED. CONT'D CIRCULATION TO HOMOGENIZE MUD COLUMN.
43600.7083 | 43600.7812 | 1.75 | DRL | PT-P | DC / DFS | CONT'D DRILL OUT CMT + F.SHOE (579M) TO 580M.
43600.7812 | 43600.8646 | 2 | DRL | PT-P | D | COMMENCED NEXT SECTION DRILLING. DRILLED 17 1/2'' HOLE FROM 580M TO 583M.
43600.8646 | 43600.8958 | 0.75 | DRL | PT-P | CIR | CIRCULATED TO HOMOGENIZE MUD. P/BACK INSIDE 20'' CSG SHOE.
43600.8958 | 43600.9167 | 0.5 | DRL | PT-P | SM / P/T | HELD PJSM FOR FIT, R/UP DOWELL CMT LINES & FLUSHED SAME. CLOSED LO-TORQUE VALVE P/TESTED DOWELL LINES AT 500 / 1000 PSI. HELD FOR 10 MINS OK.
43600.9167 | 43600.9479 | 0.75 | DRL | PT-P | FIT | CLOSED BOP, PERFORMED FIT WITH 1.35 SG MUD AT EMW = 1.95 SG, SURFACE PRESSURE = 494 PSI.
43600.9479 | 43601 | 1.25 | DRL | PT-P | D | RIH TO BTM, RECORDED SCR AND RESUMED DRILLING, DRILLED 17 1/2'' HOLE FROM 583M TO 586M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-16
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43601 | 43601.0625 | 1.5 | DRL | PT-P | D | CONT'D DRILLING 17 1/2'' HOLE FROM 586M TO 590M.
43601.0625 | 43601.1042 | 1 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE.
43601.1042 | 43601.1146 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43601.1146 | 43601.1875 | 1.75 | DRL | PT-P | POOH | POOH FROM 590M TO 178M.
43601.1875 | 43601.25 | 1.5 | DRL | PT-P | BHA | POOH FROM 178M TO 37M. WHILE POOH L/DOWN D. JAR + 1 X 9 1/2'' DC.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | CHINJI / CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | POOH BHA IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D P/UP AND R/BACK 5 1/2'' DP's, P/UP AND M/UP NEW 17 1/2'' TC BIT, RIH WITH SLICK BHA FOR COC, CSG TESTED AT 1500 PSI, DRILLED OUT F. COLLAR/ SHOE TRACK, DISPLACED MUD DRILLED OUT SHOE/ NEW FORMATION +3 M, PERFORMED FIT AT EMW = 1.95 SG, DRILLED 17 1/2'' HOLE DOWN TO 586M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE DRILL 17 1/2'' HOLE TO 590M, CIRCULATE TO CLEAN HOLE, POOH TO CHANGE BHA, P/UP VORTEX BHA AND RIH TO RESUME DRILLING, DRILL AHEAD 17 1/2'' HOLE.
REMARKS |  |  | PD ALONG WITH B/UP ON LOCATION. B/UP MWD AWAITING.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14