## DDR#122
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 122
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-04-22
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR RAO / TALHA SHAKIL |  |  | MD/TVD @ 00:00HRS: |  | 4188 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 121.5833
RIG REP.: |  | JAVED IQBAL / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 4188 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-04-21 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 12.25 |  | BIT No. |  | 5RR3 |  |  |  |  | 15 | IN (M) |  | 4188 |  | OUT (M) | 4188 |  | STRING (BBL) | 73
CHECK TIME |  | 23:59 | MD @ 00:00HR (M) |  | 4188 |  | SIZE (IN) |  | 12 1/4" |  |  |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1894
DEPTH, MD (M) |  | 4188 | TVD @ 00:00HR (M) |  | 4188 |  | MANUFACTURER |  | HLB |  | PDC BIT |  |  | 12.25 | 3.25 |  | 6 5/8 REG |  | 0.36 | 0.1 |  | PITS (BBL) | 805
MW IN (SG) |  | 2.24 | DAILY PROGRESS (M) |  | 0 |  | TYPE |  | MMD65DMH |  | BIT SUB |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 1.04 | 0.4 |  | ACT. SYS (BBL) | 2772
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 12932459 |  | 1 X 8" NMDC |  |  | 8 3/16 | 2.875 |  | 6 5/8 REG |  | 9.41 | 2.1012 |  | RESV. SYS (BBL) | 1180
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | M323 |  | 1 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.28 | 2.0722 |  | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 4x16+2x18/32 |  | STRING STAB |  |  | 12.125 | 2 13/16 |  | 6 5/8 REG |  | 2.46 | 0.54931 |  | KILL MW (SG) | 2.3
µ FUNNEL (SEC) |  | 72 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4188 |  | 1 X 8" DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 9.22 | 2.0588 |  | TOTAL | 4552
PV |  | 44 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | STRING STAB |  |  | 12.125 | 2 13/16 |  | 6 5/8 REG |  | 2.35 | 0.52475 |  | DIESEL (LTR)
YIELD POINT |  | 39 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | 10 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 92.69 | 20.6975 |  | RIG TANK | 79000
GEL ST. |  | 23/46 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | DRILLING JAR |  |  | 7 7/8 | 3 |  | 6 5/8 REG |  | 5.19 | 1.1589 |  | CAMP TANK | 17000
WL (ml/30 min.) |  | 6.2 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 1 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.35 | 2.0878 |  | CONSUMED | 10500
CT ( in/32) |  | 3 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | X/OVER |  |  | 7 7/8 | 6 9/16 |  | 6 5/8 REG |  | 0.94 | 0.069967 |  | RECEIVED | 32000
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  | 165 |  | AVG. ROP (M/HR) |  |  |  | 7 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 65.44 | 4.8709 |  | TOTAL | 96000
ALK (FILT.) |  | 0.5/1.1 | PICK-UP WT. (TON) |  | 170 |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  | 155 |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 148950
KCl (mg/l) |  | 43129 | JAR | 85.55 | NMDC | 85.55 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 148950
CHLORIDES |  | 19500 | 5" HWDPS | 85.55 | STAB - 1 | 85.55 | TFA (IN²) |  | 1.282 | [12 empty] | TOTAL | 440000
CALCIUM |  | 200 | 8" DCS | 85.55 | STAB - 2 | 85.55 | HSI | [14 empty] | POB
OIL% |  | 5 | 9 1/2" DCS |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 207.73 |  |  | MPCL | 3
LUBE % |  | 2 | BHA ROT. HRS |  | 85.55 |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 24 |  |  | MPCL SERV | 16
SOLIDS % |  | 39.88 | ON BOTTOM HRS |  | 0 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 20.4373 |  |  | SECURITY | 4
M.B.T. |  | 12.5 | CIRC. HRS |  | 91.15 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 47
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 12
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 100 | 2 x 140 |  | 20" SURFACE CASING |  |  | 594 | 3502 |  | 0.66 |  | 136.87 |  |  | 0.19 |  | MWD |  | TOTAL | 106
DAILY WELL COST (US$) |  | 36364.06 | SHAKER-2 | 2 x 140 | 1 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 3531 |  | 0.83 |  | 141.02 |  |  | 0.18 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 8675571.935 | SHAKER-3 | 2 x 140 | 1 x 140 |  | 9 5/8" PRODUCTION CSG |  |  |  | 3559 |  | 0.78 |  | 132.49 |  |  | 0.14 |  | MWD |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 48.07% | MUD CLEANER | 1 x 170 + 2 x 140 |  |  | 7" LINER |  |  |  | 4187 |  | 1 |  | - |  |  | - |  | TOTCO |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P2/P3) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-03-31 |  | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4188 |  | 800/800 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4188 |  | 950/950 |  | CHINJI | 342
FIRE DRILL | 2018-03-16 |  | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4188 |  | 1100/1100 |  | KAMLIAL | 1255
PIT DRILL | 2018-03-16 |  | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-03-16 |  | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-04-16 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 5 | MUD LOSSES IN 24 HRS |  |  | 0 |  | MUD LOSSES |  |  |  | 133 |  | SAKESAR
STRETCHER DRILL | 2018-03-16 |  | NEXT BOP TEST DATE |  | 2018-04-30 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 5 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-04-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43211 | 43211.125 | 3 | DRL | PT-P | RW | HARD REAMED FROM 4178M TO 4188M (BOTTOM). OBSERVED HI TORQUE & TDS STALLED FREQUENTLY WHILE REAMING.
43211.125 | 43211.2188 | 2.25 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE PRIOR TO POOH. RECORDED SCR.
43211.2188 | 43211.2292 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43211.2292 | 43211.2917 | 1.5 | DRL | PT-P | POOH | BACK REAMED/PUMPED OUT FROM 4188M TO 4125M. POOH ON ELEVATOR FROM 4125M TO 3999M. OBSERVED COMPRESSION AT 3999M. ATTEMPTED TO CLEAR WITH RECIPROCATION. FOUND STRING STUCK.
43211.2917 | 43211.3125 | 0.5 | DRL | NPT-UP | STK | RESUMED CIRCULATION & WORKED ON STUCK STRING WITH COMBINATION OF TORQUE & COMPRESSION. OBSERVED STRING RELEASED & ROTATION RESUMED.
43211.3125 | 43211.8438 | 12.75 | DRL | PT-P | POOH | BACK REAMED/PUMPED OUT FROM 4002M TO 3638M. POOH ON ELEVATOR TO 2348M (INSIDE CSG SHOE).
43211.8438 | 43211.8542 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43211.8542 | 43212 | 3.5 | DRL | PT-P | POOH | PUMPED SLUG & CONT'D POOH 12-1/4" BIT FROM 2348M TO 1350M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-04-22
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43212 | 43212.1042 | 2.5 | DRL | PT-P | POOH | CONT'D POOH 12-1/4" BIT FROM 1350M TO 207M (BHA TOP).
43212.1042 | 43212.1146 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43212.1146 | 43212.25 | 3.25 | DRL | PT-P | BHA | POOH 12-1/4" BIT TO 20M & L/D BHA. FOUND STABILIZERS 1/8" UG (12-1/8").
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE & SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | POOH 12-1/4" BIT & L/D BHA.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | HARD REAMED FROM 4178M TO 4188M. CIRCULATED TO CLEAN HOLE & POOH TO 1350M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE & L/D BHA. RIH NEW 12-1/4" BIT ON INSPECTED BHA & DRILL AHEAD.
REMARKS
Formulas:
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14