## DDR#122
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 121.9792
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-09-03
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD / ADNAN / MOHSIN / HASSAN |  |  | MD/TVD @ 00:00HRS: |  | 4455 | 4455 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 121.9792
RIG REP.: |  | TARIQ BUTT / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 4455 | 4455 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-09-02 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 20 |  | BHA NO. |  |  | 23 | IN (M) |  | 4455 |  | OUT (M) |  |  | STRING (BBL) | 259.7
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 6 RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1775.9
DEPTH, MD (M) | 4455 | 4455 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 12.25 |  | O SHOT + EXT |  |  | 11.75 | 3.5 |  | 6 5/8 REG |  | 2.25 | 0.50242 |  | PITS (BBL) | 696
MW IN (SG) | 2.27 | 2.27 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | BAKER |  | PBL SUB |  |  | 8.25 | 3.5 |  | 6 5/8 REG |  | 3.48 | 0.77708 |  | ACT. SYS (BBL) | 2731.6
MW OUT (SG) | 2.27 | 2.27 | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MXL-3 |  | 8" BUMPER SUB |  |  | 8 | 3.5 |  | 6 5/8 REG |  | 1.58 | 0.35281 |  | RESV. SYS (BBL) | 1378
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 5221807 |  | 8" FISHING JAR |  |  | 8 | 3 |  | 6 5/8 REG |  | 4.13 | 0.92222 |  | KILL MUD (BBL) | 0
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  | 137 |  | 6 x 8" DC |  |  | 7.8125 | 2.875 |  | 6 5/8 REG |  | 55.65 | 12.4266 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 64 | 63 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | OPEN JETS |  | 8" INTENSIFIER |  |  | 7.625 | 3 |  | 6 5/8 REG |  | 5.34 | 1.1924 |  | TOTAL | 4109.6
PV | 43 | 44 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4455 |  | X/O |  |  | 7.625 | 2.8125 |  | 6 5/8 REG |  | 0.79 | 0.17641 |  | DIESEL (LTR)
YIELD POINT | 27 | 27 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  | 4455 | [12 empty] | RIG TANK | 145358
GEL ST. | 17/28 | 18/29 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 21705
WL (ml/30 min) | 5 | 5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 4556
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 167063
ALK (FILT.) | 0.4/2.7 | 0.4/2.7 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
PH | 9.7 | 9.8 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 445000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 70000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 101300
KCl (mg/l) | 44808 | 44807.5 | JAR |  | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 104300
CHLORIDES (mg/l) | 25000 | 25000 | 5 1/2" HWDPS |  | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 515000
HARDNESS (mg/l) | 400 | 410 | 9 1/2" DCS |  | STAB - 3 |  | TFA (IN²) | [15 empty] | POB
PENETREX % | 2 | 2 | 8" DCS |  | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 73.22 |  |  | MPCL | 8
OIL % | 4 | 4 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 9 |  |  | MPCL SERV | 20
SOLIDS % | 43.21 | 43.21 | DAILY ON BOTTOM HRS | [6 empty] | 1/1/WT/A/E/1/CT/BHA |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 11 | 11 | DAILY CIRC. HRS |  | 1.55 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 57
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4340 |  | 1.33 |  | 254.87 |  |  | 0.26 |  | MWD |  | TOTAL | 116
DAILY WELL COST (US$) |  | 42774.88 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4368 |  | 1.53 |  | 246.46 |  |  | 0.31 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 9533707.8634 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4398 |  | 1.7 |  | 245.61 |  |  | 0.71 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 47.89% | MUD CLEANER | 3 x 170 | [7 empty] | 4427 |  | 1.65 |  | 244.55 |  |  | 0.38 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.27SG) | [5 empty] | MAASP (PSI) | 171.749
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4392 | 450/400/400 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4392 | 550/500/500 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-08-19 | 2019-09-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50/80 |  | 4392 | 620/560/560/1050 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-08-30 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-08-19 | 2019-09-18 | NEXT BOP TEST DATE |  | 2019-09-13 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-02
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43710 | 43710.0729 | 1.75 | DRL | NPT-UP | RW | PUMPED OUT FROM 1409M TO 1010M.
43710.0729 | 43710.0833 | 0.25 | DRL | NPT-UP | CIR | CIRCULATED AT 650 GPM TO WASH BHA.
43710.0833 | 43710.1875 | 2.5 | DRL | NPT-UP | POOH | POOH FROM 1010M TO 182M ON ELEVATORS.
43710.1875 | 43710.1979 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43710.1979 | 43710.25 | 1.25 | DRL | NPT-UP | BHA | POOH BHA FROM 182M TO SURFACE. L/D STAB + JAR + BIT.
43710.25 | 43710.4688 | 5.25 | DRL | NPT-UP | F | P/U AND M/U FISHING ASSEMBLY AND RIH DOWN TO 73M. WHILE RIH, F/TESTED PBL SUB, OK. RECOVERED DART AND BALLS FROM CATCHER SUB.
43710.4688 | 43710.6771 | 5 | DRL | NPT-UP | F | CONT'D RIH FROM 73M TO 1901M.
43710.6771 | 43710.7396 | 1.5 | DRL | NPT-UP | RR | OBSERVED POWER SHUT DOWN. RESTARTED GENERATORS. OBSERVED DRAW WORKS EMERGENCY BRAKES NOT DISENGAGING. WORKED ON STUCK RELAY & DISENGAGED DRAW WORKS BRAKES.
43710.7396 | 43710.7812 | 1 | DRL | NPT-UP | F | CONT'D RIH FROM 1901M TO 2358M.
43710.7812 | 43710.7917 | 0.25 | DRL | NPT-UP | F | BROKE CIRCULATION. MEANWHILE, M/U 2x 5 1/2" DP STANDS IN MOUSE HOLE.
43710.7917 | 43711 | 5 | DRL | NPT-UP | F | CONT'D RIH ON ELEVATORS FROM 2358M TO 3819M. OBSERVED TIGHT SPOTS AT 2798M, 2811M & 3003M. CLEARED THE SAME WITH RECIPROCATION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-03
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43711 | 43711.125 | 3 | DRL | NPT-UP | F | CONT'D RIH ON ELEVATORS FROM 3819M TO 4363M. PRECAUTIONARY WASHED DOWN FROM 4363M TO 4436M.
43711.125 | 43711.1458 | 0.5 | DRL | NPT-UP | F | RECORDED ON / OFF BOTTOM PARAMETERS (SLACK OFF WEIGHT WITH / WITHOUT CIRC. 168 / 165 TON & PICK UP WEIGHT WITH / WITHOUT CIRC. 185 / 185 TON). TAGGED TOF AT 4436M WITH 5 TON COMPRESSION. ATTEMPTED TO ENGAGE FISH W/O ROTATION, NO SUCCESS. WORKED ON STRING WITH ROTATION AND ENGAGED FISH SUCCESSFULLY. OBSERVED SPP INCREASED FROM 190 PSI TO 350 PSI AT 206 GPM. STOPPED PUMPS AND SWALLOWED (1.45 METERS) FISH BY SLACKING OFF 15 TON WEIGHT. PICKED UP STRING AND OBSERVED STRING STUCK WHICH GOT RELEASED WITH 70 TON OVERPULL. CIRCULATED AND OBSERVED PRESSURE INCREASED TO 1500PSI WHICH GRADUALLY DROPPED TO 980PSI @ 287GPM.
43711.1458 | 43711.25 | 2.5 | DRL | NPT-UP | F | PUMPED OUT FROM 4436M TO 4105M. OBSERVED TIGHT SPOTS AT 4420M, 4391M, 4316M & 4162M. CLEARED THE SAME WITH RECIPROCATION.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | POOH FISH.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. RIH WITH FISHING ASSY TO 1901M. OBSERVED POWER SHUT DOWN, RESTARTED GENERATORS. WORKED ON DRAW WORKS BRAKES. RESUMED RIH FROM 1901M TO 3819M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH FISH TO SURFACE.
REMARKS |  |  | SACRIFICED GOAT IN THE NAME OF ALLAH ALMIGHTY.
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14