## DDR#123
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 122.9792
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-09-04
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / HASSAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4455 | 4455 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 122.9792
RIG REP.: |  | TARIQ BUTT / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 4455 | 4455 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-09-03 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  | 23 | IN (M) |  | 4455 |  | OUT (M) |  |  | STRING (BBL) | 259.7
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1775.9
DEPTH, MD (M) | 4455 | 4455 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  |  | O SHOT + EXT |  |  | 11.75 | 3.5 |  | 6 5/8 REG |  | 2.25 | 0.50242 |  | PITS (BBL) | 912
MW IN (SG) | 2.28 | 2.32 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  |  | PBL SUB |  |  | 8.25 | 3.5 |  | 6 5/8 REG |  | 3.48 | 0.77708 |  | ACT. SYS (BBL) | 2947.6
MW OUT (SG) | 2.28 | 2.3 | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  |  | 8" BUMPER SUB |  |  | 8 | 3.5 |  | 6 5/8 REG |  | 1.58 | 0.35281 |  | RESV. SYS (BBL) | 1213
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  |  | 8" FISHING JAR |  |  | 8 | 3 |  | 6 5/8 REG |  | 4.13 | 0.92222 |  | KILL MUD (BBL) | 0
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 6 x 8" DC |  |  | 7.8125 | 2.875 |  | 6 5/8 REG |  | 55.65 | 12.4266 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 57 | 59 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  |  |  | 8" INTENSIFIER |  |  | 7.625 | 3 |  | 6 5/8 REG |  | 5.34 | 1.1924 |  | TOTAL | 4160.6
PV | 45 | 48 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | X/O |  |  | 7.625 | 2.8125 |  | 6 5/8 REG |  | 0.79 | 0.17641 |  | DIESEL (LTR)
YIELD POINT | 28 | 27 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 140863
GEL ST. | 17/28 | 18/30 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 20998
WL (ml/30 min) | 5.4 | 5.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 5202
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 161861
ALK (FILT.) | 0.4/2.8 | 0.3/2.6 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
PH | 9.7 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 435000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 68000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 125200
KCl (mg/l) | 43854 | 43854 | JAR |  | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 113200
CHLORIDES (mg/l) | 24500 | 24000 | 5 1/2" HWDPS |  | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 503000
HARDNESS (mg/l) | 390 | 400 | 9 1/2" DCS |  | STAB - 3 |  | TFA (IN²) | [15 empty] | POB
PENETREX % | 2 | 2 | 8" DCS |  | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 73.22 |  |  | MPCL | 7
OIL % | 4 | 3.75 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 9 |  |  | MPCL SERV | 20
SOLIDS % | 43.23 | 45.02 | DAILY ON BOTTOM HRS | [8 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 11 | 11 | DAILY CIRC. HRS |  | 13.2 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4340 |  | 1.33 |  | 254.87 |  |  | 0.26 |  | MWD |  | TOTAL | 113
DAILY WELL COST (US$) |  | 47096 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4368 |  | 1.53 |  | 246.46 |  |  | 0.31 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 9580803.8634 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4398 |  | 1.7 |  | 245.61 |  |  | 0.71 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 48.13% | MUD CLEANER | 3 x 170 | [7 empty] | 4427 |  | 1.65 |  | 244.55 |  |  | 0.38 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.27SG) | [5 empty] | MAASP (PSI) | 0
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4392 | 450/400/400 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4392 | 550/500/500 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-08-19 | 2019-09-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50/80 |  | 4392 | 620/560/560/1050 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-08-30 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-08-19 | 2019-09-18 | NEXT BOP TEST DATE |  | 2019-09-13 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-03
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43711 | 43711.125 | 3 | DRL | NPT-UP | F | CONT'D RIH ON ELEVATORS FROM 3819M TO 4363M. PRECAUTIONARY WASHED DOWN FROM 4363M TO 4436M.
43711.125 | 43711.1458 | 0.5 | DRL | NPT-UP | F | RECORDED ON / OFF BOTTOM PARAMETERS (SLACK OFF WEIGHT WITH / WITHOUT CIRC. 168 / 165 TON & PICK UP WEIGHT WITH / WITHOUT CIRC. 185 / 185 TON). TAGGED TOF AT 4436M WITH 5 TON COMPRESSION. ATTEMPTED TO ENGAGE FISH W/O ROTATION, NO SUCCESS. WORKED ON STRING WITH ROTATION AND ENGAGED FISH SUCCESSFULLY. OBSERVED SPP INCREASED FROM 190 PSI TO 350 PSI AT 206 GPM. STOPPED PUMPS AND SWALLOWED (1.45 METERS) FISH BY SLACKING OFF 15 TON WEIGHT. PICKED UP STRING AND OBSERVED STRING STUCK WHICH GOT RELEASED WITH 70 TON OVERPULL. CIRCULATED AND OBSERVED PRESSURE INCREASED TO 1500PSI WHICH GRADUALLY DROPPED TO 980PSI @ 287GPM.
43711.1458 | 43711.5625 | 10 | DRL | NPT-UP | F | PUMPED OUT FROM 4436M TO 3070M. OBSERVED CUT MUD WEIGHT (MWOUT = 2.25 SG).
43711.5625 | 43711.5833 | 0.5 | DRL | NPT-UP | FC | FLOW CHECKED - OBSERVED WELL TRICKLING.
43711.5833 | 43711.6042 | 0.5 | DRL | NPT-UP | WC | SHUT IN & MONITORED WELL. RECORDED SIDP = 0 PSI, SICP = 0 PSI.
43711.6042 | 43711.8854 | 6.75 | DRL | NPT-UP | WC | CIRCULATED TO HOMOGENIZE MUD COLUMN. MEANWHILE, WEIGHED UP MUD (MWIN = 2.31 SG & MWOUT = 2.29 SG) & RECIPROCATED STRING. OBSERVED MINIMUM MWOUT = 2.19 SG WHILE CIRCULATION.
43711.8854 | 43711.8958 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43711.8958 | 43712 | 2.5 | DRL | NPT-UP | F | PUMPED OUT FROM 3070M TO 2873M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43712 | 43712.0521 | 1.25 | DRL | NPT-UP | F | PUMPED OUT FROM 2873M TO 2784M.
43712.0521 | 43712.0625 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43712.0625 | 43712.1562 | 2.25 | DRL | NPT-UP | F | PUMPED OUT FROM 2784M TO 2578M.
43712.1562 | 43712.1667 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43712.1667 | 43712.25 | 2 | DRL | NPT-UP | F | PUMPED OUT FROM 2578M TO 2386M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | POOH FISH.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH FROM 3819M TO 4436M. WORKED ON STRING & ENGAGED FISH. PUMPED OUT FROM 4436 TO 3070M. OBSERVED WELL TRICKLING. CIRCULATED & WEIGHED UP MUD. PUMPED OUT FROM 3070M TO 2873M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH FISH TO SURFACE.
REMARKS
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14