## DDR#125
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 125
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-04-25
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR RAO / AHSEN / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4199 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 124.5833
RIG REP.: |  | JAVED IQBAL / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 4199 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-04-24 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 12.25 |  | BIT No. |  | 7 |  |  |  |  | 16 | IN (M) |  | 4188 |  | OUT (M) |  |  | STRING (BBL) | 261
CHECK TIME | 14:59 |  | MD @ 00:00HR (M) |  | 4199 |  | SIZE (IN) |  | 12 1/4" |  |  |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1650
DEPTH, MD (M) | 4199 |  | TVD @ 00:00HR (M) |  | 4199 |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 12.25 | 3.25 |  | 6 5/8 REG |  | 0.25 | 0.1 |  | PITS (BBL) | 1003
MW IN (SG) | 2.24 |  | DAILY PROGRESS (M) |  | 0 |  | TYPE |  | SKH616M |  | BIT SUB |  |  | 8-7/16" | 3 |  | 6 5/8 REG |  | 1.07 | 0.4 |  | ACT. SYS (BBL) | 2914
MW OUT (SG) |  |  | INST. ROP (M/HR) |  | - |  | SERIAL NO. |  | E244697 |  | 2 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 18.58 | 4.1489 |  | RESV. SYS (BBL) | 1128
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | M422 |  | STRING STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.45 | 0.54708 |  | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 6x18/32" |  | 1 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.1 | 2.032 |  | KILL MW (SG) | 2.3
µ FUNNEL (SEC) | 82 |  | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4188 |  | STRING STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.04 | 0.45553 |  | TOTAL | 4642
PV | 44 |  | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 9 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 83.24 | 18.5874 |  | DIESEL (LTR)
YIELD POINT | 39 |  | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  | 11 |  | DRILLING JAR |  |  | 7-5/8'' | 3.125 |  | 6 5/8 REG |  | 5.06 | 1.1299 |  | RIG TANK | 111000
GEL ST. | 23/46 |  | PRESSURE (PSI) |  |  |  | RPM SURF. |  | 120-130 |  | 1 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.29 | 2.0744 |  | CAMP TANK | 15500
WL (ml/30 min.) | 6.2 |  | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  | 120-130 |  | X/OVER |  |  | 8-3/8'' | 2.75 |  | 6 5/8 REG |  | 0.95 | 0.21213 |  | CONSUMED | 13500
CT ( in/32) | 3 |  | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  | 4-8 |  | 7 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 65.61 | 4.8835 |  | RECEIVED | 57000
ALK (MUD) | 0.3 |  | STRING WT. (TON) - ROT |  | 162 |  | AVG. ROP (M/HR) |  | 1.0064 | [12 empty] | TOTAL | 126500
ALK (FILT.) | 0.5/1.0 |  | PICK-UP WT. (TON) |  | 165 |  | BIT ROT HRS. |  | 10.93 | [12 empty] | WATER (LTR)
PH | 9.5 |  | SLACK-OFF WT. (TON) |  | 155 |  | K-REVS IN 24 HRS |  | 83.94 | [12 empty] | RIG STORAGE | 370000
HTHP WL |  |  | ROTATING HRS OF CURRENT IN HOLE BHA |  |  |  | CUMM. K-REVS |  | 83.94 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 37.31 | [12 empty] | CONSUMED | 292900
KCl (mg/l) | 42023 |  | JAR | 17.18 | STAB - 1 | 17.18 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 262900
CHLORIDES | 19000 |  | 5" HWDPS | 17.18 | STAB - 2 | 17.18 | TFA (IN²) |  | 1.49 | [12 empty] | TOTAL | 410000
CALCIUM | 200 |  | 8" DCS | 17.18 |  |  | HSI | [14 empty] | POB
OIL% | 5 |  | 9 1/2" DCS |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 197.64 |  |  | MPCL | 4
LUBE % | 2 |  | BHA ROT. HRS |  | 17.18 |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 24.7044 |  |  | MPCL SERV | 15
SOLIDS % | 39.9 |  | ON BOTTOM HRS |  | 10.93 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 18.7732 |  |  | SECURITY | 4
M.B.T. | 12.5 |  | CIRC. HRS |  | 36.5 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 54
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 100 | 2 x 140 |  | 20" SURFACE CASING |  |  | 594 | 3862 |  | 1.75 |  | 98.28 |  |  | 0.17 |  | EMS |  | TOTAL | 111
DAILY WELL COST (US$) |  | 53259.12 | SHAKER-2 | 2 x 140 | 1 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 3870 |  | 1.66 |  | 98.65 |  |  | 0.35 |  | EMS |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 8803463.2416 | SHAKER-3 | 2 x 140 | 1 x 140 |  | 9 5/8" PRODUCTION CSG |  |  |  | 3890 |  | 1.43 |  | 99.8 |  |  | 0.35 |  | EMS |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 48.78% | MUD CLEANER | 1 x 170 + 2 x 140 |  |  | 7" LINER |  |  |  | 4187 |  | 1 |  | - |  |  | - |  | TOTCO |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P2/P3) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-03-31 |  | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4188 |  | 800/800 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4188 |  | 950/950 |  | CHINJI | 342
FIRE DRILL | 2018-03-16 |  | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4188 |  | 1100/1100 |  | KAMLIAL | 1255
PIT DRILL | 2018-03-16 |  | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-03-16 |  | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-04-16 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  | 0 |  | MUD LOSSES |  |  |  | 133 |  | SAKESAR
STRETCHER DRILL | 2018-03-16 |  | NEXT BOP TEST DATE |  | 2018-04-30 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-04-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43214 | 43214.0833 | 2 | DRL | NPT-UP | STK | WORKED ON STUCK STRING WITH COMBINATION OF TORQUE / OVERPULL & COMPRESSION - NO SUCCESS. MEANWHILE PREPARED 2.24 S.G LUBE PILL WITH 8% LUBE.
43214.0833 | 43214.125 | 1 | DRL | NPT-UP | SP | PUMPED 60 BBL LUBE PILL. SPOTTED 40 BBL AGAINST BHA & LEFT 20 BBL INSIDE DRILL STRING. WAITED ONE HOUR FOR SOAKING THE PILL.
43214.125 | 43214.1875 | 1.5 | DRL | NPT-UP | STK | WORKED ON STUCK STRING WITH COMBINATION OF TORQUE / OVERPULL & COMPRESSION. APPLIED MAX. 80 TON OVERPULL & COMPRESSION & 20 KFT.LB TORQUE. DISPLACED 3 BBL LUBE PILL FROM STRING TO ANNULUS AFTER EVERY 15 MIN - NO SUCCESS.
43214.1875 | 43214.625 | 10.5 | DRL | NPT-UP | STK | RESUMED CIRCULATION. WORKED ON STUCK STRING WITH COMBINATION OF TORQUE / OVERPULL & COMPRESSION. APPLIED MAX. 100 TON OVERPULL & COMPRESSION & 20 KFT.LB TORQUE - NO SUCCESS. MEANWHILE PREPARED BLACK MAGIC PILL OF 2.25 S.G.
43214.625 | 43214.7083 | 2 | DRL | NPT-UP | SP | PUMPED & SPOTTED 45 BBL BLACK MAGIC PILL AGAINST BHA & LEFT 40 BBL INSIDE DRILL STRING. APPLIED 60 TON OVERPULL, KEPT STRING IN TENSION & WAITED ONE HOUR FOR SOAKING THE PILL.
43214.7083 | 43215 | 7 | DRL | NPT-UP | STK | WORKED ON STUCK STRING WITH COMBINATION OF TORQUE / OVERPULL & COMPRESSION. APPLIED MAX. 100 TON OVERPULL & COMPRESSION & 20 KFT.LB TORQUE. DISPLACED 1 BBL BLACK MAGIC PILL FROM STRING TO ANNULUS AFTER EVERY 30 MIN - NO SUCCESS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-04-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43215 | 43215.25 | 6 | DRL | NPT-UP | STK | CONTINUED WORKING ON STUCK STRING WITH COMBINATION OF TORQUE / OVERPULL & COMPRESSION. APPLIED MAX. 100 TON OVERPULL & COMPRESSION & 20 KFT.LB TORQUE. DISPLACED 1 BBL BLACK MAGIC PILL FROM STRING TO ANNULUS AFTER EVERY 30 MIN - NO SUCCESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE & SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | WORKING ON STUCK STRING
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | SPOTTED LUBE PILL & BLACK MAGIC PILL. WORKED ON STUCK STRING. NO SUCCESS
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | WORK & RELEASE STUCK STRING.
REMARKS
Formulas:
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14