## DDR#125
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 124.9792
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-09-06
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4455 | 4455 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 124.9792
RIG REP.: |  | TARIQ BUTT / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 4455 | 4455 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-09-05 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 21 |  | BHA NO. |  |  | 24 | IN (M) |  | 4455 |  | OUT (M) |  |  | STRING (BBL) | 92.1
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 8 RR2 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1993.2
DEPTH, MD (M) | 4455 | 4455 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 12.25 |  | PDC BIT |  |  | 12.25 |  |  |  |  | 0.41 | 0.2 |  | PITS (BBL) | 854
MW IN (SG) | 2.32 | 2.32 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | BAKER HUGHES |  | NEAR BIT STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 1.6 | 0.35728 |  | ACT. SYS (BBL) | 2939.3
MW OUT (SG) | 2.32 | 2.32 | INST. ROP (M/HR) |  |  |  | TYPE |  |  | TD606FX |  | PONY DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 4.48 | 1.0004 |  | RESV. SYS (BBL) | 1198
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 5293592 |  | ST. STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 1.55 | 0.34611 |  | KILL MUD (BBL) | 0
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  | M223 |  | L. SAVER SUB |  |  | 8.25 | 3.25 |  | 6 5/8 REG |  | 0.39 | 0.087086 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 58 | 59 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 6 x 13/32 |  | SPSA |  |  | 8.5 | 3.25 |  | 6 5/8 REG |  | 9.42 | 2.1035 |  | TOTAL | 4137.3
PV | 49 | 50 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4455 |  | U. SAVER SUB |  |  | 8.25 | 3.25 |  | 6 5/8 REG |  | 0.47 | 0.10495 |  | DIESEL (LTR)
YIELD POINT | 27 | 26 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.33 | 0.52029 |  | RIG TANK | 131256
GEL ST. | 18/29 | 17/29 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | NMDC |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 9.34 | 2.0856 |  | CAMP TANK | 19577
WL (ml/30 min) | 5 | 5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | PBL SUB |  |  | 8.125 | 3.5 |  | 6 5/8 REG |  | 3.48 | 0.77708 |  | CONSUMED | 4799
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | 9 x DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 83.09 | 18.5539 |  | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) |  |  |  |  | D. JAR |  |  | 7.8125 | 3 |  | 6 5/8 REG |  | 9.43 | 2.1057 |  | TOTAL | 150833
ALK (FILT.) | 0.3/2.7 | 0.3/2.7 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) |  |  |  |  | 3 x DC |  |  | 8 | 2.9375 |  | 6 5/8 REG |  | 27.64 | 6.172 |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. |  |  |  |  | X-OVER |  |  | 7.625 | 2.875 |  | 5 1/2 FH |  | 0.76 | 0.16971 |  | RIG STORAGE | 430000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  |  |  | 9 x HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.95 | 7.8748 |  | CAMP STORAGE | 68000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 137100
KCl (mg/l) | 43854 | 43854 | JAR |  | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 126100
CHLORIDES (mg/l) | 24000 | 24000 | 5 1/2" HWDPS |  | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 498000
HARDNESS (mg/l) | 400 | 410 | 9 1/2" DCS |  | STAB - 3 |  | TFA (IN²) |  |  | 0.78 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS |  | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 239.34 |  |  | MPCL | 7
OIL % | 3.75 | 3.75 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 26 |  |  | MPCL SERV | 18
SOLIDS % | 44.76 | 44.81 | DAILY ON BOTTOM HRS | [8 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 17 |  |  | SECURITY
M.B.T. (lb/bbl) | 11 | 11 | DAILY CIRC. HRS | [8 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4340 |  | 1.33 |  | 254.87 |  |  | 0.26 |  | MWD |  | TOTAL | 110
DAILY WELL COST (US$) |  | 36469 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4368 |  | 1.53 |  | 246.46 |  |  | 0.31 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 9654725.8634 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4398 |  | 1.7 |  | 245.61 |  |  | 0.71 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 48.5% | MUD CLEANER | 3 x 170 | [7 empty] | 4427 |  | 1.65 |  | 244.55 |  |  | 0.38 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.27SG) | [5 empty] | MAASP (PSI) | 0
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4392 | 450/400/400 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4392 | 550/500/500 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-08-19 | 2019-09-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50/80 |  | 4392 | 620/560/560/1050 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-08-30 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-08-19 | 2019-09-18 | NEXT BOP TEST DATE |  | 2019-09-13 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-05
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43713 | 43713.1771 | 4.25 | DRL | NPT-UP | F | POOH ON ELEVATORS FROM 586M TO 73M (TOP OF BHA). PUMPED OUT EVERY 10TH STAND.
43713.1771 | 43713.1875 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43713.1875 | 43713.2396 | 1.25 | DRL | NPT-UP | F | POOH FISHING BHA FROM 73M TO SURFACE , RECOVERED FISH (AL-HAMDU-LILLAH).
43713.2396 | 43713.4062 | 4 | DRL | NPT-UP | F | ATTEMPTED TO B/O BIT. FOUND ALL CONNECTIONS OVER TORQUED. L/D BIT + 2 x STABS + PONY DC + SPSA + FISHING ASSEMBLY.
43713.4062 | 43713.5208 | 2.75 | DRL | NPT-UP | BHA | L/D 9x 8" DC + 9x 5 1/2" HWDP SINGLE BY SINGLE.
43713.5208 | 43713.6458 | 3 | DRL | PT-P | BHA | P/U & M/U 12 1/4'' RR PDC BIT + 12 1/8'' NBS + 8" PONY DC + SPSA (MWD) + 12 1/8" ST. STAB & RIH DOWN TO 20M.
43713.6458 | 43713.6667 | 0.5 | DRL | PT-P | E/C | FUNCTION TESTED MWD TOOL, OK.
43713.6667 | 43713.6875 | 0.5 | DRL | PT-P | BHA | P/U & M/U NMDC + PBL SUB WITH EXTENDED CATCHER.
43713.6875 | 43713.7292 | 1 | DRL | PT-P | E/C | FUNCTION TESTED PBL SUB, OK. RETRIEVED BALLS & DART FROM CATCHER SUB.
43713.7292 | 43713.875 | 3.5 | DRL | PT-P | BHA | RIH BHA FROM 31M TO 239M. WHILE RIH, P/U 12x 8" DC, D. JAR & 9x 5 1/2" HWDP SINGLE BY SINGLE.
43713.875 | 43714 | 3 | DRL | PT-P | RIH | CONT'D RIH FROM 239M TO 1465M. FILLED UP STRING EVERY 10 STDS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-06
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43714 | 43714.1042 | 2.5 | DRL | PT-P | RIH | CONT'D RIH FROM 1465M TO 2381M. FILLED UP STRING EVERY 10 STDS.
43714.1042 | 43714.1667 | 1.5 | DRL | PT-P | DP | M/U 5x 5 1/2" DP STDS IN MOUSE HOLE & RACKED BACK. MEANWHILE, CIRCULATED THROUGH CIRC HEAD.
43714.1667 | 43714.25 | 2 | DRL | PT-P | RIH | CONT'D RIH FROM 2381M TO 2724M & IS IN PROGRESS. REAMED DOWN IN INTERVAL (2520-2525M).
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH FISH TO SURFACE. L/D FISH & FISHING ASSY. RIH RR 12 1/4" PDC BIT WITH INSPECTED ROTARY BHA DOWN TO 1465M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH DOWN TO BOTTOM. CIRCULATE TO HOMOGENIZE MUD. DRILL AHEAD 12 1/4" HOLE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14