## DDR#127
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 126.9792
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-09-08
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4477 | 4477 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 126.9792
RIG REP.: |  | TARIQ BUTT / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 4484 | 4484 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 22
2019-09-07 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | RUN NO. |  |  | 21 |  | BHA NO. |  |  | 24 | IN (M) |  | 4455 |  | OUT (M) |  |  | STRING (BBL) | 301.5
CHECK TIME | 6:50 | 23:59 | MD @ 00:00HR (M) |  | 4477 |  | BIT NO. |  |  | 8 RR2 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1713.2
DEPTH, MD (M) | 4456 | 4477 | TVD @ 00:00HR (M) |  | 4477 |  | SIZE (IN) |  |  | 12.25 |  | PDC BIT |  |  | 12.25 |  |  |  |  | 0.41 | 0.2 |  | PITS (BBL) | 756
MW IN (SG) | 2.32 | 2.3 | DAILY PROGRESS (M) |  | 22 |  | MANUFACTURER |  |  | BAKER HUGHES |  | NEAR BIT STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 1.6 | 0.35728 |  | ACT. SYS (BBL) | 2770.7
MW OUT (SG) | 2.32 | 2.3 | INST. ROP (M/HR) |  | 2.15 |  | TYPE |  |  | TD606FX |  | PONY DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 4.48 | 1.0004 |  | RESV. SYS (BBL) | 1403
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 1.58 |  | SERIAL NO. |  |  | 5293592 |  | ST. STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 1.55 | 0.34611 |  | KILL MUD (BBL) | 0
FL TEMP. °F | 165 | 177 | AVG. WOB (TON) |  | 8-10 |  | IADC CODE |  |  | M223 |  | L. SAVER SUB |  |  | 8.25 | 3.25 |  | 6 5/8 REG |  | 0.39 | 0.087086 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 70 | 58 | AVG. RPM SURFACE |  | 110-130 |  | NOZZLES (1/32") |  |  | 6 x 13/32 |  | SPSA |  |  | 8.5 | 3.25 |  | 6 5/8 REG |  | 9.42 | 2.1035 |  | TOTAL | 4173.7
PV | 50 | 49 | AVG. RPM DOWNHOLE |  | 110-130 |  | DEPTH IN (M) |  |  | 4455 |  | U. SAVER SUB |  |  | 8.25 | 3.25 |  | 6 5/8 REG |  | 0.47 | 0.10495 |  | DIESEL (LTR)
YIELD POINT | 28 | 27 | FLOWRATE (GPM) |  | 600-620 |  | DEPTH OUT (M) |  |  |  |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.33 | 0.52029 |  | RIG TANK | 112593
GEL ST. | 19/29 | 17/30 | PRESSURE (PSI) |  | 3600-4100 |  | METERAGE (M) |  |  | 22 |  | NMDC |  |  | 8.25 | 2.875 |  | 6 5/8 REG |  | 9.34 | 2.0856 |  | CAMP TANK | 18228
WL (ml/30 min) | 4.8 | 5.4 | TORQ. ON-BTM (KLB-FT) |  | 7-9 |  | RPM SURF. |  |  | 110-130 |  | PBL SUB |  |  | 8.125 | 3.5 |  | 6 5/8 REG |  | 3.48 | 0.77708 |  | CONSUMED | 10754
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 4-5 |  | RPM BTM. |  |  | 110-130 |  | 9 x DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 83.09 | 18.5539 |  | RECEIVED
ALK (MUD) | 0.4 | 0.5 | STRING WT. (TON) - ROT |  | 185 |  | WOB (TON) |  |  | 8-10 |  | D. JAR |  |  | 7.8125 | 3 |  | 6 5/8 REG |  | 9.43 | 2.1057 |  | TOTAL | 130821
ALK (FILT.) | 0.3/2.7 | 0.4/2 | PICK-UP WT. (TON) |  | 195 |  | AVG. ROP (M/HR) |  |  | 1.5771 |  | 3 x DC |  |  | 8 | 2.9375 |  | 6 5/8 REG |  | 27.64 | 6.172 |  | WATER (LTR)
PH | 9.5 | 9.8 | SLACK-OFF WT. (TON) |  | 165 |  | BIT ROT HRS. |  |  | 13.95 |  | X-OVER |  |  | 7.625 | 2.875 |  | 5 1/2 FH |  | 0.76 | 0.16971 |  | RIG STORAGE | 421000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  | 105.31 |  | 9 x HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.95 | 7.8748 |  | CAMP STORAGE | 69000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  | 105.31 | [12 empty] | CONSUMED | 192500
KCl (mg/l) | 45761 | 45761 | JAR | 28.68 | STAB - 1 | 28.68 | ANN. VEL. (M/MIN) |  |  | 46.1 | [12 empty] | RECEIVED | 192500
CHLORIDES (mg/l) | 25000 | 25000 | 5 1/2" HWDPS | 28.68 | STAB - 2 | 28.68 | JET VELOCITY (M/SEC) |  |  | 75.4 | [12 empty] | TOTAL | 490000
HARDNESS (mg/l) | 460 | 450 | 9 1/2" DCS |  | STAB - 3 | 28.68 | TFA (IN²) |  |  | 0.78 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 28.68 | SPSA | 28.68 | HSI |  |  | 3.16 |  | TOTAL LENGTH (M) | [7 empty] | 239.34 |  |  | MPCL | 7
OIL % | 4 | 4 | DAILY BHA ROT. HRS |  | 19.35 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 26 |  |  | MPCL SERV | 16
SOLIDS % | 44.73 | 44.43 | DAILY ON BOTTOM HRS |  | 13.95 |  | BIT NO. 10 RR |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 17 |  |  | SECURITY
M.B.T. (lb/bbl) | 11 | 11 | DAILY CIRC. HRS |  | 21.7 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4368 |  | 1.53 |  | 246.46 |  |  | 0.31 |  | MWD |  | TOTAL | 107
DAILY WELL COST (US$) |  | 53254.13 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4398 |  | 1.7 |  | 245.61 |  |  | 0.71 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 9749906.4934 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4427 |  | 1.65 |  | 244.55 |  |  | 0.38 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 48.98% | MUD CLEANER | 3 x 170 | [7 empty] | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.32SG) | [5 empty] | MAASP (PSI) | 68.6996
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4455 | 185/200 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4455 | 285/300 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-08-19 | 2019-09-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4455 | 395/430 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-08-30 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 7.5 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-08-19 | 2019-09-18 | NEXT BOP TEST DATE |  | 2019-09-13 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 14 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43715 | 43715.1042 | 2.5 | DRL | PT-P | RW | WASHED / REAMED DOWN FROM 4163M TO 4419M. REAMED DOWN IN INTERVALS (4175-4181M), (4213-4214M), (4235-4243M) & (4398-4401M).
43715.1042 | 43715.1667 | 1.5 | DRL | PT-P | RW | OBSERVED COMPRESSION AT 4419M. HARD REAMED FROM 4419M TO 4423M & CONT'D REAMING DOWN TO BOTTOM.
43715.1667 | 43715.5104 | 8.25 | DRL | PT-P | D | RESUMED DRILLING & DRILLED 12 1/4" HOLE FROM 4455M TO 4463M. OBSERVED LEAKAGE IN WASH PIPE.
43715.5104 | 43715.5312 | 0.5 | DRL | NPT-UP | POOH | POOH FROM 4463M TO 4386M.
43715.5312 | 43715.5625 | 0.75 | DRL | NPT-UP | RR | REPLACED WASH PIPE. MEANWHILE, CIRCULATED & ROTATED THE STRING. PRESSURE TESTED @ 2000 PSI - OK.
43715.5625 | 43715.6042 | 1 | DRL | NPT-UP | RW | RIH FROM 4386M TO 4444M & WASHED / REAMED DOWN TO BOTTOM.
43715.6042 | 43715.8646 | 6.25 | DRL | PT-P | D | DRILLED 12 1/4" HOLE FROM 4463M TO 4472M.
43715.8646 | 43715.9062 | 1 | DRL | PT-P | RW | WHILE REAMING PRIOR CONNECTION, OBSERVED TIGHT SPOTS / ROTARY STALLING IN DRILLED INTERVAL. CLEARED THE SAME & M/U CONNECTION.
43715.9062 | 43716 | 2.25 | DRL | PT-P | D | CONT'D DRILLING 12 1/4" HOLE FROM 4472M TO 4477M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-08
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43716 | 43716.25 | 6 | DRL | PT-P | D | DRILLED 12 1/4" HOLE FROM 4477M TO 4484M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12 1/4'' HOLE IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | WASHED / REAMED FROM 4163M TO BOTTOM. DRILLED 12 1/4" HOLE FROM 4455M TO 4477M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 12 1/4" HOLE.
REMARKS |  |  | WASH PIPE LEAKED AFTER 150 HOURS.
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14