## DDR#13
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 13
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-17
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / ADNAN |  |  | MD/TVD @ 00:00HRS: |  | 665 / 665 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 12.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 745 / 745 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 79
2019-05-16 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | SPUD MUD |  | HOLE SIZE (IN) |  | 17 1/2'' |  | BIT No. |  | 4 |  | BHA No. |  |  | 5 | IN (M) |  | 590 |  | OUT (M) |  |  | STRING (BBL) | 38
CHECK TIME | 12:00 | 23:45 | MD @ 00:00HR (M) |  | 665 |  | SIZE (IN) |  | 17 1/2'' |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 653.4
DEPTH, MD (M) | 590 | 665 | TVD @ 00:00HR (M) |  | 665 |  | MANUFACTURER |  | NOV |  | 17 1/2'' PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 |  |  | PITS (BBL) | 688
MW IN (SG) | 1.35 | 1.35 | DAILY PROGRESS (M) |  | 79 |  | TYPE |  | TFH519S |  | PD |  |  | 9 | 5.125 |  | 7 5/8 REG |  | 4.29 | 1.3667 |  | ACT. SYS (BBL) | 1379.4
MW OUT (SG) |  | 1.35 | INST. ROP (M/HR) |  | 19.2 |  | SERIAL NO. |  | E260745 |  | X/O |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.76 | 0.24212 |  | RESV. SYS (BBL) | 607
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 17.63 |  | IADC CODE |  | S422 |  | MUD MOTOR (SLEEVE STAB) |  |  | 9.625 | 7 |  | 6 5/8 REG |  | 10.53 | 3.3546 |  | KILL MUD (BBL) | 400
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 6 |  | NOZZLES |  | 3X 18, 2 X 16 |  | X/O |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 1.1 | 0.35043 |  | KILL MW (SG) | 1.6
µ FUNNEL (SEC) | 62 | 60 | AVG. RPM SURFACE |  | 55 |  | DEPTH IN (M) |  | 590 |  | FLOAT SUB |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 0.78 | 0.24849 |  | TOTAL | 1986.4
PV | 27 | 27 | AVG. RPM DOWNHOLE |  | 150 |  | DEPTH OUT (M) |  |  |  | ST. STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.44 | 0.77732 |  | DIESEL (LTR)
YIELD POINT | 23 | 26 | FLOWRATE (GPM) |  | 902 |  | METERAGE (M) |  | 75 |  | LOWER S. SUB |  |  | 9.625 | 3.5 |  | 7 5/8 REG |  | 0.78 | 0.24849 |  | RIG TANK | 140496
GEL ST. | 9/14 | 05/8 | PRESSURE (PSI) |  | 1926 |  | RPM SURF. |  | 70 |  | SLIM PULSE |  |  | 9.5625 | 5 |  | 7 5/8 REG |  | 9.27 | 2.9532 |  | CAMP TANK | 22950
WL (ml/30 min.) | 6 | 5 | TORQ. ON-BTM (KLB-FT) |  | 5-8 |  | RPM BTM. |  | 170 |  | UPPER S. SUB |  |  | 9.5625 | 3 |  | 7 5/8 REG |  | 0.67 | 0.21344 |  | CONSUMED | 5304
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | WOB (TON) |  | 8-10 |  | ST. STAB |  |  | 17.375 | 2.9375 |  | 7 5/8 REG |  | 2.37 | 0.75502 |  | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 85 |  | AVG. ROP (M/HR) |  | 16.7411 |  | NMDC |  |  | 9 | 3.5 |  | 7 5/8 REG |  | 9.36 | 2.9818 |  | TOTAL | 163446
ALK (FILT.) | 0.3 | 0.5 | PICK-UP WT. (TON) |  | 83 |  | BIT ROT HRS. |  | 4.48 |  | 3 X 9 1/2'' DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 27.53 | 8.7703 |  | WATER (LTR)
PH | 10 | 9.5 | SLACK-OFF WT. (TON) |  | 83 |  | K-REVS IN 24 HRS |  | 40.39 |  | X/O |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.93 | 0.29627 |  | RIG STORAGE | 500000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 40.39 |  | 2 X 8'' DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.34 | 4.0953 |  | CAMP STORAGE | 90000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 24.8 |  | D. JAR |  |  | 7.9375 | 3.0625 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | CONSUMED | 125400
KCl (mg/l) | 38134 | 36227 | JAR | 19.35 | NMDC | 8.34 | JET VELOCITY (M/SEC) |  | 77.19 |  | 2 X 8'' DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.43 | 4.1154 |  | RECEIVED | 130400
CHLORIDES (mg/l) | 19000 | 18000 | MOTOR | 8.34 | STAB - 1 | 8.34 | TFA (IN²) |  | 1.138 |  | X/O |  |  | 7.3125 | 2.8125 |  | 5 1/2 FH |  | 0.81 | 0.18087 |  | TOTAL
HARDNESS (mg/l) | 280 | 280 | 11'' DCS |  | STAB - 2 | 8.34 | HSI |  | 1.14 |  | 10 X 5 1/2'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 94.38 | 3.4703 |  | POB
OIL% |  |  | 9 1/2" DCS | 19.35 | SPSA | 8.34 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 212.69 |  |  | MPCL | 5
LUBRICANT % | 0.5 | 0.5 | BHA ROT. HRS |  | 8.34 |  | BIT No. 3 |  | 2-2-FC-A-E-I-NO-BHA |  | BHA WT. IN MUD (TON) | [7 empty] | 33 |  |  | MPCL SERV | 23
SOLIDS % | 11.5 | 11.56 | ON BOTTOM HRS |  | 4.48 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 23 |  |  | SECURITY | 2
M.B.T. (lb/bbl) | 7.5 | 5 | CIRC. HRS |  | 10.47 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 54
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 100 | 2 X 100 |  | 30" CONDUCTOR |  |  | 37 | [11 empty] | TOTAL | 114
DAILY WELL COST (US$) |  | 113490 | SHAKER-2 | 1 X 100 | 2 X 100 |  | 20'' SURFACE/ K-55, 133# |  |  | 579 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 1884092 | SHAKER-3 | 1 X 100 | 2 X 100 | [16 empty] | LAST CSG SIZE | 20''
% OF AFE SPENT |  | 9.465% | MUD CLEANER | 3 X 140 | [17 empty] | LOT (EMW) | 1.95
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 494
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 30 |  | 665 |  | 150/150 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 40 |  | 665 |  | 200/200 |  | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 50 |  | 665 |  | 225/225 |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-05-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | BRINE LOSSES IN 24 HRS |  |  |  |  | BRINE LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2019-05-28 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-16
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43601 | 43601.0625 | 1.5 | DRL | PT-P | D | CONT'D DRILLING 17 1/2'' HOLE FROM 586M TO 590M.
43601.0625 | 43601.1042 | 1 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE.
43601.1042 | 43601.1146 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43601.1146 | 43601.1875 | 1.75 | DRL | PT-P | POOH | POOH FROM 590M TO 178M.
43601.1875 | 43601.2812 | 2.25 | DRL | PT-P | BHA | POOH FROM 178M TO SURFACE. L/D 3X9.5" DCS; 8" JAR; BIT & BIT SUB.
43601.2812 | 43601.3854 | 2.5 | DRL | PT-P | BHA | M/UP 17-1/2" RR TC BIT WITH POWER DRIVE & RIH. M/U TDS. CIRCULATED & FUNCTION TESTED. DOWN LINKED / PROGRAMMED POWER DRIVE DURING CIRCULATION. FUNCTION TESTED AFTER DOWN LINKING. OBSERVED WORKING SATISFACTORILY. RECORDED 500 PSI SPP @ 700 GPM.
43601.3854 | 43601.5 | 2.75 | DRL | PT-P | BHA | P/UP MUD MOTOR;X-OVERS; FLOAT SUB; 17-3/8" S.STAB; LOWER SAVER SUB; SPSA; UPPER SAVER SUB. M/UP WITH POWER DRIVE & RIH AS PER BHA DOWN TO 31 M. SET SLIM PUSE INSIDE SPSA. M/UP TDS. FUNCTION TESTED @ 600 GPM/600 PSI. MWD WORKING GOOD. PULLED BACK TO ROTARY TABLE. L/DOWN TC BIT. M/U 17.5" NEW PDC (NOV, TFH519S, SR # E260745, 3 X18 + 2 X 16) WITH PD.
43601.5 | 43601.625 | 3 | DRL | PT-P | BHA | CONT'D RIH SCHL VORTEX BHA DOWN TO 211M. WHILE RIH BHA P/UP 8'' D.JAR , 1 X 8'' DC & 4 X 5 1/2'' HWDP.
43601.625 | 43601.6458 | 0.5 | DRL | PT-P | RS | SERVICED TDS.
43601.6458 | 43601.7188 | 1.75 | DRL | PT-P | RIH | CONT'D RIH FROM 211M TO BOTTOM AT 590M. FILLED UP STRING EVERY 10 STDS. PRECAUTIONARY WASHED DOWN LAST SINGLE.
43601.7188 | 43601.75 | 0.75 | DRL | PT-P | DM | RESUMED DRILLING, DRILLED 17 1/2'' HOLE FROM 590M TO 609M. WHILE DRILLING OBSERVED EXCESSIVE FLOW AT SHAKERS.
43601.75 | 43601.7708 | 0.5 | DRL | PT-P | CIR | CIRCULATED TO CONDITION MUD MEANWHILE REPLACED SHAKER SCREENS FROM 120 MESH SIZE TO 100 MESH SIZE (TO HANDLE FLOW AT SHAKERS).
43601.7708 | 43602 | 5.5 | DRL | PT-P | DM | CONT'D DRILLING 17 1/2'' HOLE FROM 609M TO 665M. REAMED / WASHED DRILLED INTERVAL & RECORDED MWD SURVEY AT CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-17
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43602 | 43602.25 | 6 | DRL | PT-P | DM | CONT'D DRILLING 17 1/2'' HOLE FROM 665M TO 745M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | CHINJI / CLAYSTONE, SANDSTONE.
OPERATIONS AT 06:00 HRS |  |  | DRILLING 17 1/2'' HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 17 1/2'' HOLE FROM 586M TO 590M, CIRCULATION, FLOW CHECKED, POOH TO SURFACE, P/UP NEW PDC BIT + VORTEX BHA. RIH TO BTM AT 590M, RESUMED DRILLING, DRILLED 17 1/2'' HOLE FROM 590M TO 665M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 17 1/2'' HOLE.
REMARKS |  |  | PUMPED 20 BBL HI-VIS BRIDGE PILL AT EVERY STAND DOWN.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14