## DDR#130
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 130
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-04-30
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR RAO / AHSEN / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4199 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 129.5833
RIG REP.: |  | JAVED IQBAL / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 4199 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-04-29 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 12.25 |  | BIT No. |  | 7 | [5 empty] | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | -
CHECK TIME | 23:59 |  | MD @ 00:00HR (M) |  | 4199 |  | SIZE (IN) |  | 12 1/4" |  |  |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 2026
DEPTH, MD (M) | 4199 |  | TVD @ 00:00HR (M) |  | 4199 |  | MANUFACTURER |  | NOV | [12 empty] | PITS (BBL) | 743
MW IN (SG) | 2.13 |  | DAILY PROGRESS (M) |  | 0 |  | TYPE |  | SKH616M | [12 empty] | ACT. SYS (BBL) | 2769
MW OUT (SG) |  |  | INST. ROP (M/HR) |  | - |  | SERIAL NO. |  | E244697 | [12 empty] | RESV. SYS (BBL) | 1214
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | M422 | [12 empty] | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 6x18/32" | [12 empty] | KILL MW (SG) | 2.3
µ FUNNEL (SEC) | 80 |  | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4188 | [12 empty] | TOTAL | 4583
PV | 41 |  | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  | 4199 | [12 empty] | DIESEL (LTR)
YIELD POINT | 39 |  | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  | 11 | [12 empty] | RIG TANK | 111800
GEL ST. | 21/44 |  | PRESSURE (PSI) |  |  |  | RPM SURF. |  | 100-120 | [12 empty] | CAMP TANK | 29000
WL (ml/30 min.) | 5.9 |  | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  | 100-120 | [12 empty] | CONSUMED | 6900
CT ( in/32) | 2 |  | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  | 4-10 | [12 empty] | RECEIVED
ALK (MUD) | 0.3 |  | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  | 1.0064 | [12 empty] | TOTAL | 140800
ALK (FILT.) | 0.5/1.2 |  | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  | 10.93 | [12 empty] | WATER (LTR)
PH | 9.5 |  | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  | - | [12 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT IN HOLE BHA |  |  |  | CUMM. K-REVS |  | 138.3 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 37.9 | [12 empty] | CONSUMED | 35000
KCl (mg/l) | 43282 |  | JAR | 30.43 | STAB - 1 | 30.43 | JET VELOCITY (M/SEC) |  | 37.3 | [12 empty] | RECEIVED | 35000
CHLORIDES | 19500 |  | 5" HWDPS | 30.43 | STAB - 2 | 30.43 | TFA (IN²) |  | 1.49 | [12 empty] | TOTAL | 440000
CALCIUM | 200 |  | 8" DCS | 30.43 |  |  | HSI |  | 0.7 | [12 empty] | POB
OIL% | 5 |  | 9 1/2" DCS |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 0 |  |  | MPCL | 4
LUBE % | 2 |  | BHA ROT. HRS |  | 30.43 |  | BIT No.7 |  | 1-1-WT-A-X-I-BT-HP |  | BHA WT. IN MUD (TON) | [7 empty] | 0 |  |  | MPCL SERV | 15
SOLIDS % | 36.34 |  | ON BOTTOM HRS |  | 10.93 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 0 |  |  | SECURITY | 4
M.B.T. | 12.5 |  | CIRC. HRS |  | 99.61 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 100 | 2 x 140 |  | 20" SURFACE CASING |  |  | 594 | 3862 |  | 1.75 |  | 98.28 |  |  | 0.17 |  | EMS |  | TOTAL | 108
DAILY WELL COST (US$) |  | 35019.5961 | SHAKER-2 | 2 x 140 | 1 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 3870 |  | 1.66 |  | 98.65 |  |  | 0.35 |  | EMS |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 9167475.0956 | SHAKER-3 | 2 x 140 | 1 x 140 |  | 9 5/8" PRODUCTION CSG |  |  |  | 3890 |  | 1.43 |  | 99.8 |  |  | 0.35 |  | EMS |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 50.79% | MUD CLEANER | 1 x 170 + 2 x 140 |  |  | 7" LINER |  |  |  | 4187 |  | 1 |  | - |  |  | - |  | TOTCO |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P2/P3) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-04-16 | 2018-05-01 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4188 |  | 800/800 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4188 |  | 950/950 |  | CHINJI | 342
FIRE DRILL | 2018-04-18 | 2018-05-18 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4188 |  | 1100/1100 |  | KAMLIAL | 1255
PIT DRILL | 2018-04-25 | 2018-05-25 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-04-16 | 2018-05-01 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-04-30 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 0 | MUD LOSSES IN 24 HRS |  |  | 0 |  | MUD LOSSES |  |  |  | 133 |  | SAKESAR
STRETCHER DRILL | 2018-04-18 | 2018-05-18 | NEXT BOP TEST DATE |  | 2018-05-14 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-04-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43219 | 43219.0521 | 1.25 | DRL | NPT-UP | CIR | CONTINUED CIRCULATION TO HOMOGENIZE MUD COLUMN AT 2.13 SG.
43219.0521 | 43219.0625 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43219.0625 | 43219.3438 | 6.75 | DRL | NPT-UP | POOH | POOH 12 1/4" BIT FROM 3809M TO 2354M (13 3/8" CSG SHOE) ON ELEVATORS.
43219.3438 | 43219.3542 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43219.3542 | 43219.8438 | 11.75 | DRL | NPT-UP | POOH | POOH 12 1/4" BIT FROM 2354M TO 197M (BHA TOP). WHILE POOH L/D 54 x 5" G-105 DP DUE TO WORN OUT TOOL JOINTS AND BENT PIPE. .
43219.8438 | 43219.8542 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43219.8542 | 43219.9792 | 3 | DRL | NPT-UP | BHA | POOH 12 1/4" BIT FROM 197M TO SURFACE. L/D STABS & BIT.
43219.9792 | 43220 | 0.5 | DRL | PT-P | WB | HELD PJSM. RETRIEVED WEAR BUSHING. M/UP BOP TEST ASSEMBLY.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-04-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43220 | 43220.125 | 3 | DRL | PT-P | BOPT | SET TEST PLUG IN 13-5/8" CHS. FLUSHED BOP STACK WITH WATER. P/TESTED UPPER VARIABLE PIPE RAMS (4 1/2" - 7"), HCR & MANUAL VALVES @ KILL LINE / CHOKE LINE; IBOP @ 300 PSI / 6500 PSI FOR 5 MIN / 10 MIN - OK. P/TESTED ANNULAR BOP, ROTARY HOSE / STANDPIPE @ 300 PSI / 5000 PSI FOR 5 MIN / 10 MIN - OK. P/TESTED LOWER PIPE RAM BOP (5" RAMS), FOSV @ 300 PSI / 6500 PSI FOR 5 MIN / 10 MIN - OK.
43220.125 | 43220.1875 | 1.5 | DRL | NPT-UP | WB | RETRIEVED TEST PLUG. SET WEAR BUSHING. L/D TEST PLUG ASSEMBLY.
43220.1875 | 43220.25 | 1.5 | DRL | NPT-UP | BHA | M/UP & RIH 12 1/4" PDC BIT WITH PENDULUM BHA TO 88M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE & SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH 12 1/4" BIT.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATED TO HOMOGENIZE MUD. POOH 12-1/4" BIT TO SURFACE. M/UP BOP P/TEST ASSEMBLY.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH 12 1/4" BIT DOWN TO 13-3/8" CSG SHOE, R/D TDS AND WORK ON TDS.
REMARKS
Formulas:
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14