## DDR#133
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 132.9792
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-09-14
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4491 | 4491 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 132.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4491 | 4491 | [5 empty] | DAILY PROGRESS @ 00:00HRS:
2019-09-13 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 23 |  | BHA NO. |  |  | 26 | IN (M) |  | 4491 |  | OUT (M) |  |  | STRING (BBL) | 162.9
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 12 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1912.8
DEPTH, MD (M) | 4491 | 4491 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 12.25 |  | PDC BIT |  |  | 12.25 |  |  |  |  | 0.3 | 0.2 |  | PITS (BBL) | 661
MW IN (SG) | 2.31 | 2.31 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | NEAR BIT STAB |  |  | 12.125 | 4.875 |  | 6 5/8 REG |  | 1.61 | 0.35951 |  | ACT. SYS (BBL) | 2736.7
MW OUT (SG) | 2.31 | 2.31 | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDSiZ616 |  | PONY DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 4.38 | 0.97805 |  | RESV. SYS (BBL) | 1235
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | JP4535 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.36 | 0.52698 |  | KILL MUD (BBL) | 0
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | L. SAVER SUB |  |  | 8 5/16 | 3.25 |  | 6 5/8 REG |  | 0.33 | 0.073689 |  | KILL MW (SG) | 0
µ FUNNEL (SEC) | 72 | 70 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 6 x 14 |  | SPSA |  |  | 8.5 | 3.25 |  | 6 5/8 FH |  | 9.47 | 2.1146 |  | TOTAL | 3971.7
PV | 51 | 52 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4491 |  | U. SAVER SUB |  |  | 8.875 | 2.875 |  | 6 5/8 REG |  | 0.46 | 0.10272 |  | DIESEL (LTR)
YIELD POINT | 27 | 28 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.45 | 0.54708 |  | RIG TANK | 149350
GEL ST. | 15/28 | 15/29 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | PONY NMDC |  |  | 8 3/16 | 2.875 |  | 6 5/8 REG |  | 4.66 | 1.0406 |  | CAMP TANK | 30283
WL (ml/30 min) | 5.1 | 5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | PBL SUB |  |  | 8 | 3.5 |  | 6 5/8 REG |  | 3.48 | 0.77708 |  | CONSUMED | 5772
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | 9 x DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 83.32 | 18.6052 |  | RECEIVED | 48000
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) |  |  |  |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.64 | 2.1526 |  | TOTAL | 179633
ALK (FILT.) | 0.4/2.6 | 0.4/2.6 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) |  |  |  |  | 3 x DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 27.74 | 6.1943 |  | WATER (LTR)
PH | 9.7 | 9.8 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. |  |  |  |  | X-OVER |  |  | 7 13/16 | 2 13/16 |  | 5 1/2 FH |  | 0.79 | 0.17641 |  | RIG STORAGE | 470000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  |  |  | 9 x HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.97 | 7.8766 |  | CAMP STORAGE | 68000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 144100
KCl (mg/l) | 43854 | 43854 | JAR |  | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 148100
CHLORIDES (mg/l) | 24500 | 24500 | 5 1/2" HWDPS |  | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 538000
HARDNESS (mg/l) | 430 | 420 | 9 1/2" DCS |  | STAB - 3 |  | TFA (IN²) |  |  | 0.902 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS |  | SPSA | 51.6 | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 235.96 |  |  | MPCL | 7
OIL % | 4 | 4 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 26 |  |  | MPCL SERV | 17
SOLIDS % | 44.65 | 44.65 | DAILY ON BOTTOM HRS | [8 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 17 |  |  | SECURITY
M.B.T. (lb/bbl) | 11.5 | 11.5 | DAILY CIRC. HRS |  | 2.6 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 54
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4368 |  | 1.53 |  | 246.46 |  |  | 0.31 |  | MWD |  | TOTAL | 110
DAILY WELL COST (US$) |  | 35956.34 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4398 |  | 1.7 |  | 245.61 |  |  | 0.71 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 9990800.7559 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4427 |  | 1.65 |  | 244.55 |  |  | 0.38 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 50.19% | MUD CLEANER | 3 x 170 | [7 empty] | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.32SG) | [5 empty] | MAASP (PSI) | 34.3498
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4455 | 185/200 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4455 | 285/300 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-08-19 | 2019-09-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4455 | 395/430 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-09-13 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-08-19 | 2019-09-18 | NEXT BOP TEST DATE |  | 2019-09-27 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-13
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43721 | 43721.0104 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED, WELL STATIC.
43721.0104 | 43721.1562 | 3.5 | DRL | NPT-UP | BHA | POOH BHA FROM 210M TO SURFACE. WHILE POOH, L/D 9 x 5 1/2" HWDP, 12 x 8" DC, D. JAR, ST. STAB, BIT SUB, JUNK SUB & BIT.
43721.1562 | 43721.375 | 5.25 | DRL | PT-P | BOPT | M/U COMB TOOL ASSY AND RETRIEVED WEAR BUSHING. RIH 2 STDS OF 5 1/2" DP BELOW PLUG & SET TEST PLUG IN 13-5/8" CHS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP, ROTARY HOSE & STAND PIPE MASTER VALVES @ 500/4000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER (VARIABLE 4 1/2"-7") PIPE RAM, LOWER (5 1/2") PIPE RAM, HCR & MANUAL VALVES OF KILL & CHOKE LINE, FOSV, HYD & MANUAL IBOP @ 500/8000 PSI FOR 5/10 MIN - OK. PRESSURE TESTED BLIND/SHEAR RAM AND CO-FLEXIP-MASTER VALVE AT CHOKE MANIFOLD @ 500/8000 PSI FOR 5/10 MIN - OK. RETRIEVED TEST PLUG & R/B 2x 5 1/2" DP STDS. INSTALLED WEAR BUSHING & L/D COMB TOOL ASSY.
43721.375 | 43721.4271 | 1.25 | DRL | PT-P | BHA | M/UP NEW 12 1/4" PDC BIT + 12 1/8'' N.B STAB + 8" PONY DC + 12 1/8" ST. STAB + SPSA.
43721.4271 | 43721.4688 | 1 | DRL | NPT-UP | E/F | ATTEMPTED TO PLACE MWD TOOL IN SPSA, TOOL NOT SEATING PROPERLY. L/D SPSA AND P/U USED SPSA. INSTALLED MWD TOOL.
43721.4688 | 43721.4792 | 0.25 | DRL | PT-P | E/C | FUNCTION TESTED MWD TOOL, OK.
43721.4792 | 43721.5104 | 0.75 | DRL | PT-P | BHA | M/UP 12 1/8" ST. STAB + PONY NMDC + PBL SUB.
43721.5104 | 43721.5417 | 0.75 | DRL | NPT-UP | RR | WHILE F/TEST PBL SUB, OBSERVED PRESSURE FLUCTUATIONS. INSPECTED & FOUND MUD PUMPS SUCTION LINE CHOKED. CLEARED THE SAME.
43721.5417 | 43721.5833 | 1 | DRL | PT-P | E/C | FUNCTION TESTED PBL SUB, OK. RETRIEVED BALLS & DART FROM CATCHER SUB.
43721.5833 | 43721.7292 | 3.5 | DRL | PT-P | BHA | RESUMED RIH BHA FROM 26M TO 235M. WHILE RIH, P/U 12x 8" DC, D. JAR & 9x 5 1/2" HWDP SINGLE BY SINGLE.
43721.7292 | 43722 | 6.5 | DRL | PT-P | RIH | RIH FROM 235M TO 2483M. FILLED UP STRING EVERY 10 STDS. BROKE CIRCULATION AT 2380M INSIDE CSG SHOE FOR 15 MINS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-14
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43722 | 43722.25 | 6 | DRL | PT-P | RIH | RIH FROM 2483M TO 4211M. FILLED UP STRING EVERY 10 STDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE & L/D BHA. P/T BOP STACK. RIH NEW 12 1/4" PDC BIT WITH INSPECTED ROTARY BHA DOWN TO 2483M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH TO BOTTOM. DRILL AHEAD 12 1/4" HOLE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14