## DDR#136
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 135.9792
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-09-17
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4561 | 4561 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 135.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4561 | 4561 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 28
2019-09-16 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 12.25 |  | RUN NO. |  |  | 23 |  | BHA NO. |  |  | 26 | IN (M) |  | 4491 |  | OUT (M) |  |  | STRING (BBL) | 307.4
CHECK TIME | 6:30 | 23:59 | MD @ 00:00HR (M) |  | 4561 |  | BIT NO. |  |  | 12 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1745.9
DEPTH, MD (M) | 4541 | 4561 | TVD @ 00:00HR (M) |  | 4561 |  | SIZE (IN) |  |  | 12.25 |  | PDC BIT |  |  | 12.25 |  |  |  |  | 0.3 | 0.2 |  | PITS (BBL) | 754
MW IN (SG) | 2.3 | 2.3 | DAILY PROGRESS (M) |  | 28 |  | MANUFACTURER |  |  | SMITH |  | NEAR BIT STAB |  |  | 12.125 | 4.875 |  | 6 5/8 REG |  | 1.61 | 0.35951 |  | ACT. SYS (BBL) | 2807.3
MW OUT (SG) | 2.3 | 2.3 | INST. ROP (M/HR) |  | 3.15 |  | TYPE |  |  | MDSiZ616 |  | PONY DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 4.38 | 0.97805 |  | RESV. SYS (BBL) | 629
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 1.54 |  | SERIAL NO. |  |  | JP4535 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.36 | 0.52698 |  | KILL MUD (BBL) | 700
FL TEMP. °F | 180 | 180 | AVG. WOB (TON) |  | 7-10 |  | IADC CODE |  |  | - |  | L. SAVER SUB |  |  | 8 5/16 | 3.25 |  | 6 5/8 REG |  | 0.33 | 0.073689 |  | KILL MW (SG) | 2.33
µ FUNNEL (SEC) | 62 | 65 | AVG. RPM SURFACE |  | 140-145 |  | NOZZLES (1/32") |  |  | 6 x 14 |  | SPSA |  |  | 8.5 | 3.25 |  | 6 5/8 FH |  | 9.47 | 2.1146 |  | TOTAL | 3436.3
PV | 52 | 53 | AVG. RPM DOWNHOLE |  | 140-145 |  | DEPTH IN (M) |  |  | 4491 |  | U. SAVER SUB |  |  | 8.875 | 2.875 |  | 6 5/8 REG |  | 0.46 | 0.10272 |  | DIESEL (LTR)
YIELD POINT | 28 | 28 | FLOWRATE (GPM) |  | 625-640 |  | DEPTH OUT (M) |  |  | - |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.45 | 0.54708 |  | RIG TANK | 113326
GEL ST. | 14/30 | 15/32 | PRESSURE (PSI) |  | 3900-4200 |  | METERAGE (M) |  |  | 70 |  | PONY NMDC |  |  | 8 3/16 | 2.875 |  | 6 5/8 REG |  | 4.66 | 1.0406 |  | CAMP TANK | 28344
WL (ml/30 min) | 5.1 | 4.8 | TORQ. ON-BTM (KLB-FT) |  | 7-9 |  | RPM SURF. |  |  | 140-145 |  | PBL SUB |  |  | 8 | 3.5 |  | 6 5/8 REG |  | 3.48 | 0.77708 |  | CONSUMED | 14531
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 4-6 |  | RPM BTM. |  |  | 140-145 |  | 9 x DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 83.32 | 18.6052 |  | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 185 |  | WOB (TON) |  |  | 7-10 |  | D. JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 9.64 | 2.1526 |  | TOTAL | 141670
ALK (FILT.) | 0.4/2.2 | 0.4/2.2 | PICK-UP WT. (TON) |  | 200 |  | AVG. ROP (M/HR) |  |  | 1.5031 |  | 3 x DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 27.74 | 6.1943 |  | WATER (LTR)
PH | 9.7 | 10 | SLACK-OFF WT. (TON) |  | 175 |  | BIT ROT HRS. |  |  | 46.57 |  | X-OVER |  |  | 7 13/16 | 2 13/16 |  | 5 1/2 FH |  | 0.79 | 0.17641 |  | RIG STORAGE | 430000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  | 158.53 |  | 9 x HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.97 | 7.8766 |  | CAMP STORAGE | 67000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  | 396.19 | [12 empty] | CONSUMED | 353700
KCl (mg/l) | 44807.5 | 45761 | JAR | 60.95 | STAB - 1 | 60.95 | ANN. VEL. (M/MIN) |  |  | 57.9 | [12 empty] | RECEIVED | 285700
CHLORIDES (mg/l) | 25000 | 25500 | 5 1/2" HWDPS | 60.95 | STAB - 2 | 60.95 | JET VELOCITY (M/SEC) |  |  | 68.91 | [12 empty] | TOTAL | 497000
HARDNESS (mg/l) | 420 | 440 | 9 1/2" DCS |  | STAB - 3 | 60.95 | TFA (IN²) |  |  | 0.902 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 60.95 | SPSA | 112.55 | HSI |  |  | 2.8 |  | TOTAL LENGTH (M) | [7 empty] | 235.96 |  |  | MPCL | 7
OIL % | 4 | 4 | DAILY BHA ROT. HRS |  | 23 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 26 |  |  | MPCL SERV | 16
SOLIDS % | 44.63 | 44.74 | DAILY ON BOTTOM HRS |  | 18.24 | [6 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 17 |  |  | SECURITY
M.B.T. (lb/bbl) | 11.5 | 11.5 | DAILY CIRC. HRS |  | 23.08 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 57
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 108
DAILY WELL COST (US$) |  | 61211.8125 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 10165232.5684 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 51.07% | MUD CLEANER | 3 x 170 | [7 empty] | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.30SG) | [5 empty] | MAASP (PSI) | 68.6996
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4491 | 425/460 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4491 | 520/550 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-08-19 | 2019-09-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4491 | 615/635 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-09-13 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 28 |  | CHORGALI
STRETCHER DRILL | 2019-08-19 | 2019-09-18 | NEXT BOP TEST DATE |  | 2019-09-27 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 16 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-16
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43724 | 43724.3854 | 9.25 | DRL | PT-P | D | DRILLED 12 1/4" HOLE FROM 4533M TO 4543M.
43724.3854 | 43724.4583 | 1.75 | DRL | NPT-UP | RR | OBSERVED DRAW WORKS BRAKES ENGAGED. REPLACED THE SOLENOID. MEANWHILE, CIRCULATED AND ROTATED STRING.
43724.4583 | 43724.8438 | 9.25 | DRL | PT-P | D | DRILLED 12 1/4" HOLE FROM 4543M TO 4555M. WASHED / REAMED DRILLED INTERVAL PRIOR CONNECTION.
43724.8438 | 43724.8646 | 0.5 | DRL | NPT-UP | S | ATTEMPTED TO RECORD MWD SURVEY, NO SUCCESS DUE TO NOISY SIGNALS.
43724.8646 | 43725 | 3.25 | DRL | PT-P | D | DRILLED 12 1/4" HOLE FROM 4555M TO 4561M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-17
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43725 | 43725.0104 | 0.25 | DRL | PT-P | D | DRILLED 12 1/4" HOLE FROM 4561M TO 4561.5M. OBSERVED COMPLETE LOSS.
43725.0104 | 43725.0417 | 0.75 | DRL | NPT-UP | CIR | PUMPED AT 72 GPM THROUGH KILL LINE. OBSERVED NO RETURNS. POOH TO 4545M.
43725.0417 | 43725.2083 | 4 | DRL | NPT-UP | CIR | DROPPED & CHASED PBL ACTIVATION DART AT 215 GPM. PUMPED 150 BBL LCM PILL OF 70 PPB & DISPLACED WITH 200 BBL MUD (STRING OUT 50 BBL LCM PILL). OBSERVED FLUID LEVEL AROUND WELLHEAD DURING LCM DISPLACEMENT.
43725.2083 | 43725.25 | 1 | DRL | NPT-UP | RW | PUMPED OUT FROM 4545M TO 4439M.
TOTAL |  | 6 |  |  |  | TOTAL MUD LOST - 740 BBL
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | POOH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 12 1/4" HOLE FROM 4533M TO 4561M. WORKED ON DRAW WORKS BRAKES.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CURE LOSSES & DRILL AHEAD 12 1/4" HOLE.
REMARKS |  |  | WASH PIPE CIRCULATING HRS = 36.2 @ 0:00 HRS
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14