## DDR#138
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 138
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-05-08
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR RAO / AHSEN / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4231 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 137.5833
RIG REP.: |  | JAVED IQBAL / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 4237 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 32
2018-05-07 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 12.25 |  | BIT No. |  | 7RR1 |  |  |  |  | 17 | IN (M) |  | 4199 |  | OUT (M) |  |  | STRING (BBL) | 262
CHECK TIME | 11:59 | 23:45 | MD @ 00:00HR (M) |  | 4231 |  | SIZE (IN) |  | 12 1/4" |  |  |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1666
DEPTH, MD (M) | 4217 | 4231 | TVD @ 00:00HR (M) |  | 4231 |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 12.25 | 3.25 |  | 6 5/8 REG |  | 0.25 | 0.1 |  | PITS (BBL) | 882
MW IN (SG) | 2.13 | 2.13 | DAILY PROGRESS (M) |  | 32 |  | TYPE |  | SKH616M |  | BIT SUB |  |  | 8-7/16" | 3 |  | 6 5/8 REG |  | 1.07 | 0.4 |  | ACT. SYS (BBL) | 2810
MW OUT (SG) | 2.13 | 2.13 | INST. ROP (M/HR) |  | 2.45 |  | SERIAL NO. |  | E244697 |  | 2 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 18.58 | 4.1489 |  | RESV. SYS (BBL) | 1069
ECD (SG) | 2.15 | 2.15 | AVG. ROP (M/HR) |  | 1.65 |  | IADC CODE |  | M422 |  | STRING STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.45 | 0.54708 |  | KILL MUD (BBL) | 600
FL TEMP. °F | 164 | 159 | AVG. WOB (TON) |  | 6 - 8 |  | NOZZLES |  | 6x18/32" |  | 1 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.1 | 2.032 |  | KILL MW (SG) | 2.3
µ FUNNEL (SEC) | 66 | 65 | AVG. RPM SURFACE |  | 120 |  | DEPTH IN (M) |  | 4199 |  | STRING STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.04 | 0.45553 |  | TOTAL | 4479
PV | 40 | 41 | AVG. RPM DOWNHOLE |  | 120 |  | DEPTH OUT (M) |  |  |  | 9 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 83.24 | 18.5874 |  | DIESEL (LTR)
YIELD POINT | 38 | 38 | FLOWRATE (GPM) |  | 570 |  | METERAGE (M) |  | 32 |  | DRILLING JAR |  |  | 7-5/8'' | 3.125 |  | 6 5/8 REG |  | 5.06 | 1.1299 |  | RIG TANK | 132000
GEL ST. | 15/37 | 16/38 | PRESSURE (PSI) |  | 3100 - 3300 |  | RPM SURF. |  | 120 |  | 1 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.29 | 2.0744 |  | CAMP TANK | 33000
WL (ml/30 min.) | 5.8 | 5.6 | TORQ. ON-BTM (KLB-FT) |  | 7 - 8 |  | RPM BTM. |  | 120 |  | X/OVER |  |  | 8-3/8'' | 2.75 |  | 6 5/8 REG |  | 0.95 | 0.21213 |  | CONSUMED | 11500
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 4 - 6 |  | WOB (TON) |  | 6 - 8 |  | 7 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 65.61 | 4.8835 |  | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  | 165 |  | AVG. ROP (M/HR) |  | 1.7058 | [12 empty] | TOTAL | 165000
ALK (FILT.) | 0.5/1.1 | 0.5/1.0 | PICK-UP WT. (TON) |  | 175 |  | BIT ROT HRS. |  | 18.76 | [12 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 155 |  | K-REVS IN 24 HRS |  | 137.25 | [12 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT IN HOLE BHA |  |  |  | CUMM. K-REVS |  | 266.44 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 36.76 | [12 empty] | CONSUMED | 127720
KCl (mg/l) | 45341 | 44235 | JAR | 72.86 | STAB - 1 | 72.86 | JET VELOCITY (M/SEC) |  | 37 | [12 empty] | RECEIVED | 127720
CHLORIDES | 20500 | 20000 | 5" HWDPS | 72.86 | STAB - 2 | 72.86 | TFA (IN²) |  | 1.49 | [12 empty] | TOTAL | 440000
CALCIUM | 200 | 200 | 8" DCS | 72.86 |  |  | HSI |  | 0.7 | [12 empty] | POB
OIL% | 5 | 5 | 9 1/2" DCS |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 197.64 |  |  | MPCL | 4
LUBE % | 2 | 2 | BHA ROT. HRS |  | 72.86 |  | BIT No. 7RR1 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 25.1918 |  |  | MPCL SERV | 12
SOLIDS % | 36.05 | 36.02 | ON BOTTOM HRS |  | 18.76 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 19.1436 |  |  | SECURITY | 4
M.B.T. | 12.5 | 12.5 | CIRC. HRS |  | 158.92 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 54
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 100 | 1 x 100 |  | 20" SURFACE CASING |  |  | 594 | 3862 |  | 1.75 |  | 98.28 |  |  | 0.17 |  | EMS |  | TOTAL | 109
DAILY WELL COST (US$) |  | 40020.0111 | SHAKER-2 | 2 x 140 | 1 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 3870 |  | 1.66 |  | 98.65 |  |  | 0.35 |  | EMS |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 9318497.6717 | SHAKER-3 | 2 x 140 | 1 x 140 |  | 9 5/8" PRODUCTION CSG |  |  |  | 3890 |  | 1.43 |  | 99.8 |  |  | 0.35 |  | EMS |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 51.63% | MUD CLEANER | 1 x 170 + 2 x 140 |  |  | 7" LINER |  |  |  | 4187 |  | 1 |  | - |  |  | - |  | TOTCO |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P3) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-04-16 | 2018-05-16 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4200 |  | 610/615 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4200 |  | 740/745 |  | CHINJI | 342
FIRE DRILL | 2018-04-18 | 2018-05-18 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4200 |  | 880/890 |  | KAMLIAL | 1255
PIT DRILL | 2018-04-25 | 2018-05-25 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-04-16 | 2018-05-16 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-04-30 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 22 | MUD LOSSES IN 24 HRS |  |  | 0 |  | MUD LOSSES |  |  |  | 133 |  | SAKESAR
STRETCHER DRILL | 2018-04-18 | 2018-05-18 | NEXT BOP TEST DATE |  | 2018-05-14 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 22 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-05-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43227 | 43227.1458 | 3.5 | DRL | NPT-UP | RW | HARD REAMED FROM 4170M TO 4199M (BOTTOM). OBSERVED HI TORQUE & TDS STALLED FREQUENTLY WHILE REAMING.
43227.1458 | 43228 | 20.5 | DRL | PT-P | D | RESUMED DRILLING & DRILLED 12 1/4" HOLE FROM 4199M DOWN TO 4231M. REAMED TWICE AT CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-05-08
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43228 | 43228.25 | 6 | DRL | PT-P | D | DRILLED 12 1/4" HOLE FROM 4231M DOWN TO 4237M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE & SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 12 1/4" HOLE
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | HARD REAMED FROM 4170M TO BTM @ 4199M. DRILLED 12 1/4" HOLE FROM 4199M TO 4231M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 12 1/4" HOLE TO SECTION TD.
REMARKS
Formulas:
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14