## DDR#143
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 143
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-09-24
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 142.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-09-23 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 24 |  | BHA NO. |  |  | 27 | IN (M) |  | 4561.5 |  | OUT (M) |  |  | STRING (BBL) | 300
CHECK TIME | 11:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 13 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1780.6
DEPTH, MD (M) | 4561 | 4561 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 12.25 |  | TRICONE BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.35 | 0.078048 |  | PITS (BBL) | 768
MW IN (SG) | 2.29 | 2.29 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | BAKER |  | BIT SUB |  |  | 8.3125 | 4.9375 |  | 6 5/8 REG |  | 1.03 | 0.22968 |  | ACT. SYS (BBL) | 2848.6
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | VG-09 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.36 | 0.52627 |  | RESV. SYS (BBL) | 745
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 5293867 |  | 1 X DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.25 | 2.0627 |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  | 437 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.45 | 0.54634 |  | KILL MW (SG)
µ FUNNEL (SEC) | 68 | 62 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 X 18'' |  | 2 X DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 18.42 | 4.1076 |  | TOTAL | 3593.6
PV | 50 | 48 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4561.5 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.02 | 0.45045 |  | DIESEL (LTR)
YIELD POINT | 28 | 27 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | 6 X DC's |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 55.65 | 12.4097 |  | RIG TANK | 123472
GEL ST. | 15/29 | 15/26 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | D. JAR |  |  | 8 | 3 |  | 6 5/8 REG |  | 9.64 | 2.1497 |  | CAMP TANK | 23644
WL (ml/30 min) | 4.5 | 4.3 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | 3 X DC's |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 27.74 | 6.1859 |  | CONSUMED | 8687
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | X/O |  |  | 7.8125 | 2.8125 |  | 6 5/8 REG |  | 0.79 | 0.17617 |  | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) |  |  |  |  | 9 X HWDP's |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.97 | 7.8659 |  | TOTAL | 147116
ALK (FILT.) | 0.4/2.2 | 0.4/2.2 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 300000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 74000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 210700
KCl (mg/l) | 45761 | 43854 | JAR | 101.31 | STAB - 1 | 101.31 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 124700
CHLORIDES (mg/l) | 25000 | 24500 | 5 1/2" HWDPS | 101.31 | STAB - 2 | 101.31 | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 374000
HARDNESS (mg/l) | 430 | 430 | 9 1/2" DCS |  | STAB - 3 | 101.31 | TFA (IN²) |  |  | 0.7455 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 101.31 | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 214.67 |  |  | MPCL | 5
OIL % | 4 | 4 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 18 |  |  | MPCL SERV | 18
SOLIDS % | 43.82 | 44.04 | DAILY ON BOTTOM HRS | [8 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 13 |  |  | SECURITY
M.B.T. (lb/bbl) | 11.5 | 11.5 | DAILY CIRC. HRS |  | 19.6 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 106
DAILY WELL COST (US$) |  | 94521 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 10712149 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 53.81% | MUD CLEANER | 3 x 170 | [7 empty] | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.29SG) | [5 empty] | MAASP (PSI) | 103.0494
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4559 | 400/400 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4559 | 520/580 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-08-19 | 2019-09-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 60 |  | 4559 | 680/720 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-09-13 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  | 569 |  | MUD LOSSES |  |  |  | 1470 |  | CHORGALI
STRETCHER DRILL | 2019-08-19 | 2019-09-18 | NEXT BOP TEST DATE |  | 2019-09-27 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43731 | 43731.0208 | 0.5 | DRL | PT-P | RIH | CONT'D RIH FROM 4220M TO 4310M.
43731.0208 | 43731.3542 | 8 | DRL | PT-P | RW | PRECAUTIONARY WASHED DOWN FROM 4310M TO 4500M. OBSERVED OBSTRUCTION AT 4500M, ATTEMPTED TO CLEAR WITH RECIPROCATION, NO SUCCESS, REAMED DOWN FROM 4500M TO 4555M. OBSERVED HARD REAMING BELOW 4530M.
43731.3542 | 43731.6875 | 8 | DRL | PT-P | CIR | CIRCULATED TO HOMOGENIZED MUD. MEANWHILE RECIPROCATED STRING. INCREASED FLOW RATE GRADUALLY TO 550 GPM, CHECKED FOR ANY GAIN / LOSS, OK.
43731.6875 | 43731.7292 | 1 | DRL | PT-P | RW | REAMED DOWN FROM 4555M TO 4561.5M.
43731.7292 | 43731.75 | 0.5 | DRL | PT-P | D | PRECAUTIONARY PUMPED 250 BBL LCM PRIOR TAGGING THE BOTTOM AT 4561.5M, DRILLED 12 1/4'' HOLE FROM 4561.5M TO 4561.65M. OBSERVED COMPLETE LOSS.
43731.75 | 43731.7917 | 1 | DRL | NPT-UP | SP | L/UP LCM, PUMPED 150 BBL (100PPB) LCM PILL. OBSERVED NO RETURNS.
43731.7917 | 43731.8542 | 1.5 | DRL | NPT-UP | RW | PUMPED OUT FROM 4561M TO 4406M. OBSERVED NO RETURNS.
43731.8542 | 43731.9271 | 1.75 | DRL | NPT-UP | OTH | PREPARED 120 BBL (170PPB) LCM PILL. MEANWHILE ROTATED STRING.
43731.9271 | 43731.9583 | 0.75 | DRL | NPT-UP | RIH | RIH FROM 4406M TO 4542M. WASHED DOWN LAST SINGLE.
43731.9583 | 43732 | 1 | DRL | NPT-UP | SP | PUMPED 115 BBL (170PPB) LCM PILL FOLLOWED BY MUD, OBSERVED RETURNS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43732 | 43732.0625 | 1.5 | DRL | NPT-UP | DISP | CONT'D DISPLACEMENT LCM PILL, MEANWHILE MONITORED RETURNS.
43732.0625 | 43732.1042 | 1 | DRL | NPT-UP | RW | PUMPED OUT FROM 4542M TO 4246M.
43732.1042 | 43732.1979 | 2.25 | DRL | NPT-UP | FC | ALLOWED SOAKING TIME TO LCM PILL, MEANWHILE OBSERVED WELL ON TRIP TANK. OBSERVED WELL TRICKLING.
43732.1979 | 43732.2188 | 0.5 | DRL | NPT-UP | SHUT | CLOSED ANNULAR BOP TO SHUT-IN THE WELL. RECORDED SIDPP = '0' PSI, SICP = '0' PSI.
43732.2188 | 43732.25 | 0.75 | DRL | NPT-UP | CIR | OPENED BOP, CIRCULATION IN PROGRESS. MEANWHILE MONITORING PIT LEVELS / MUD DENSITY (IN = 2.30 / OUT = 2.26 SP. GR)
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | CIRCULATION IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH TO 4310M, PRECAUTIONARY WASHED DOWN TO 4500M, OBSERVED OBSTRUCTION, REAMED DOWN TO 4561.50M, PUMPED 250 LCM PILL, DRILLED 12 1/4'' HOLE FROM 4561.5M TO 4561.65M, OBSERVED COMPLETE LOSS, PUMPED 150 BBL (100PPB) LCM PILL, PUMPED OUT TO 4406M, PREPARED 120 BBL (170PPB) LCM PILL, RIH TO 4542M, PUMPED LCM PILL, OBSERVED RETURNS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CURE LOSSES, CIRCULATE TO CONDITION/HOMOGENIZE MUD, PUMP OUT OF HOLE.
REMARKS |  |  | TOTAL MUD LOST = 569 BBL
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14