## DDR#145
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 145
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-09-26
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 144.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-09-25 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 24 |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 35
CHECK TIME | 11:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 13 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 2155
DEPTH, MD (M) | 4561 | 4561 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 12.25 |  | MULE SHOE |  |  | 5 | 4.276 |  | 4 1/2 IF |  | 1.68 |  |  | PITS (BBL) | 611
MW IN (SG) | 2.29 | 2.29 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | BAKER |  | X/O |  |  | 7.125 | 3 |  | 5 1/2FH |  | 0.3 |  |  | ACT. SYS (BBL) | 2801
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | VG-09 | [12 empty] | RESV. SYS (BBL) | 827
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 5293867 | [12 empty] | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  | 437 | [12 empty] | KILL MW (SG)
µ FUNNEL (SEC) | 60 | 65 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 X 18'' | [12 empty] | TOTAL | 3628
PV | 48 | 50 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4561.5 | [12 empty] | DIESEL (LTR)
YIELD POINT | 27 | 27 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  | 4561.65 | [12 empty] | RIG TANK | 113394
GEL ST. | 14/27 | 16/29 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 22329
WL (ml/30 min) | 4.6 | 4.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 5451
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 135723
ALK (FILT.) | 0.3/2.0 | 0.3/2.0 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 68000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 110800
KCl (mg/l) | 43854 | 43854 | JAR | 113.64 | STAB - 1 | 113.64 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 108800
CHLORIDES (mg/l) | 24000 | 24000 | 5 1/2" HWDPS | 113.64 | STAB - 2 | 113.64 | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 468000
HARDNESS (mg/l) | 410 | 410 | 9 1/2" DCS |  | STAB - 3 | 113.64 | TFA (IN²) |  |  | 0.7455 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 113.64 | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 1.98 |  |  | MPCL | 5
OIL % | 4 | 4 | DAILY BHA ROT. HRS |  | 12.08 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 18
SOLIDS % | 43.95 | 43.95 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. 13 |  |  | 1-2-FC-A-E-I-NO-HP |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 11.5 | 11.5 | DAILY CIRC. HRS |  | 12.78 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 22
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 103
DAILY WELL COST (US$) |  | 33197 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 10800413 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 54.26% | MUD CLEANER | 3 x 170 | [7 empty] | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.29SG) | [5 empty] | MAASP (PSI) | 103.0494
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4559 | 400/400 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4559 | 520/580 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-08-19 | 2019-09-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 60 |  | 4559 | 680/720 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-09-13 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 1470 |  | CHORGALI
STRETCHER DRILL | 2019-08-19 | 2019-09-18 | NEXT BOP TEST DATE |  | 2019-09-27 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43733 | 43733.25 | 6 | DRL | NPT-UP | RW | CONT'D PUMP OUT OF HOLE FROM 3416M TO 2413M.
43733.25 | 43733.2604 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43733.2604 | 43733.6354 | 9 | DRL | NPT-UP | RW | CONT'D PUMP OUT OF HOLE FROM 2413M TO 996M.
43733.6354 | 43733.6458 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43733.6458 | 43733.8125 | 4 | DRL | NPT-UP | POOH | POOH ON ELEVATOR FROM 996M TO 213M (TOP OF BHA).
43733.8125 | 43733.8229 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43733.8229 | 43733.9271 | 2.5 | DRL | NPT-UP | BHA | POOH FROM 213M TO SURFACE, MEANWHILE L/DOWN D. JAR, STABS AND TC BIT.
43733.9271 | 43734 | 1.75 | DRL | PT-P | RIH | P/UP AND M/UP 5'' MULE SHOE + X/O. RIH ON 5.5'' DP's TO 573M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43734 | 43734.0521 | 1.25 | DRL | NPT-P | RS | SLIPPED AND CUT 32M D. LINE.
43734.0521 | 43734.2292 | 4.25 | DRL | PT-P | RIH | CONT'D RIH FROM 573M TO 2401M.
43734.2292 | 43734.2396 | 0.25 | DRL | PT-P | CIR | BROKE CIRCULATION.
43734.2396 | 43734.25 | 0.25 | DRL | PT-P | RIH | CONT'D RIH FROM 2401M TO 2430M
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | RIH WITH 5'' MULE SHOE FOR CMT PLACEMENT.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D PUMP OUT OF HOLE TO 996M, FLOW CHECKED - WELL STATIC, POOH ON ELEVATOR FROM 996M TO SURFACE, L/DOWN JAR, STABS AND BIT, RIH WITH 5'' MULE SHOE TO 573M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CUT AND SLIP D. LINE, CONTINUE RIH TO BOTTOM AT 4560M, CIRCULATION , PLACE CMT PLUG, POOH.
REMARKS
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14