## DDR#146
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 146
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-09-27
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 145.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-09-26 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 300
CHECK TIME | 11:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1810
DEPTH, MD (M) | 4561 | 4561 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  |  | MULE SHOE |  |  | 5 | 4.276 |  | 4 1/2 IF |  | 1.68 |  |  | PITS (BBL) | 838
MW IN (SG) | 2.29 | 2.29 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  |  | X/O |  |  | 7.125 | 3 |  | 5 1/2FH |  | 0.3 |  |  | ACT. SYS (BBL) | 2948
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE | [15 empty] | RESV. SYS (BBL) | 777
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. | [15 empty] | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE | [15 empty] | KILL MW (SG)
µ FUNNEL (SEC) | 60 | 62 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") | [15 empty] | TOTAL | 3725
PV | 48 | 51 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT | 27 | 23 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 108582
GEL ST. | 14/26 | 15/28 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 21705
WL (ml/30 min) | 4.6 | 4.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 5436
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 130287
ALK (FILT.) | 0.3/2.0 | 0.3/2.0 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 300000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 66000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 155000
KCl (mg/l) | 43854 | 43854 | JAR |  | STAB - 1 | 0 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 53000
CHLORIDES (mg/l) | 24000 | 24000 | 5 1/2" HWDPS |  | STAB - 2 | 0 | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 366000
HARDNESS (mg/l) | 410 | 410 | 9 1/2" DCS |  | STAB - 3 | 0 | TFA (IN²) | [15 empty] | POB
PENETREX % | 2 | 2 | 8" DCS |  | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 1.98 |  |  | MPCL | 5
OIL % | 4 | 4 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 18
SOLIDS % | 43.95 | 43.75 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 11.5 | 11.5 | DAILY CIRC. HRS |  | 7.9 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 57
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 22
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 107
DAILY WELL COST (US$) |  | 40402 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 10840814 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 54.46% | MUD CLEANER | 3 x 170 | [7 empty] | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.29SG) | [5 empty] | MAASP (PSI) | 103.0494
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4559 | 400/400 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4559 | 520/580 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-08-19 | 2019-09-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 60 |  | 4559 | 680/720 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-09-13 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 1470 |  | CHORGALI
STRETCHER DRILL | 2019-08-19 | 2019-09-18 | NEXT BOP TEST DATE |  | 2019-09-27 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43734 | 43734.0521 | 1.25 | DRL | NPT-P | RS | SLIPPED AND CUT 32M D. LINE.
43734.0521 | 43734.5417 | 11.75 | DRL | PT-P | RIH | CONT'D RIH FROM 573M TO 4500M. BROKE CIRCULATION AT 3004M, 3661M, 4234M.
43734.5417 | 43734.5521 | 0.25 | DRL | PT-P | RW | WASHED DOWN FROM 4500M TO 4558M.
43734.5521 | 43734.6979 | 3.5 | DRL | PT-P | RIH | CIRCULATED TO HOMOGENIZED MUD (IN / OUT = 2.29 S.G). MEANWHILE INCREASED FLOW RATE GRADUALLY FROM 350 GPM TO 550 GPM TO CHECK ANY GAIN / LOSS. OK.
43734.6979 | 43734.7292 | 0.75 | DRL | PT-P | RU | HELD PJSM, P/UP AND R/UP DOWEL LINES ALONG WITH CIRCULATING HEAD.
43734.7292 | 43734.7604 | 0.75 | DRL | PT-P | P/T | CLOSED VALVE, P/TESTED SCHL DOWEL LINE AT 500/3000 PSI, HELD FOR 10 MINS, OK.
43734.7604 | 43734.8021 | 1 | DRL | PT-P | CIR | CIRCULATED TO CONDITION MUD MEANWHILE MIXED FLUID TO WEIGHT UP CMT SLURRY.
43734.8021 | 43734.875 | 1.75 | DRL | PT-P | CMT | PERFORMED CMT PLUG JOB AS PER PROGRAM. PUMPED 60 BBL SPACER @ 6 BPM (MUD PUSH II, 20 PPG) FROM DOWEL UNIT FOLLOWED BY 40 BBL BATCH MIXED CMT @ 4-5 BPM (ADDED CEMNET, 20.5 PPG). FOAM BALLS WERE DROPPED BEFORE AND AFTER THE CMT. DISPLACEMENT WAS DONE BY 15 BBL SPACER (MUD PUSH II, 20 PPG) FOLLOWED BY 281 BBL OF MUD @ 6 BPM FROM DOWEL UNIT. NO LOSSES WERE OBSERVED DURING THE JOB.
43734.875 | 43734.9271 | 1.25 | DRL | PT-P | POOH | R/DOWN DOWEL LINES & CIRCULATING HEAD. POOH FROM 4558M TO 4300M. (OBSERVED WET PULL AFTER 4 STDS)
43734.9271 | 43735 | 1.75 | DRL | PT-P | CIR | ESTABLISHED CIRCULATION, PUMPED 20 BBL TRACER PILL (RICE HUSK, BRIDGE FORM) AND CIRCULATED TO CONDITION MUD.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43735 | 43735.0521 | 1.25 | DRL | PT-P | CIR | CONT'D CIRCULATION TO CONDITION MUD.
43735.0521 | 43735.0625 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43735.0625 | 43735.25 | 4.5 | DRL | PT-P | CIR | PUMPED OUT OF HOLE FROM 4300M TO 3585M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | PUMP OUT OF HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | SLIPPED AND CUT D. LINE, RIH WITH 5'' MULE SHOE TO 4500M, WASHED DOWN TO BTM AT 4558M, CIRCULATION TO HOMOGENIZE MUD, R/UP DOWEL UNIT AND PERFORMED CMT PLUG JOB, POOH FROM 4558M TO 4300M, PUMPED TRACER PILL AND CIRCULATION.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CIRCULATION, PUMP OUT OF HOLE TO 2419M (CSG SHOE), POOH ON EVEVATOR TO SURFACE, BOPT, CONDITION TRIP.
REMARKS |  |  | TRACER RECEIVED ON SURFACE AFTER 2000 STKS (170 BBL).
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14