## DDR#147
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 147
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-09-28
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 146.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-09-27 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 11:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 2202
DEPTH, MD (M) | 4561 | 4561 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) | [15 empty] | PITS (BBL) | 662
MW IN (SG) | 2.29 | 2.29 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER | [15 empty] | ACT. SYS (BBL) | 2864
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE | [15 empty] | RESV. SYS (BBL) | 779
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. | [15 empty] | KILL MUD (BBL)
FL TEMP. °F | 154.4 |  | AVG. WOB (TON) |  |  |  | IADC CODE | [15 empty] | KILL MW (SG)
µ FUNNEL (SEC) | 65 | 60 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") | [15 empty] | TOTAL | 3643
PV | 50 | 48 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT | 24 | 24 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 103597
GEL ST. | 15/27 | 14/25 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 21077
WL (ml/30 min) | 4.8 | 4.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 5613
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 124674
ALK (FILT.) | 0.3/2.0 | 0.3/2.0 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 65000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 155800
KCl (mg/l) | 43854 | 43854 | JAR |  | STAB - 1 | 0 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 254800
CHLORIDES (mg/l) | 24000 | 24000 | 5 1/2" HWDPS |  | STAB - 2 | 0 | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 465000
HARDNESS (mg/l) | 410 | 410 | 9 1/2" DCS |  | STAB - 3 | 0 | TFA (IN²) | [15 empty] | POB
PENETREX % | 2 | 2 | 8" DCS |  | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 0 |  |  | MPCL | 5
OIL % | 4 | 4 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 18
SOLIDS % | 43.75 | 43.95 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 11.5 | 11.5 | DAILY CIRC. HRS |  | 6.22 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 54
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 110
DAILY WELL COST (US$) |  | 33163 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 10873977 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 54.63% | MUD CLEANER | 3 x 170 | [7 empty] | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.29SG) | [5 empty] | MAASP (PSI) | 103.0494
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4559 | 400/400 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4559 | 520/580 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-08-19 | 2019-09-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 60 |  | 4559 | 680/720 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-09-28 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 1470 |  | CHORGALI
STRETCHER DRILL | 2019-08-19 | 2019-09-18 | NEXT BOP TEST DATE |  | 2019-10-12 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43735 | 43735.0521 | 1.25 | DRL | PT-P | CIR | CONT'D CIRCULATION TO CONDITION MUD.
43735.0521 | 43735.0625 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43735.0625 | 43735.2812 | 5.25 | DRL | PT-P | POOH | PUMPED OUT OF HOLE FROM 4300 M TO 3437 M.
43735.2812 | 43735.3229 | 1 | DRL | NPT-UP | WOW | STOPPED PUMP OUT DUE TO HEAVY RAIN, TO AVOID DECREASE IN MUD SP.GR & MUD DILUTION. MONITORED WELL ON TRIP TANK. WELL STATIC
43735.3229 | 43735.6146 | 7 | DRL | PT-P | RW | RESUMED PUMP OUT OF HOLE FROM 3437M TO 2382M.
43735.6146 | 43735.625 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43735.625 | 43735.6354 | 0.25 | DRL | NPT-P | RS | SERVICED TDS.
43735.6354 | 43736 | 8.75 | DRL | PT-P | POOH | POOH ON ELEVATOR FROM 2382M TO SURFACE. B/OUT & L/DOWN 5'' MULE SHOE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43736 | 43736.2188 | 5.25 | DRL | PT-P | BOPT | HELD PJSM, M/U COMB TOOL ASSY. RETRIEVED WEAR BUSHING. RIH 2 STDS OF 5 1/2" DP BELOW PLUG & SET TEST PLUG IN 13-5/8" CHS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP, ROTARY HOSE & STAND PIPE MASTER VALVES @ 500/4500 PSI FOR 5/10 MIN - OK. P/TESTED UPPER (VARIABLE 4 1/2"-7") PIPE RAM, LOWER (5 1/2") PIPE RAM, HCR & MANUAL VALVES OF KILL & CHOKE LINE, FOSV, HYD & MANUAL IBOP @ 500/8000 PSI FOR 5/10 MIN - OK. PRESSURE TESTED BLIND/SHEAR RAM AND CO-FLEXIP-MASTER VALVE AT CHOKE MANIFOLD @ 500/8000 PSI FOR 5/10 MIN - OK. RETRIEVED TEST PLUG & R/B 2 x 5 1/2" DP STDS. INSTALLED WEAR BUSHING & L/D COMB TOOL ASSY.
43736.2188 | 43736.25 | 0.75 | DRL | PT-P | BHA | P/UP & M/UP 12 1/4'' USED PDC BIT (NOV, TK-66, SR # E243361, 6 X 16/32'') + N.B STAB + 8'' DC (IN PROGRESS).
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | P/UP & M/UP BHA IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D CIRCULATION TO CONDITION MUD, PUMPED OUT OF HOLE FROM 4300M TO 2382M, FLOW CHECKED - WELL STATIC, POOH ON ELEVATOR FROM 2382M TO SURFACE, L/DOWN MULE SHOE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | BOPT, P/UP AND M/UP USED PDC BIT AND RIH WITH CONDITION BHA TO TAG CMT, DRESS CMT PLUG, CONDITION MUD.
REMARKS
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14