## DDR#149
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 149
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-09-30
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 148.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-09-29 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 25 |  | BHA NO. |  |  | 28 | IN (M) |  | 4561.65 |  | OUT (M) |  |  | STRING (BBL) | 307
CHECK TIME | 11:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 10RR1 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1772
DEPTH, MD (M) | 4561 | 4561 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 12.25 |  | PDC BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.35 | 0.078154 |  | PITS (BBL) | 779
MW IN (SG) | 2.29 | 2.29 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | NOV |  | NB STAB (F.V) |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 1.61 | 0.35951 |  | ACT. SYS (BBL) | 2858
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | TK66 |  | 1 X DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.25 | 2.0655 |  | RESV. SYS (BBL) | 683
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | E243361 |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.45 | 0.54708 |  | KILL MUD (BBL)
FL TEMP. °F | 159.8 | 159.8 | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 2 X DC's |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 18.42 | 4.1132 |  | KILL MW (SG)
µ FUNNEL (SEC) | 48 | 47 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 6 X 16/32'' |  | ST. STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.02 | 0.45106 |  | TOTAL | 3541
PV | 49 | 48 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4561.65 |  | 6 X DC's |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 55.65 | 12.4266 |  | DIESEL (LTR)
YIELD POINT | 22 | 20 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | D. JAR |  |  | 8 | 3.125 |  | 6 5/8 REG |  | 9.6 | 2.1437 |  | RIG TANK | 90260
GEL ST. | 14/26 | 13/24 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | 3 X DC's |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 27.74 | 6.1943 |  | CAMP TANK | 19814
WL (ml/30 min) | 4.6 | 4.3 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | X/O |  |  | 7.8125 | 2.8125 |  | 5 1/2 FH |  | 0.79 | 0.17641 |  | CONSUMED | 9279
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | 9 X HWDP's |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 84.97 | 7.8766 |  | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 110074
ALK (FILT.) | 0.4/2.1 | 0.4/2.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
PH | 9.8 | 9.8 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 65000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 121900
KCl (mg/l) | 43854 | 43854 | JAR | 40.73 | STAB - 1 | 102.9 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 107900
CHLORIDES (mg/l) | 24000 | 24000 | 5 1/2" HWDPS | 102.9 | STAB - 2 | 102.9 | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 465000
HARDNESS (mg/l) | 410 | 410 | 9 1/2" DCS |  | STAB - 3 | 102.9 | TFA (IN²) |  |  | 1.178 | [12 empty] | POB
PENETREX % | 2 | 2 | 8" DCS | 102.9 | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 212.85 |  |  | MPCL | 5
OIL % | 4 | 4 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 18 |  |  | MPCL SERV | 19
SOLIDS % | 44.6 | 44.5 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 13 |  |  | SECURITY
M.B.T. (lb/bbl) | 11.5 | 11.5 | DAILY CIRC. HRS |  | 6.22 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 52
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 22
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 107
DAILY WELL COST (US$) |  | 39515 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 10979235 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 55.16% | MUD CLEANER | 3 x 170 | [7 empty] | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.29SG) | [5 empty] | MAASP (PSI) | 103.0494
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (PI/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4495 | 180/200/200 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4495 | 300/300/300 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-08-19 | 2019-09-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4495 | 400/400/420 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-09-28 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 10 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 1470 |  | CHORGALI
STRETCHER DRILL | 2019-08-19 | 2019-09-18 | NEXT BOP TEST DATE |  | 2019-10-12 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43737 | 43737.0521 | 1.25 | DRL | PT-P | RIH | CONT'D RIH FROM 4102M TO 4305M. OBSERVED OBSTRUCTION AT 4305M.
43737.0521 | 43737.1042 | 1.25 | DRL | PT-P | RW | WASHED DOWN FROM 4305M AND TAGGED TOP OF CMT AT 4497M. (CONFIRMED WITH 10T WOB)
43737.1042 | 43737.2188 | 2.75 | DRL | PT-P | CIR | CIRCULATED FOR BOTTOMS UP. MEANWHILE RECIPROCATED STRING. OBSERVED CMT CHUNKS AT BTMS UP.
43737.2188 | 43737.2396 | 0.5 | DRL | PT-P | RW | RECORDED SCR, REAMED DOWN FROM 4494M TO 4497M.
43737.2396 | 43738 | 18.25 | DRL | PT-P | DC | DRESSED CMT FROM 4497M TO 4547M. OBSERVED HARD CMT BELOW 4522M. OBSERVED FREQUENT ROTARY STALLING WHILE DRESSING CMT.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-09-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43738 | 43738.1562 | 3.75 | DRL | PT-P | DC | CONT'D DRESSING CMT FROM 4547M TO 4550M.
43738.1562 | 43738.25 | 2.25 | DRL | PT-P | CIR | PUMPED CALCIUM CARBIDE FOLLOWED BY 20 BBL (RICE HUSK, BRIGE FORM) AS TRACER PILL. CIRCULATION TO CONDITION MUD IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | CIRCULATION IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH FROM 4102M TO 4305M, WASHED DOWN TO 4497 M AND TAGGED TOC, CIRC FOR BTMS UP, REAMED DOWN FROM 4494M TO 4497M, DRESSED CMT FROM 4497M TO 4522M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE DRESSING CMT FROM 4547M TO 4550M, CIRCULATION TO CONDITION MUD, FLOW CHECK, PUMP OUT OF HOLE FROM 4550M TO 1000M, POOH TO SURFACE.
REMARKS |  |  | HESITANTLY INCREASED FLOW RATE FROM 500 GPM TO 625 GPM AT 4549M FOR 15 MINS, OBSERVED NO GAIN / LOSS.
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14