## DDR#15
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 15
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-19
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / ADNAN |  |  | MD/TVD @ 00:00HRS: |  | 1237 / 1237 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 14.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 1317 / 1317 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 252
2019-05-18 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MOD. LIGNO |  | HOLE SIZE (IN) |  | 17 1/2'' |  | BIT No. |  | 4 |  | BHA No. |  |  | 5 | IN (M) |  | 590 |  | OUT (M) |  |  | STRING (BBL) | 78
CHECK TIME | 12:00 | 23:45 | MD @ 00:00HR (M) |  | 1237 |  | SIZE (IN) |  | 17 1/2'' |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1159.18
DEPTH, MD (M) |  | 1236 | TVD @ 00:00HR (M) |  | 1237 |  | MANUFACTURER |  | NOV |  | 17 1/2'' PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 |  |  | PITS (BBL) | 675
MW IN (SG) | 1.35 | 1.35 | DAILY PROGRESS (M) |  | 252 |  | TYPE |  | TFH519S |  | PD |  |  | 9 | 5.125 |  | 7 5/8 REG |  | 4.29 | 1.3667 |  | ACT. SYS (BBL) | 1912.18
MW OUT (SG) | 1.35 | 1.35 | INST. ROP (M/HR) |  | 19.02 |  | SERIAL NO. |  | E260745 |  | X/O |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.76 | 0.24212 |  | RESV. SYS (BBL) | 710
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 19.78 |  | IADC CODE |  | S422 |  | MUD MOTOR (SLEEVE STAB) |  |  | 9.625 | 7 |  | 6 5/8 REG |  | 10.53 | 3.3546 |  | KILL MUD (BBL) | 500
FL TEMP. °F |  | 138.2 | AVG. WOB (TON) |  | 10 |  | NOZZLES |  | 3X 18, 2 X 16 |  | X/O |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 1.1 | 0.35043 |  | KILL MW (SG) | 1.7
µ FUNNEL (SEC) | 55 | 57 | AVG. RPM SURFACE |  | 74 |  | DEPTH IN (M) |  | 590 |  | FLOAT SUB |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 0.78 | 0.24849 |  | TOTAL | 2622.18
PV | 28 | 28 | AVG. RPM DOWNHOLE |  | 175 |  | DEPTH OUT (M) |  |  |  | ST. STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.44 | 0.77732 |  | DIESEL (LTR)
YIELD POINT | 30 | 27 | FLOWRATE (GPM) |  | 920 |  | METERAGE (M) |  | 647 |  | LOWER S. SUB |  |  | 9.625 | 3.5 |  | 7 5/8 REG |  | 0.78 | 0.24849 |  | RIG TANK | 120279
GEL ST. | 7/9 | 7/11 | PRESSURE (PSI) |  | 2372 |  | RPM SURF. |  | 75 |  | SLIM PULSE |  |  | 9.5625 | 5 |  | 7 5/8 REG |  | 9.27 | 2.9532 |  | CAMP TANK | 21705
WL (ml/30 min.) | 4.6 | 4.5 | TORQ. ON-BTM (KLB-FT) |  | 8-14 |  | RPM BTM. |  | 175 |  | UPPER S. SUB |  |  | 9.5625 | 3 |  | 7 5/8 REG |  | 0.67 | 0.21344 |  | CONSUMED | 9473
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | WOB (TON) |  | 6 -14 |  | ST. STAB |  |  | 17.375 | 2.9375 |  | 7 5/8 REG |  | 2.37 | 0.75502 |  | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 104 |  | AVG. ROP (M/HR) |  | 19.2331 |  | NMDC |  |  | 9 | 3.5 |  | 7 5/8 REG |  | 9.36 | 2.9818 |  | TOTAL | 141984
ALK (FILT.) | 0.3 | 0.4 | PICK-UP WT. (TON) |  | 105 |  | BIT ROT HRS. |  | 33.64 |  | 3 X 9 1/2'' DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 27.53 | 8.7703 |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 100 |  | K-REVS IN 24 HRS |  | 135.8 |  | X/O |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.93 | 0.29627 |  | RIG STORAGE | 490000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 346.01 |  | 2 X 8'' DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.34 | 4.0953 |  | CAMP STORAGE | 80000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 25.7 |  | D. JAR |  |  | 7.9375 | 3.0625 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | CONSUMED | 158100
KCl (mg/l) | 50527.6 | 53959.6 | JAR | 56.79 | NMDC | 46.78 | JET VELOCITY (M/SEC) |  | 77.19 |  | 2 X 8'' DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.43 | 4.1154 |  | RECEIVED | 173100
CHLORIDES (mg/l) | 25000 | 25500 | MOTOR | 46.78 | STAB - 1 | 46.78 | TFA (IN²) |  | 1.138 |  | X/O |  |  | 7.3125 | 2.8125 |  | 5 1/2 FH |  | 0.81 | 0.18087 |  | TOTAL
HARDNESS (mg/l) | 300 | 300 | 9 1/2" DCS | 56.79 | STAB - 2 | 46.78 | HSI |  | 1.405 |  | 10 X 5 1/2'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 94.38 | 3.4703 |  | POB
SAND % |  | 0.5 | 8" DCS | 56.79 | SPSA | 46.78 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 212.69 |  |  | MPCL | 5
LUBRICANT % | 1 | 1 | BHA ROT. HRS |  | 46.78 |  | BIT No. 4 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 33 |  |  | MPCL SERV | 23
SOLIDS % | 11.7 | 11.67 | ON BOTTOM HRS |  | 12.98 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 23 |  |  | SECURITY | 2
M.B.T. (lb/bbl) | 8 | 7.5 | CIRC. HRS |  | 17.76 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 54
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 100 | 2 X 100 |  | 30" CONDUCTOR |  |  | 37 | 1180/1180 |  | 0.1 | [6 empty] | MWD |  | TOTAL | 114
DAILY WELL COST (US$) |  | 86490 | SHAKER-2 | 1 X 100 | 2 X 100 |  | 20'' SURFACE/ K-55, 133# |  |  | 579 | 1209/1209 |  | 0.08 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 2060459 | SHAKER-3 | 1 X 100 | 2 X 100 | [5 empty] | 1238/1238 |  | 0.17 | [6 empty] | MWD |  | LAST CSG SIZE | 20''
% OF AFE SPENT |  | 10.35% | MUD CLEANER | 3 X 140 | [6 empty] | 1266/1266 |  | 0.08 | [6 empty] | MWD |  | LOT (EMW) | 1.95
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 494
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 30 |  | 1272 |  | 225/225 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 40 |  | 1272 |  | 275/275 |  | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 50 |  | 1272 |  | 350/350 |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-05-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 20 | BRINE LOSSES IN 24 HRS |  |  |  |  | BRINE LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2019-05-28 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 20 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-18
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43603 | 43603.0521 | 1.25 | DRL | PT-P | CIR | SWEPT OUT 30 BBL HI-VIS BRIDGE PILL, KEPT CIRCULATING TILL SHAKERS CLEAN.
43603.0521 | 43603.0625 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43603.0625 | 43603.2292 | 4 | DRL | PT-P | WT | PERFORMED WIPER TRIP; POOH FROM 985M TO 566M (INSIDE CSG). RIH BACK TO BOTTOM AT 985M. HOLE CONDITION, GOOD. PRECAUTIONARY WASHED DOWN LAST STAND.
43603.2292 | 43603.3646 | 3.25 | DRL | PT-P | DM | CONT'D DRILLING 17 1/2'' HOLE FROM 985M TO 1042M. REAMED / WASHED DRILLED INTERVAL & RECORDED MWD SURVEY AT CONNECTION.
43603.3646 | 43603.3854 | 0.5 | DRL | PT-P | RS | SERVICED TDS.
43603.3854 | 43604 | 14.75 | DRL | PT-P | DM | CONT'D DRILLING 17 1/2'' HOLE FROM 1042M TO 1237M. REAMED / WASHED DRILLED INTERVAL & RECORDED MWD SURVEY AT CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43604 | 43604.25 | 6 | DRL | PT-P | DM | CONT'D DRILLING 17 1/2'' HOLE FROM 1237M TO 1317M. REAMED / WASHED DRILLED INTERVAL & RECORDED MWD SURVEY AT CONNECTION.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KAMLIAL / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | DRILLING 17 1/2'' HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | SWEPT OUT 30 BBL HI-VIS BRIDGE PILL & CIRCULATED TO CLEAN HOLE, PERFORMED WIPER TRIP TO 20'' CSG SHOE, HOLE CONDITION, GOOD. RIH BACK TO BTM AND RESUME DRILLING, DRILLED DOWN TO 1237M .
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 17 1/2'' HOLE TO 1385M, PERFORM WIPER TRIP, RIH TO BTM AND RESUME DRILLING.
REMARKS |  |  | PUMPED 20 BBL HI-VIS BRIDGE PILL AT EVERY STAND DOWN.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14