## DDR#155
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 155
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-10-06
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 154.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-10-05 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 11:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 2202
DEPTH, MD (M) | 4561 | 4561 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) | [15 empty] | PITS (BBL) | 650
MW IN (SG) | 2.29 | 2.29 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER | [15 empty] | ACT. SYS (BBL) | 2852
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE | [15 empty] | RESV. SYS (BBL) | 576
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. | [15 empty] | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE | [15 empty] | KILL MW (SG)
µ FUNNEL (SEC) | 55 | 60 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") | [15 empty] | TOTAL | 3428
PV | 41 | 42 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT | 16 | 18 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 106109
GEL ST. | 8/20 | 12/23 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 15929
WL (ml/30 min) | 4.3 | 4.3 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 7452
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 122038
ALK (FILT.) | 0.4/2.1 | 0.4/2.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
PH | 9.8 | 9.8 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 440000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 85000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 135000
KCl (mg/l) | 42900 | 42900 | JAR |  | STAB - 1 | 0 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 142700
CHLORIDES (mg/l) | 23500 | 23500 | 5 1/2" HWDPS |  | STAB - 2 | 0 | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 525000
HARDNESS (mg/l) | 410 | 410 | 9 1/2" DCS |  | STAB - 3 | 0 | TFA (IN²) | [15 empty] | POB
PENETREX % | 2 | 2 | 8" DCS |  | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 0 |  |  | MPCL | 5
OIL % | 3.5 | 3.5 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 31
SOLIDS % | 43.76 | 43.76 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 11.5 | 11.5 | DAILY CIRC. HRS | [8 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 127
DAILY WELL COST (US$) |  | 1191581 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 12353065 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 13 3/8" X 13 5/8"
% OF AFE SPENT |  | 62.06% | MUD CLEANER | 3 x 170 | [7 empty] | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | LOT (EMW) | 2.32
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (2.29SG) | [5 empty] | MAASP (PSI) | 103.0494
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (PI/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4495 | 180/200/200 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4495 | 300/300/300 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-08-19 | 2019-09-18 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4495 | 400/400/420 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-09-28 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 1470 |  | CHORGALI
STRETCHER DRILL | 2019-08-19 | 2019-09-18 | NEXT BOP TEST DATE |  | 2019-10-12 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-05
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43743 | 43743.1562 | 3.75 | DRL | PT-P | CIR | CONT'D CIRCULATION MEANWHILE SCHL DOWEL MIXED FLUID FOR CMT JOB.
43743.1562 | 43743.2188 | 1.5 | DRL | PT-P | RU | HELD PJSM, P/UP PRE-LOADED DOWEL CMT HEAD, CMT LINES. CONNECTED WITH RIG PUMPS AND DOWEL UNIT.
43743.2188 | 43743.2396 | 0.5 | DRL | PT-P | P/T | FLUSHED CMT LINES WITH FRESH WATER. CLOSED VALVE, P/TESTED DOWEL CMT LINES AT 500/5000 PSI. HELD FOR 5/10 MINS OK.
43743.2396 | 43743.3542 | 2.75 | DRL | PT-P | CIR | SWITCHED OVER TO RIG PUMPS, CIRCULATING TO CONDITION MUD MEANWHILE ADDING RETARDER TO MIX FLUID IN PROGRESS.
43743.3542 | 43743.6771 | 7.75 | DRL | PT-P | CMC | PERFORMED 9 5/8'' CSG CEMENT JOB AS FOLLOW: PUMPED 150 BBL (MUD PUSH II, 20PPG) SPACER FROM RIG PUMP, DROPPED BTM PLUG, SWITCHED OVER TO DOWEL CMT UNIT. PUMPED 362 BBL (FLY MIXED, 20.5 PPG) LEAD-A SLURRY @ 4-5 BPM FOLLOWED BY 385 BBL (FLY MIXED, 20.5 PPG) LEAD-B @ 4-5 BPM SLURRY. TAIL SLURRY OF 140 BBL (BATCH MIXED, 20.5 PPG) WAS PUMPED @ 4-5 BPM IN THE END. TOP PLUG WAS DROPPED PRIOR DISPLACEMENT. DISPLACEMENT: SWITCHED OVER TO RIG PUMPS, PUMPED 20 BBL SPACER (MUD PUSH II, 20 PPG) FOLLOWED BY 1022 BBL MUD (2.29 SG) @ 10 BPM. FINAL DISPLACEMENT VOLUME (13 BBL) WERE PUMPED FROM DOWEL UNIT @ 2 BPM. OBSERVED PLUGS BUMPED AFTER DISPLACING 1055 BBL, INCREASED PRESSURE GRADUALLY FROM 800 PSI TO 1300 PSI. HELD FOR 5 MINS, OK. GRADUALLY INCREASED PRESSURE FROM 1300 PSI TO 3000 PSI TO INFLATE ACP PACKING ELEMENT. PRESSURE WAS FURTHER INCREASED TO 4000 PSI FOR GREEN CMT TEST, OK. CHECKED FOR BACK FLOW, NO BACK FLOW. FLOATS HOLDING. JOB CONCLUDED SUCCESSFULLY. NO LOSSES WERE OBSERVED DURING THE JOB / SPACER CONTAMINATION SURFACED AFTER DISPLACING 930 BBL MUD.
43743.6771 | 43743.8021 | 3 | DRL | PT-P | WOC / NDB | MADE ARRANGEMENTS TO LIFT BOP, DISCONNECTED FLOW LINE, LIFTED BOP STACK.
43743.8021 | 43743.8438 | 1 | DRL | PT-P | WOC / WH | CENTRED 9.625'' CSG AND SET SLIP AND SEAL ASSY IN CASING HEAD SPOOL. SLACKED OFF CSG WEIGHT ON SLIP AND SEAL ASSEMBLY.
43743.8438 | 43743.9688 | 3 | DRL | PT-P | WOC / CC | ROUGH CUT 9.625'' CSG & N/D BOP. MEANWHILE R/D DOWEL CMT HEAD, SPIDER ELEVATOR, L/D LANDING JOINT + CUT JOINT.
43743.9688 | 43744 | 0.75 | DRL | PT-P | WOC / CC | FINAL CUT 9.625'' CSG IN PROGRESS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-06
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43744 | 43744.1458 | 3.5 | DRL | PT-P | WOC / CC | CONT'D FINAL CUT 9.625'' CSG AT 6.5'' WITH WF COLD CUTTER. BEVELLED AND DRESSED SAME.
43744.1458 | 43744.25 | 2.5 | DRL | PT-P | WOC / WH | INSTALLED 13 5/8" - 10K BTM X 11" - 10K TOP TUBING HEAD SPOOL (THS) & TIGHTENED STUD BOLTS (IN PROGRESS).
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | WOC MEANWHILE N/U WH IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATED TO CONDITION MUD, PERFORMED CMT JOB AS PER PLAN, N/D BOP, ROUGH CUT CSG, SET SLIP AND SEAL ASSEMBLY. FINAL CUT CSG IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | FINAL CUT 9.625'' CSG, NU WH, P/TEST WH, NU BOP, P/TEST BOP, WOC MEANWHILE PREPARE FOR NEXT HOLE SECTION.
REMARKS |  |  | RELEASED WF TRS, ACP ENGR.
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14