## DDR#159
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 159
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-10-10
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 158.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-10-09 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 26 |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 100
CHECK TIME |  | 23:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 14RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 897.9
DEPTH, MD (M) |  | 4561 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 8.5 |  | PDC BIT |  |  | 8.5" |  |  | 4-1/2 Reg |  | 0.26 |  |  | PITS (BBL) | 685
MW IN (SG) |  | 2.29 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | BIT SUB |  |  | 6-1/2" | 2-7/16" |  | 4-1/2 Reg |  | 1.07 |  |  | ACT. SYS (BBL) | 1682.9
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDSi616 |  | 1 X 6.5" DC |  |  | 6-1/2" | 2.75 |  | 4-1/2 IF |  | 9.24 |  |  | RESV. SYS (BBL) | 750
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | JN5340 |  | S.STAB |  |  | 8-3/8" | 2.9375 |  | 4-1/2 IF |  | 1.88 |  |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 14 X 6.5" DC |  |  | 6-1/2" | 2.75 |  | 4-1/2 IF |  | 129.62 |  |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 60 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3X18 + 3X16 |  | HYD-MECH. JAR |  |  | 6-1/2" | 2.75 |  | 4-1/2 IF |  | 9.94 |  |  | TOTAL | 2432.9
PV |  | 42 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | 3 X 6.5" DC |  |  | 6-1/2" | 2.75 |  | 4-1/2 IF |  | 27.78 |  |  | DIESEL (LTR)
YIELD POINT |  | 23 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | 15 X 5" HWDPS |  |  | 6-3/8" | 3 |  | 4-1/2 IF |  | 139.52 |  |  | RIG TANK | 137597
GEL ST. |  | 12/16 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 13732
WL (ml/30 min) |  | 4.3 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 4858
CT ( in/32) |  | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED | 47867
ALK (MUD) |  | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 151329
ALK (FILT.) |  | 0.4/2.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
PH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 80000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 141600
KCl (mg/l) |  | 43854 | JAR |  | STAB - 1 | 0 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 131600
CHLORIDES (mg/l) |  | 24000 | 5 1/2" HWDPS |  | STAB - 2 | 0 | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 530000
HARDNESS (mg/l) |  | 400 | 9 1/2" DCS |  | STAB - 3 | 0 | TFA (IN²) |  |  | 1.33 | [12 empty] | POB
PENETREX % |  | 2 | 8" DCS |  | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 319.31 |  |  | MPCL | 5
OIL % |  | 3 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 20 |  |  | MPCL SERV | 16
SOLIDS % |  | 43.74 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 13 |  |  | SECURITY
M.B.T. (lb/bbl) |  | 11.3 | DAILY CIRC. HRS | [8 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 105
DAILY WELL COST (US$) |  | 30861 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 12751476 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE
% OF AFE SPENT |  | 64.06% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (PI/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 5000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-10-08 | 2019-11-07 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-10-07 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-10-08 | 2019-11-07 | NEXT BOP TEST DATE |  | 2019-10-21 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-09
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43747 | 43747.2917 | 7 | DRL | PT-P | DP | RIH 5.5'' RIG DP's & L/DOWN SAME SGL BY SGL FROM CATWALK.
43747.2917 | 43747.4688 | 4.25 | DRL | PT-P | BHA | P/UP & M/UP 8 1/2'' USED PDC BIT (SMITH, MDSi616, SR# JN5340, 3 X 16 + 3 X 18) + BIT SUB. P/UP, M/UP BHA COMPONENTS SGL BY SGL, RIH AS PER BHA DOWN TO 319M. DRIFTED EACH JT.
43747.4688 | 43747.4896 | 0.5 | DRL | PT-P | CIR | CIRCULATED @ 290 GPM TO FLUSH BHA.
43747.4896 | 43748 | 12.25 | DRL | PT-P | DP / RIH | CONT'D P/UP AND M/UP NEW 5'' DP'S (G-105) SGL BY SGL FROM CATWALK. RIH FROM 319M TO 1888M, DRIFTED EACH JOINT. FILLED UP & CIRCULATED AFTER RIH EVERY 50 JT's @ 180-200 GPM.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43747 | 43747.25 | 6 | DRL | PT-P | DP / RIH | CONT'D P/UP AND M/UP NEW 5'' DP'S (G-105) SGL BY SGL FROM CATWALK. RIH FROM 1888M TO 2709M. DRIFTED EACH JOINT WHILE P/UP. FILLED UP & CIRCULATED AFTER RIH EVERY 50 JT's AT 180-200 GPM.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | P/UP, M/UP & RIH NEW 5'' DP's FROM CATWALK IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D L/DOWN RIG 5.5'' DP's SGL BY SGL FROM CATWALK, P/UP AND M/UP 8 1/2'' USED PDC & BIT SUB, P/UP, M/UP & RIH AS PER BHA TO 319M, FLUSHED SAME, RIH FROM 319M TO 1888M, MEANWHILE P/UP AND M/UP NEW 5'' DP's SGL BY SGL FROM CATWALK.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE P/UP AND M/UP NEW 5'' DP's AND RIH TO TAG TOC/PLUGS AT +/- 4509M, DRILL OUT PLUGS, F.COLLAR & CMT TO +/- 4545M.
REMARKS |  |  | PREPARED 1000 BBL NEW MUD FOR UPCOMING SECTION / MANAGER DRILLING & MANAGER EXPLORATION VISITED WELL-SITE.
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14