## DDR#16
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 16
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-20
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / ADNAN |  |  | MD/TVD @ 00:00HRS: |  | 1386 / 1386 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 15.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 1386 / 1386 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 149
2019-05-19 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MOD. LIGNO |  | HOLE SIZE (IN) |  | 17 1/2'' |  | BIT No. |  | 4 |  | BHA No. |  |  | 5 | IN (M) |  | 590 |  | OUT (M) |  |  | STRING (BBL) | 88
CHECK TIME | 12:00 | 23:45 | MD @ 00:00HR (M) |  | 1386 |  | SIZE (IN) |  | 17 1/2'' |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1288
DEPTH, MD (M) | 1386 | 1386 | TVD @ 00:00HR (M) |  | 1386 |  | MANUFACTURER |  | NOV |  | 17 1/2'' PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 |  |  | PITS (BBL) | 648
MW IN (SG) | 1.35 | 1.35 | DAILY PROGRESS (M) |  | 149 |  | TYPE |  | TFH519S |  | PD |  |  | 9 | 5.125 |  | 7 5/8 REG |  | 4.29 | 1.3667 |  | ACT. SYS (BBL) | 2024
MW OUT (SG) | 1.35 | 1.35 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E260745 |  | X/O |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.76 | 0.24212 |  | RESV. SYS (BBL) | 890
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 19.78 |  | IADC CODE |  | S422 |  | MUD MOTOR (SLEEVE STAB) |  |  | 9.625 | 7 |  | 6 5/8 REG |  | 10.53 | 3.3546 |  | KILL MUD (BBL) | 500
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 11 |  | NOZZLES |  | 3X 18, 2 X 16 |  | X/O |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 1.1 | 0.35043 |  | KILL MW (SG) | 1.8
µ FUNNEL (SEC) | 59 | 56 | AVG. RPM SURFACE |  | 80 |  | DEPTH IN (M) |  | 590 |  | FLOAT SUB |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 0.78 | 0.24849 |  | TOTAL | 2914
PV | 26 | 26 | AVG. RPM DOWNHOLE |  | 180 |  | DEPTH OUT (M) |  |  |  | ST. STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.44 | 0.77732 |  | DIESEL (LTR)
YIELD POINT | 30 | 28 | FLOWRATE (GPM) |  | 920 |  | METERAGE (M) |  | 796 |  | LOWER S. SUB |  |  | 9.625 | 3.5 |  | 7 5/8 REG |  | 0.78 | 0.24849 |  | RIG TANK | 110739
GEL ST. | 8/10 | 8/10 | PRESSURE (PSI) |  | 2500 |  | RPM SURF. |  | 80 |  | SLIM PULSE |  |  | 9.5625 | 5 |  | 7 5/8 REG |  | 9.27 | 2.9532 |  | CAMP TANK | 21077
WL (ml/30 min.) | 5 | 5.2 | TORQ. ON-BTM (KLB-FT) |  | 8-14 |  | RPM BTM. |  | 180 |  | UPPER S. SUB |  |  | 9.5625 | 3 |  | 7 5/8 REG |  | 0.67 | 0.21344 |  | CONSUMED | 10168
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | WOB (TON) |  | 6 -15 |  | ST. STAB |  |  | 17.375 | 2.9375 |  | 7 5/8 REG |  | 2.37 | 0.75502 |  | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 112 |  | AVG. ROP (M/HR) |  | 19.1576 |  | NMDC |  |  | 9 | 3.5 |  | 7 5/8 REG |  | 9.36 | 2.9818 |  | TOTAL | 131816
ALK (FILT.) | 0.2 | 0.3 | PICK-UP WT. (TON) |  | 113 |  | BIT ROT HRS. |  | 41.55 |  | 3 X 9 1/2'' DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 27.53 | 8.7703 |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 111 |  | K-REVS IN 24 HRS |  | 85.74 |  | X/O |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.93 | 0.29627 |  | RIG STORAGE | 500000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 431.75 |  | 2 X 8'' DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.34 | 4.0953 |  | CAMP STORAGE | 90000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 25.7 |  | D. JAR |  |  | 7.9375 | 3.0625 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | CONSUMED | 250800
KCl (mg/l) | 43854.1 | 47667.5 | JAR | 66.27 | NMDC | 56.26 | JET VELOCITY (M/SEC) |  | 77.19 |  | 2 X 8'' DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.43 | 4.1154 |  | RECEIVED | 270800
CHLORIDES (mg/l) | 25000 | 25500 | MOTOR | 56.26 | STAB - 1 | 56.26 | TFA (IN²) |  | 1.138 |  | X/O |  |  | 7.3125 | 2.8125 |  | 5 1/2 FH |  | 0.81 | 0.18087 |  | TOTAL
HARDNESS (mg/l) | 400 | 300 | 9 1/2" DCS | 66.27 | STAB - 2 | 56.26 | HSI |  | 1.405 |  | 10 X 5 1/2'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 94.38 | 3.4703 |  | POB
SAND % |  | 0.5 | 8" DCS | 66.27 | SPSA | 56.26 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 212.69 |  |  | MPCL | 5
LUBRICANT % | 0.5 | 1 | BHA ROT. HRS |  | 56.26 |  | BIT No. 4 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 33 |  |  | MPCL SERV | 25
SOLIDS % | 11.9 | 11.86 | ON BOTTOM HRS |  | 7.91 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 23 |  |  | SECURITY | 2
M.B.T. (lb/bbl) | 7.5 | 7.5 | CIRC. HRS |  | 17.15 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 54
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 7
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 100 | 2 X 100 |  | 30" CONDUCTOR |  |  | 37 | 1266/1266 |  | 0.08 | [6 empty] | MWD |  | TOTAL | 118
DAILY WELL COST (US$) |  | 76866 | SHAKER-2 | 1 X 100 | 2 X 100 |  | 20'' SURFACE/ K-55, 133# |  |  | 579 | 1295/1295 |  | 0.15 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 2137325 | SHAKER-3 | 1 X 100 | 2 X 100 | [5 empty] | 1324/1324 |  | 0.1 | [6 empty] | MWD |  | LAST CSG SIZE | 20''
% OF AFE SPENT |  | 10.74% | MUD CLEANER | 3 X 140 | [6 empty] | 1351/1351 |  | 0.07 | [6 empty] | MWD |  | LOT (EMW) | 1.95
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 494
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PRESS.PSI |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 30 |  | 1385 | 250 / 250 / 250 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 40 |  | 1385 | 300 / 300 / 300 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 50 |  | 1385 | 380 / 380 / 380 |  |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-05-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 19 | BRINE LOSSES IN 24 HRS |  |  |  |  | BRINE LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2019-05-28 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 19 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43604 | 43604.375 | 9 | DRL | PT-P | DM | CONT'D DRILLING 17 1/2'' HOLE FROM 1237M TO 1357M. REAMED / WASHED DRILLED INTERVAL & RECORDED MWD SURVEY PRIOR TO CONNECTION.
43604.375 | 43604.3854 | 0.25 | DRL | PT-P | RS | SERVICED TDS.
43604.3854 | 43604.4583 | 1.75 | DRL | PT-P | DM | CONT'D DRILLING 17 1/2'' HOLE FROM 1357M TO 1386M. REAMED / WASHED DRILLED INTERVAL & RECORDED MWD SURVEY PRIOR TO CONNECTION.
43604.4583 | 43604.5208 | 1.5 | DRL | PT-P | CIR | SWEPT OUT 30 BBL BRIDGING/HV PILL & CIRCULATED TILL SHAKERS CLEAN PRIOR TO WIPER TRIP.
43604.5208 | 43604.5312 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43604.5312 | 43604.6875 | 3.75 | DRL | PT-P | WT | POOH FROM 1386M TO 955M, RIH FROM 955M TO 1358M. FOUND HOLE CONDITION, GOOD.
43604.6875 | 43604.75 | 1.5 | DRL | NPT-UP | RW | WHILE WASHING DOWN LAST STD FROM 1358M TO 1386M, OBSERVED TDS PIPE HANDLER JAMMED, IBOP CLOSED. PUMP'S POP OFF VALVE ACTIVATED. ATTEMPTED TO ROTATE/UNLOCK PIPE HANDLER , NO SUCCESS.
43604.75 | 43604.7917 | 1 | DRL | NPT-UP | RR | P/UP OFF BTM, POOH FROM 1386M TO 1366M (L/DOWN 2X 5 1/2'' DP JTS.)
43604.7917 | 43604.9271 | 3.25 | DRL | NPT-UP | RR | WORKED ON PIPE HANDLER , ATTEMPTED TO RECTIFY PROBLEM, DISCONNECTED HYDRAULIC SYSTEM OF PIPE HANDLER; CHANGED SOLENOID VALVE OF PIPE HANDLER LOCKING PIN. NO SUCCESS. CIRCULATED,RECIPROCATED & ROTATED STRING INTERMITTENTLY DURING WORK ON PIPE HANDLER. DECIDED TO POOH TO CASING SHOE & RECTIFY THE PIPE HANDLER PROBLEM.
43604.9271 | 43605 | 1.75 | DRL | NPT-UP | POOH | POOH FROM 1366M TO 1110M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-20
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43605 | 43605.1042 | 2.5 | DRL | NPT-UP | POOH | CONT'D POOH FROM 1110M TO 566M (INSIDE 20'' CSG).
43605.1042 | 43605.1667 | 1.5 | DRL | NPT-UP | RR | WORKED ON TDS (PIPE HANDLER) &CHANGED PRESSURE REDUCER VALVE OF PIPE HANDLER. ISSUE RESOLVED, FUNCTION TESTED PIPE HANDLER, OK.
43605.1667 | 43605.25 | 2 | DRL | NPT-UP | RIH | RIH FROM 566M TO 1300M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KAMLIAL / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | RIH IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 17 1/2'' HOLE DOWN TO 1386M, SWEPT OUT 30 BBL HI-VIS BRIDGE PILL & CIRCULATED TO CLEAN HOLE, FLOW CHECKED- WELL STATIC, PERFORMED WIPER TRIP TO 985M, RIH TO 1358M, WASHED DOWN FROM 1358M TO 1386 M, OBSERVED PROBLEM WITH TDS PIPE HANDLER, ATTEMPTED TO RESOLVE PROBLEM , NO SUCCESS, P/BACK TO 1366M, WORKED ON TDS PIPE HANDLER MEANWHILE CIRCULATED AND RECIPROCATED STRING. DECIDED TO POOH INSIDE CSG. POOH FROM 1366M TO 1110M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE POOH INSIDE 20'' CSG, RESOLVE TDS PROBLEM, RIH TO BTM AT 1386M, RESUME DRILLING, DRILL AHEAD 17 1/2'' HOLE.
REMARKS |  |  | PUMPED 20 BBL HI-VIS BRIDGE PILL AT EVERY STAND DOWN.( REPAIR WORK ON PIPE HANDLER WAS HINDERED BY HEAVY WIND STORM)
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14