## DDR#160
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 160
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-10-11
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / ADNAN / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 159.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-10-10 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 26 |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 252.6
CHECK TIME |  | 22:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 14RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 689.4
DEPTH, MD (M) |  | 4561 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 8.5 |  | PDC BIT |  |  | 8.5 |  |  | 4-1/2 REG |  | 0.26 |  |  | PITS (BBL) | 683
MW IN (SG) |  | 2.29 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | BIT SUB |  |  | 6.5 | 2.4375 |  | 4-1/2 REG |  | 1.07 |  |  | ACT. SYS (BBL) | 1625
MW OUT (SG) |  | 2.29 | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDSi616 |  | 1 x 6 1/2" DC |  |  | 6.5 | 2.75 |  | 4-1/2 IF |  | 9.24 |  |  | RESV. SYS (BBL) | 776
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | JN5340 |  | ST. STAB |  |  | 8.375 | 2.9375 |  | 4-1/2 IF |  | 1.88 |  |  | KILL MUD (BBL)
FL TEMP. °F |  | 125.6 | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 14 x 6 1/2" DC |  |  | 6.5 | 2.75 |  | 4-1/2 IF |  | 129.62 |  |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 64 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3x18 + 3x16 |  | HYD-MECH. JAR |  |  | 6.5 | 2.75 |  | 4-1/2 IF |  | 9.94 |  |  | TOTAL | 2401
PV |  | 43 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | 3 x 6 1/2" DC |  |  | 6.5 | 2.75 |  | 4-1/2 IF |  | 27.78 |  |  | DIESEL (LTR)
YIELD POINT |  | 24 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | 15 x 5" HWDP |  |  | 6.375 | 3 |  | 4-1/2 IF |  | 139.52 |  |  | RIG TANK | 132489
GEL ST. |  | 13/19 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 13190
WL (ml/30 min) |  | 5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 5650
CT ( in/32) |  | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) |  | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 145679
ALK (FILT.) |  | 0.4/2 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
PH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 76000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 174500
KCl (mg/l) |  | 43854 | JAR | 4.25 | STAB - 1 | 4.25 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 170500
CHLORIDES (mg/l) |  | 23000 | 5" HWDPS | 4.25 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 526000
HARDNESS (mg/l) |  | 400 | 6 1/2" DCS | 4.25 | STAB - 3 |  | TFA (IN²) |  |  | 1.33 | [12 empty] | POB
PENETREX % |  | 1 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 319.31 |  |  | MPCL | 5
OIL % |  | 3 | DAILY BHA ROT. HRS |  | 4.25 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 20 |  |  | MPCL SERV | 15
SOLIDS % |  | 43.77 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 13 |  |  | SECURITY
M.B.T. (lb/bbl) |  | 11.3 | DAILY CIRC. HRS |  | 8.25 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 22
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 103
DAILY WELL COST (US$) |  | 88417.65 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 12839893.5429 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE
% OF AFE SPENT |  | 64.5% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (PI/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-10-08 | 2019-11-07 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-10-07 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-10-08 | 2019-11-07 | NEXT BOP TEST DATE |  | 2019-10-21 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43748 | 43748.3646 | 8.75 | DRL | PT-P | DP / RIH | CONT'D P/UP AND M/UP NEW 5" DP'S (G-105) SGL BY SGL FROM CATWALK. RIH FROM 1888M TO 3057M (TOTAL 285 JOINTS OF G-105). DRIFTED EACH JOINT WHILE P/UP. FILLED UP STRING AFTER EVERY 50 JT's & CIRCULATED @ 200 GPM FOR 10 MINUTES.
43748.3646 | 43748.3958 | 0.75 | DRL | PTP | CIR | CIRCULATED @450 GPM FOR BOTTOMS UP.
43748.3958 | 43748.7188 | 7.75 | DRL | PT-P | DP / RIH | CONT'D P/UP AND M/UP 5" DP'S (S-135) SGL BY SGL FROM CATWALK. RIH FROM 3057M TO 4488M. DRIFTED EACH JOINT WHILE P/UP. FILLED UP STRING AFTER EVERY 50 JT's & CIRCULATED @ 200 GPM FOR 10 MINUTES.
43748.7188 | 43748.7604 | 1 | DRL | PT-P | RW | WASHED DOWN AND TAGGED CEMENT/PLUGS AT 4509.5M & CIRCULATED.
43748.7604 | 43748.9375 | 4.25 | DRL | PT-P | DC | DRILLED TOP/BOTTOM PLUGS, F/COLLAR & SHOE TRACK CEMENT DOWN TO 4545M.
43748.9375 | 43749 | 1.5 | DRL | PT-P | CIR | CIRCULATED TILL SHAKERS CLEAN. PUMPED SLUG PRIOR POOH.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-11
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43749 | 43749.25 | 6 | DRL | PT-P | POOH | POOH FROM 4545M TO 1844M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | POOH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D P/UP AND M/UP NEW 5" DP's & RIH TO TAG TOC/PLUGS AT 4509.5M. DRILLED OUT PLUGS, F/COLLAR & CMT DOWN TO 4545M. CIRCULATED PRIOR POOH.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. RIH WITH 9 5/8" CSG SCRAPPER PRIOR CBL-VDL.
REMARKS
Formulas:
MIRAJ-1 = [KCL MODIFIED LIGNO.]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14