## DDR#162
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 161.9792
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-10-13
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 161.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4561.65 M | 4561.65 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-10-12 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 28 |  | BHA NO. |  |  | 31 | IN (M) |  | 4561 |  | OUT (M) |  |  | STRING (BBL) | 80
CHECK TIME |  | 21:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 15 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 924.3
DEPTH, MD (M) |  | 4561 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 8.5 |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.26 | 0.03 |  | PITS (BBL) | 681
MW IN (SG) |  | 1.9 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | N.B STAB |  |  | 8.375 | 2.9375 |  | 4 1/2 IF |  | 1.74 | 0.22788 |  | ACT. SYS (BBL) | 1685.3
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDSi616LBPX |  | 1 x PONY DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 2.86 | 0.37456 |  | RESV. SYS (BBL) | 776
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | JP7562 |  | ST. STAB |  |  | 8.375 | 2.9375 |  | 4 1/2 IF |  | 1.88 | 0.24622 |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 1 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.27 | 1.2141 |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 55 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 6x13/32 |  | ST. STAB |  |  | 8.375 | 2.9375 |  | 4 1/2 IF |  | 1.55 | 0.203 |  | TOTAL | 2461.3
PV |  | 25 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | PBL SUB |  |  | 6.75 | 1.331 |  | 4 1/2 IF |  | 3.48 | 0.45576 |  | DIESEL (LTR)
YIELD POINT |  | 15 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | 15 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 138.86 | 18.186 |  | RIG TANK | 123046
GEL ST. |  | 8/12 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | HYD DRL JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.94 | 1.3018 |  | CAMP TANK | 12115
WL (ml/30 min) |  | 6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | 3 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 27.78 | 3.6382 |  | CONSUMED | 4748
CT ( in/32) |  | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | 12 x HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 111.43 | 8.1757 |  | RECEIVED
ALK (MUD) |  | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 135161
ALK (FILT.) |  | 0.3/2 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 65000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 121200
KCl (mg/l) |  | 38134 | JAR | 4.25 | STAB - 1 | 4.25 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 126200
CHLORIDES (mg/l) |  | 20000 | 5" HWDPS | 4.25 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 515000
HARDNESS (mg/l) |  | 400 | 6 1/2" DCS | 4.25 | STAB - 3 |  | TFA (IN²) |  |  | 0.778 | [12 empty] | POB
PENETREX % |  | 1 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 309.05 |  |  | MPCL | 5
OIL % |  | 2 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 20 |  |  | MPCL SERV | 22
SOLIDS % |  | 30.19 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. 14 RR |  |  | 1-1-WT-A-X-I-BT-LOG |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 13 |  |  | SECURITY
M.B.T. (lb/bbl) |  | 8.8 | DAILY CIRC. HRS |  | 1.31 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 52
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 120 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 113
DAILY WELL COST (US$) |  | 58932.375 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 12932999.4179 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE
% OF AFE SPENT |  | 64.97% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | LOT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (PI/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | NAGRI | SURFACE
FIRE DRILL | 2019-10-08 | 2019-11-07 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-10-07 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL | 2019-10-08 | 2019-11-07 | NEXT BOP TEST DATE |  | 2019-10-21 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-12
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43750 | 43750.0312 | 0.75 | DRL | PT-P | CIR | CIRCULATED FOR BOTTOMS UP. PUMPED SLUG PRIOR POOH.
43750.0312 | 43750.3958 | 8.75 | DRL | PT-P | COC | POOH FROM 4544M TO 318M AT THE TOP OF BHA.
43750.3958 | 43750.4583 | 1.5 | DRL | PT-P | COC | CONT'D POOH BHA TO SURFACE. L/D JAR, SCRAPPER & BIT.
43750.4583 | 43750.4896 | 0.75 | DRL | PT-P | RU | HELD PJSM. R/U SLB W/L GEARS.
43750.4896 | 43750.7292 | 5.75 | DRL | PT-P | W/L | CONDUCTED CBL-VDL -CCL-GR LOG IN 9 5/8" CSG.
43750.7292 | 43750.7396 | 0.25 | DRL | PT-P | RD | R/D SLB W/L GEARS.
43750.7396 | 43750.7812 | 1 | DRL | PT-P | BHA | HELD PJSM. P/U & M/U NEW 8 1/2" PDC BIT + N.B STAB + 1x PONY DC + ST. STAB + 1x DC + ST. STAB + PBL SUB.
43750.7812 | 43750.8125 | 0.75 | DRL | PT-P | E/C | FUNCTION TESTED PBL SUB. RETRIEVED DART AND BALLS FROM CATCHER TUBE.
43750.8125 | 43750.875 | 1.5 | DRL | PT-P | BHA | CONT'D RIH BHA FROM 21M TO 309M. L/D 1x 5" HWDP STD. FILLED UP BHA.
43750.875 | 43751 | 3 | DRL | PT-P | RIH | RIH FROM 309M TO 1546M. FILLED UP STRING AFTER EVERY 20 STDS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-13
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43751 | 43751.1667 | 4 | DRL | PT-P | RIH | CONT'D RIH FROM 1546M TO 3046M. FILLED UP STRING AFTER EVERY 20 STDS.
43751.1667 | 43751.25 | 2 | DRL | PT-P | DP / RIH | P/U & M/U 26x 5" S-135 DP SINGLE BY SINGLE FROM CATWALK AND RIH FROM 3046M TO 3297M. DRIFTED JTS WITH 2.5" DRIFT.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. CONDUCTED CBL-VDL -CCL-GR LOG IN 9 5/8" CSG. RIH NEW 8 1/2" PDC BIT WITH ROTARY BHA DOWN TO 1546M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH TO 4545M. DISPLACE HOLE WITH 1.65 SG MUD. DRILL OUT F/SHOE / CEMENT & FORMATION DOWN TO 4564M. CONDUCT FIT & DRILL 8 1/2" HOLE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14