## DDR#164
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 164
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-06-03
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | SAIFULLAH TURK/ SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4535 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 163.5833
RIG REP.: |  | TARIQ BUTT / FAYAAZ HUSSAIN MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4535 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-06-02 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 12.25 |  | BIT No. |  | 5RR5 |  | BHA No. |  |  | 20 | IN (M) |  | 4535 |  | OUT (M) | 4535 |  | STRING (BBL) | 286
CHECK TIME |  | 23:59 | MD @ 00:00HR (M) |  | 4535 |  | SIZE (IN) |  | 12 1/4" |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1767
DEPTH, MD (M) |  | 4535 | TVD @ 00:00HR (M) |  | 4535 |  | MANUFACTURER |  | HLB |  | PDC BIT |  |  | 12.25 | 3.25 |  | 6 5/8 REG |  | 0.35 | 0.1 |  | PITS (BBL) | 890
MW IN (SG) |  | 2.13 | DAILY PROGRESS (M) |  |  |  | TYPE |  | MMD65DMH |  | BIT SUB |  |  | 8-7/16" | 3 |  | 6 5/8 REG |  | 1.04 | 0.4 |  | ACT. SYS (BBL) | 2943
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 12932459 |  | 8 1/4'' NMDC |  |  | 8.25 | 2.75 |  | 6 5/8 REG |  | 9.22 | 2.0588 |  | RESV. SYS (BBL) | 723
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | STRING STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.33 | 0.52029 |  | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 4X16/32'' + 2x18/32" |  | 1 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.28 | 2.0722 |  | KILL MW (SG) | 2.3
µ FUNNEL (SEC) |  | 77 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4535 |  | STRING STAB |  |  | 12.125 | 2.875 |  | 6 5/8 REG |  | 2.48 | 0.55378 |  | TOTAL | 4266
PV |  | 30 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 11 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 101.92 | 22.7586 |  | DIESEL (LTR)
YIELD POINT |  | 42 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | DRILLING JAR |  |  | 7-5/8'' | 3.125 |  | 6 5/8 REG |  | 9.13 | 2.0387 |  | RIG TANK | 124000
GEL ST. |  | 21/42 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 1 X 8" DC |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 9.35 | 2.0878 |  | CAMP TANK | 30000
WL (ml/30 min.) |  | 6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | X/OVER |  |  | 8-3/8'' | 2.75 |  | 6 5/8 REG |  | 0.94 | 0.2099 |  | CONSUMED | 8500
CT ( in/32) |  | 3 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 7 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 65.55 | 4.8791 |  | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 154000
ALK (FILT.) |  | 0.5/1.3 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT IN HOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 189530
KCl (mg/l) |  | 46714 | JAR | 224.32 | STAB - 1 | 224.32 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 189530
CHLORIDES |  | 22000 | 5" HWDPS | 224.32 | STAB - 2 | 224.32 | TFA (IN²) |  | 1.28 | [12 empty] | TOTAL | 440000
CALCIUM |  | 240 | 8" DCS | 224.32 |  |  | HSI | [14 empty] | POB
OIL% |  | 6 | 9 1/2" DCS |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 211.59 |  |  | MPCL | 3
LUBE % |  | 2 | BHA ROT. HRS |  | 224.32 |  | BIT No. 5RR5 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 22 |  |  | MPCL SERV | 25
SOLIDS % |  | 36.75 | ON BOTTOM HRS |  | 163.49 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 18 |  |  | SECURITY | 4
M.B.T. |  | 12.5 | CIRC. HRS |  | 232.79 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 100 | 1 x 100 |  | 20" SURFACE CASING |  |  | 594 | 3890 |  | 1.43 |  | 99.8 |  |  | 0.35 |  | EMS |  | TOTAL | 120
DAILY WELL COST (US$) |  | 48565 | SHAKER-2 | 2 x 140 | 1 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4187 |  | 1 |  | - |  |  | - |  | TOTCO |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 10540510 | SHAKER-3 | 2 x 140 | 1 x 140 |  | 9 5/8" PRODUCTION CSG |  |  |  | 4395 |  | 1 |  | - |  |  | - |  | TOTCO |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 58.4% | MUD CLEANER | 1 x 170 + 2 x 140 |  |  | 7" LINER |  |  |  | 4525 |  | 0.75 |  | - |  |  | - |  | TOTCO |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI) | 234
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-05-18 | 2018-06-17 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 4519 |  | 975 / 1080 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-05-20 | 2018-06-19 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 4519 |  | 970 / 1070 |  | KAMLIAL | 1255
PIT DRILL | 2018-04-25 | 2018-05-25 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA | [14 empty] | MURREE | 1445
KICK DRILL | 2018-05-18 | 2018-06-17 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-05-18 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  | 0 |  | MUD LOSSES |  |  |  | 133 |  | SAKESAR
STRETCHER DRILL | 2018-05-20 | 2018-06-19 | NEXT BOP TEST DATE |  | 2018-06-08 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-06-02
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43253 | 43253.0417 | 1 | DRL | PT-P | CIR | CONT'D CIRCULATION TO CONDITION MUD.
43253.0417 | 43253.2292 | 4.5 | DRL | PT-P | POOH | POOH FROM 4535M TO 3500M. (PUMPED OUT TIGHT HOLE SECTIONS FROM 4350 TO 4340M & FROM 4240M TO 4225M).
43253.2292 | 43253.3958 | 4 | DRL | PT-P | RIH | RIH FROM 3500 M TO 4507 M. WASHED DOWN LAST STAND. TIGHT SPOTS OBSERVED DURING RIH @4100M;4110M;4140M;4266M;4468M CLEARED BY RECIPROCATION OF DRILL STRING.
43253.3958 | 43253.5 | 2.5 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE PRIOR TO WIPER TRIP.
43253.5 | 43253.5104 | 0.25 | DRL | PT-P | FC | FLOW CHECKED. WELL STATIC
43253.5104 | 43253.6562 | 3.5 | DRL | PT-P | POOH | POOH UP TO 4196M. DURING POOH TIGHT SPOTS OBSERVED, BACK REAMED @ 4451M TO 4441M;4424M; 4413M TO 4411M. FOLLOWING TIGHT SPOTS OBSERVED WHEN TOOL JOINT WAS NEAR ROTARY TABLE 4386M;4376M;4348M; 4319M & 4311M- CLEARED BY RECIPROCATION OF DRILL STRING.
43253.6562 | 43253.7292 | 1.75 | DRL | PT-P | RW | OBSERVED COMPRESSION WHILE RIH, REAMED DOWN FROM 4196M TO 4280M. OBSERVED HARD REAMING BELOW 4216M.
43253.7292 | 43253.7917 | 1.5 | DRL | PT-P | RIH | RIH ON ELEVATORS FROM 4280M TO 4510M.
43253.7917 | 43253.8021 | 0.25 | DRL | PT-P | RW | WASHED/REAMED DOWN FROM 4510M TO 4535M.
43253.8021 | 43253.9583 | 3.75 | DRL | PT-P | CIR | CIRCULATED TO CONDITION MUD.
43253.9583 | 43254 | 1 | DRL | PT-P | SP | PUMPED & DISPLACED 275 BBL (6PPB) LUBRA BEADS PILL IN OPEN HOLE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-06-03
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43254 | 43254.1042 | 2.5 | DRL | PT-P | POOH | POOH FROM 4535M TO 4000M. OBSERVED MINOR TIGHT HOLE SECTIONS AT 4247M; 4218M TO 4214M; 4199M; 4146M. CLEARED SAME BY RECIPROCATION OF DRILL STRING.
43254.1042 | 43254.1562 | 1.25 | DRL | PT-P | SP | PUMPED & DISPLACED SECOND PILL, 275 BBL (6PPB) LUBRA BEADS IN OPEN HOLE.
43254.1562 | 43254.25 | 2.25 | DRL | PT-P | POOH | POOH FROM 4000M TO 3328M.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | POOH IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D CIRCULATION TO CONDITION MUD, POOH FROM 4535M TO 3500M (PUMPED OUT TIGHT HOLE SECTIONS), RIH TO BTM AT 4535M, CIRCULATION, POOH TO 4196M, RIH TO BTM (REAMED DOWN TIGHT SPOTS), CIRCULATION TO CONDITION MUD, SPOTTED 275 BBL LUBRA BEADS PILL.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH FROM 4535M TO 4000M, SPOT SECOND LUBRA BEADS PILL, POOH TO SURFACE, L/DOWN S. STAB + JAR + BIT. CHANGE UPPER PIPE RAMS TO CSG RAMS, R/UP W.FORD FOR 9 5/8'' CSG JOB.
REMARKS |  |  | PREPARING FOR 9 5/8'' CSG JOB.
Formulas:
DHARIAN - 1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14+7