## DDR#166
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 166
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-10-17
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4672 | 4672 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 165.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4672 | 4672 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 24
2019-10-16 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 8.5 |  | RUN NO. |  |  | 28 |  | BHA NO. |  |  | 31 | IN (M) |  | 4561 |  | OUT (M) | 4672 |  | STRING (BBL) | 262.2
CHECK TIME | 10:00 | 23:59 | MD @ 00:00HR (M) |  | 4672 |  | BIT NO. |  |  | 15 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 701.7
DEPTH, MD (M) | 4670 | 4672 | TVD @ 00:00HR (M) |  | 4672 |  | SIZE (IN) |  |  | 8.5 |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.26 | 0.03 |  | PITS (BBL) | 556
MW IN (SG) | 1.7 | 1.7 | DAILY PROGRESS (M) |  | 24 |  | MANUFACTURER |  |  | SMITH |  | N.B STAB |  |  | 8.375 | 2.9375 |  | 4 1/2 IF |  | 1.74 | 0.22788 |  | ACT. SYS (BBL) | 1519.9
MW OUT (SG) | 1.7 | 1.7 | INST. ROP (M/HR) |  | - |  | TYPE |  |  | MDSi616LBPX |  | 1 x PONY DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 2.86 | 0.37456 |  | RESV. SYS (BBL) | 1728
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 3.1933 |  | SERIAL NO. |  |  | JP7562 |  | ST. STAB |  |  | 8.375 | 2.9375 |  | 4 1/2 IF |  | 1.88 | 0.24622 |  | KILL MUD (BBL)
FL TEMP. °F | 145 | 147 | AVG. WOB (TON) |  | 3-6 |  | IADC CODE |  |  |  |  | 1 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.27 | 1.2141 |  | KILL MW (SG)
µ FUNNEL (SEC) | 52 | 55 | AVG. RPM SURFACE |  | 100 |  | NOZZLES (1/32") |  |  | 6x13/32 |  | ST. STAB |  |  | 8.375 | 2.9375 |  | 4 1/2 IF |  | 1.55 | 0.203 |  | TOTAL | 3247.9
PV | 41 | 43 | AVG. RPM DOWNHOLE |  | 100 |  | DEPTH IN (M) |  |  | 4561 |  | PBL SUB |  |  | 6.75 | 1.331 |  | 4 1/2 IF |  | 3.48 | 0.45576 |  | DIESEL (LTR)
YIELD POINT | 26 | 26 | FLOWRATE (GPM) |  | 480 |  | DEPTH OUT (M) |  |  | 4672 |  | 15 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 138.86 | 18.186 |  | RIG TANK | 122535
GEL ST. | 10/13 | 12/15 | PRESSURE (PSI) |  | 3300-3400 |  | METERAGE (M) |  |  | 111 |  | HYD DRL JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.94 | 1.3018 |  | CAMP TANK | 26053
WL (ml/30 min) | 4.2 | 4 | TORQ. ON-BTM (KLB-FT) |  | 3-8 |  | RPM SURF. |  |  | 100 |  | 3 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 27.78 | 3.6382 |  | CONSUMED | 9609
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 2-3 |  | RPM BTM. |  |  | 100 |  | 12 x HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 111.43 | 8.1757 |  | RECEIVED
ALK (MUD) | 0.4 | 0.5 | STRING WT. (TON) - ROT |  | 167 |  | WOB (TON) |  |  | 3-6 | [12 empty] | TOTAL | 148588
ALK (FILT.) | 0.2/1 | 0.3/1.2 | PICK-UP WT. (TON) |  | 182 |  | AVG. ROP (M/HR) |  |  | 3.1933 | [12 empty] | WATER (LTR)
pH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 170 |  | BIT ROT HRS. |  |  | 34.76 | [12 empty] | RIG STORAGE | 350000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  | 46.75 | [12 empty] | CAMP STORAGE | 60000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  | 203.66 | [12 empty] | CONSUMED | 223600
KCl (mg/l) | 55294.3 | 56247.7 | JAR | 57.56 | STAB - 1 | 57.56 | ANN. VEL. (M/MIN) |  |  | 87.6 | [12 empty] | RECEIVED | 183600
CHLORIDES (mg/l) | 27000 | 28000 | 5" HWDPS | 57.56 | STAB - 2 | 53.31 | JET VELOCITY (M/SEC) |  |  | 61.48 | [12 empty] | TOTAL | 410000
HARDNESS (mg/l) | 320 | 320 | 6 1/2" DCS | 57.56 | STAB - 3 | 53.31 | TFA (IN²) |  |  | 0.778 | [12 empty] | POB
PENETREX % | 2 | 2 |  |  |  |  | HSI |  |  | 2.59 |  | TOTAL LENGTH (M) | [7 empty] | 309.05 |  |  | MPCL | 5
OIL % | 1 | 1 | DAILY BHA ROT. HRS |  | 14 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 20 |  |  | MPCL SERV | 18
SOLIDS % | 32.33 | 32.29 | DAILY ON BOTTOM HRS |  | 7.89 |  | BIT NO. 15 |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 13 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 20.98 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x100 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 112
DAILY WELL COST (US$) |  | 56587.15 | SHAKER-2 | 3 x 120 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 13284273.9804 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 66.74% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1945.7226
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (PI/P2) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4641 | 680/650 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4641 | 820/800 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-10-08 | 2019-11-07 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-10-07 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI | 4576/4576
STRETCHER DRILL | 2019-10-08 | 2019-11-07 | NEXT BOP TEST DATE |  | 2019-10-21 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 17 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR | 4667/4667
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-16
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43754 | 43754.375 | 9 | DRL | PT-P | D | CONT'D DRILLING 8 1/2" HOLE FROM 4648M TO 4670M.
43754.375 | 43754.4583 | 2 | DRL | PT-P | CS | CIRCULATED FOR BOTTOMS UP TO COLLECT FORMATION SAMPLE.
43754.4583 | 43754.5 | 1 | DRL | PT-P | D | RESUMED DRILLING & DRILLED 8 1/2" HOLE FROM 4670M TO 4672M.
43754.5 | 43754.5938 | 2.25 | DRL | PT-P | CS | CIRCULATED FOR BOTTOMS UP TO COLLECT FORMATION SAMPLE. GEOLOGIST CONFIRMED CORE POINT @ 4672M & TOP OF SAKESSAR FM @ 4667M.
43754.5938 | 43754.6042 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43754.6042 | 43754.6667 | 1.5 | DRL | PT-P | WT | POOH INSIDE 9 5/8" CSG SHOE (4547M). BACK REAMED TIGHT HOLE FROM 4650M TO 4622M. WASHED UP FROM 4622M TO 4565M.
43754.6667 | 43754.6771 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43754.6771 | 43754.75 | 1.75 | DRL | PT-P | WT | RIH DOWN TO BOTTOM @ 4672M. DURING RIH; OBSERVED TIGHT SPOTS AT 4589M TO 4591M. CLEARED WITH RECPROCATION OF STRING. WASHED DOWN TIGHT SPOTS FROM 4606M TO 4610M & REAMED DOWN TIGHT SPOTS FROM 4610M TO 4613M - WASHED DOWN FROM 4613 M TO 4663M - REAMED DOWN FROM 4663M TO BOTTOM. ERRATIC TORQUE & SPP VARIATION OBSERVED DURING REAMING AT 4663M. OBSERVED EXCESSIVE MECHANICAL CAVING AT BOTTOMS UP.
43754.75 | 43754.8438 | 2.25 | DRL | PT-P | CIR | PUMPED 40 BBL HI-VIS PILL & CIRCULATED OUT. OBSERVED EXCESSIVE MECHANICAL CAVING AT BOTTOMS UP.
43754.8438 | 43754.8542 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43754.8542 | 43754.8958 | 1 | DRL | PT-P | WT | CONDUCTED WIPER TRIP TO 9 5/8" CSG SHOE. HOLE CONDITION, GOOD.
43754.8958 | 43754.9896 | 2.25 | DRL | PT-P | CIR | PUMPED 30 BBL HI-VIS PILL & CIRCULATED OUT TILL SHAKERS CLEAN.
43754.9896 | 43755 | 0.25 | DRL | PT-P | SP | PUMPED 50 BBL BRIDGING PILL.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-17
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43754 | 43754.0312 | 0.75 | DRL | PT-P | SP | CONT'D PUMPING 50 BBL BRIDGING PILL, UNDERDISPLACED & SPOTTED AT BOTTOM.
43754.0312 | 43754.25 | 5.25 | DRL | PT-P | POOH | POOH FROM 4672M TO 2671M & IS IN PROGRESS. FLOW CHECKED AT BOTTOM & INSIDE CSG SHOE, WELL STATIC.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | SAKESSAR / LIMESTONE.
OPERATIONS AT 06:00 HRS |  |  | POOH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 8 1/2" HOLE FROM 4648M TO 4672M (CORING POINT). CONDUCTED WIPER TRIP TWICE. CIRCULATED TO CLEAN HOLE PRIOR POOH.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. RIH WITH CORING ASSY FOR CORE # 01 IN SAKESSAR FORMATION.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14