## DDR#168
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 168
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-10-19
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4673.3 | 4673.3 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 167.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4673.3 | 4673.3 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 1.3
2019-10-18 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 8.5 |  | RUN NO. |  |  | 29 |  | BHA NO. |  |  | 32 | IN (M) |  | 4672 |  | OUT (M) | 4673.3 |  | STRING (BBL) | 142.8
CHECK TIME | 11:00 | 23:59 | MD @ 00:00HR (M) |  | 4673.3 |  | BIT NO.(CORE HEAD) |  |  | 16 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 865.5
DEPTH, MD (M) | 4672 | 4673.3 | TVD @ 00:00HR (M) |  | 4673.3 |  | SIZE (IN) |  |  | 8 1/2" x 4" |  | CORE HEAD |  |  | 8.5 |  |  | HDT |  | 0.37 | 0.053 |  | PITS (BBL) | 570
MW IN (SG) | 1.7 | 1.7 | DAILY PROGRESS (M) |  | 1.3 |  | MANUFACTURER |  |  | HALLIBURTON |  | OUTER CORE BARREL |  |  | 6.75 | 5.375 |  | HDT |  | 11.08 | 1.3456 |  | ACT. SYS (BBL) | 1578.3
MW OUT (SG) | 1.7 |  | INST. ROP (M/HR) |  | - |  | TYPE |  |  | FC3843 |  | PBL SUB |  |  | 6.75 | 1.33 |  | 4 1/2 IF |  | 3.48 | 0.45576 |  | RESV. SYS (BBL) | 1668
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 0.75581 |  | SERIAL NO. |  |  | 13079049 |  | 15 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 138.86 | 18.186 |  | KILL MUD (BBL)
FL TEMP. °F | 148 |  | AVG. WOB (TON) |  | 1-10 |  | IADC CODE |  |  | M433 |  | HYD DRL JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.94 | 1.3018 |  | KILL MW (SG)
µ FUNNEL (SEC) | 54 | 57 | AVG. RPM SURFACE |  | 50-70 |  | NOZZLES (1/32") |  |  | 8 x PORTS |  | 3 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 27.78 | 3.6382 |  | TOTAL | 3246.3
PV | 42 | 44 | AVG. RPM DOWNHOLE |  | 50-70 |  | DEPTH IN (M) |  |  | 4672 |  | 12 x HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 111.43 | 8.1757 |  | DIESEL (LTR)
YIELD POINT | 26 | 27 | FLOWRATE (GPM) |  | 180-240 |  | DEPTH OUT (M) |  |  | 4673.3 | [12 empty] | RIG TANK | 111299
GEL ST. | 9/12 | 11/15 | PRESSURE (PSI) |  | 970-1240 |  | METERAGE (M) |  |  | 1.3 | [12 empty] | CAMP TANK | 25086
WL (ml/30 min) | 4.2 | 4.2 | TORQ. ON-BTM (KLB-FT) |  | 3-9 |  | RPM SURF. |  |  | 50-70 | [12 empty] | CONSUMED | 5462
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 1-2 |  | RPM BTM. |  |  | 50-70 | [12 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 173 |  | WOB (TON) |  |  | 1-10 | [12 empty] | TOTAL | 136385
ALK (FILT.) | 0.4/1.2 | 0.4/1.2 | PICK-UP WT. (TON) |  | 175 |  | AVG. ROP (M/HR) |  |  | 0.75581 | [12 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  | 170 |  | BIT ROT HRS. |  |  | 1.72 | [12 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  | 5.99 | [12 empty] | CAMP STORAGE | 72000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  | 5.99 | [12 empty] | CONSUMED | 133600
KCl (mg/l) | 55294.3 | 55294.3 | JAR | 66.22 | STAB - 1 | 66.22 | ANN. VEL. (M/MIN) |  |  | 34.2 | [12 empty] | RECEIVED | 130600
CHLORIDES (mg/l) | 28000 | 28000 | 5" HWDPS | 66.22 | STAB - 2 | 61.97 | JET VELOCITY (M/SEC) |  |  | 10.53 | [12 empty] | TOTAL | 522000
HARDNESS (mg/l) | 320 | 320 | 6 1/2" DCS | 66.22 | STAB - 3 | 61.97 | TFA (IN²) |  |  | 1.77 | [12 empty] | POB
PENETREX % | 2 | 2 |  |  |  |  | HSI |  |  | 0.03 |  | TOTAL LENGTH (M) | [7 empty] | 302.94 |  |  | MPCL | 5
OIL % | 0.5 | 0.5 | DAILY BHA ROT. HRS |  | 8.66 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 25 |  |  | MPCL SERV | 18
SOLIDS % | 32.39 | 32.39 | DAILY ON BOTTOM HRS |  | 1.72 |  | BIT NO. 15 |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 16 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 10.21 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 106
DAILY WELL COST (US$) |  | 37612.85 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 13429325.3504 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 67.46% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1945.7226
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (PI/P2) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4670 | 780/770 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4670 | 950/920 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-10-08 | 2019-11-07 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 60 |  | 4670 | 1010 / -- |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-10-07 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI | 4576/4576
STRETCHER DRILL | 2019-10-08 | 2019-11-07 | NEXT BOP TEST DATE |  | 2019-10-22 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR | 4667/4667
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-18
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43756 | 43756.2917 | 7 | DRL | PT-P | COR / RIH | CONT'D RIH CORING ASSEMBLY FROM 2576M TO 4578M. BROKE CIRCULATION AFTER 1500M.
43756.2917 | 43756.3542 | 1.5 | DRL | PT-P | COR / RW | WASHED DOWN FROM 4578M DOWN TO BOTTOM @ 4672M.
43756.3542 | 43756.4167 | 1.5 | DRL | PT-P | COR / CIR | CIRCULATED FOR BOTTOM UP. MAXIMUM TG RECORDED 1.97%.
43756.4167 | 43756.4479 | 0.75 | DRL | PT-P | COR / CIR | DROPPED 1.25" STEEL BALL INSIDE STRING & CHASED WITH MUD. OBSERVED CLEAR INDICATION OF BALL SEATING. SPP INCREASED FROM 1450 PSI TO 1720 PSI. RECORDED SCR.
43756.4479 | 43756.6875 | 5.75 | DRL | PT-P | COR | TAGGED BOTTOM & STARTED CUTTING CORE. CUT CORE FROM 4672M TO 4673.3M. STOPPED CORING DUE TO NO ROP & CORING TORQUE DECREASED FROM 9 KFT-LB TO 3 KFT-LB. DECIDED TO POOH. P/UP STRING OFF BOTTOM TO BREAK CORE. NO OVER PULL OBSERVED.
43756.6875 | 43756.6979 | 0.25 | DRL | PT-P | COR / FC | FLOW CHECKED, WELL STATIC.
43756.6979 | 43756.7292 | 0.75 | DRL | PT-P | COR / RW | PUMPED OUT TO 4522M (INSIDE CSG SHOE) TO AVOID SWABBING.
43756.7292 | 43756.7396 | 0.25 | DRL | PT-P | COR / FC | FLOW CHECKED, WELL STATIC.
43756.7396 | 43757 | 6.25 | DRL | PT-P | COR / POOH | POOH FROM 4522M TO 2606M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43757 | 43757.25 | 6 | DRL | PT-P | COR / POOH | CONT'D POOH FROM 2606M TO 561M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | SAKESSAR / LIMESTONE.
OPERATIONS AT 06:00 HRS |  |  | POOH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH FROM 2576M DOWN TO BOTTOM. CUT CORE# 01 IN SAKESSAR FORMATION FROM 4672M TO 4673.3M. POOH TO 2606M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH & RECOVER CORE# 01. RIH AGAIN WITH CORING ASSY FOR CORE# 02 IN SAKESSAR FORMATION.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+15