## DDR#169
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 169
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-06-08
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | SAIFULLAH TURK/ SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4535 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 168.5833
RIG REP.: |  | TARIQ BUTT / FAYAAZ HUSSAIN MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4535 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-06-07 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT No. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 502
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1548
DEPTH, MD (M) | 4535 | 4535 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  |  | 9 5/8'' F/SHOE |  |  | 9.625 |  |  | VT |  | 0.711 |  |  | PITS (BBL) | 571
MW IN (SG) | 2.2 | 2.32 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  |  | 1 X 9 5/8'' JT |  |  | 9.625 | 8.535 |  | VT |  | 12.823 |  |  | ACT. SYS (BBL) | 2621
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  | 2 X 9 5/8'' JT |  |  | 9.625 | 8.535 |  | VT |  | 12.823 |  |  | RESV. SYS (BBL) | 721
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | 9 5/8'' F/COLLAR |  |  | 9.625 |  |  | VT |  | 0.895 |  |  | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  |  |  | 3 X 9 5/8'' JT |  |  | 9.625 | 8.535 |  | VT |  | 12.82 |  |  | KILL MW (SG) | 2.4
µ FUNNEL (SEC) | 60 | 62 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | 9 5/8'' L/COLLAR |  |  | 9.625 | 8.535 |  | VT |  | 0.546 |  |  | TOTAL | 3942
PV | 37 | 41 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT | 24 | 25 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 126000
GEL ST. | 18/37 | 19/38 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 27500
WL (ml/30 min.) | 6 | 6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 5500
CT ( in/32) | 3 | 3 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 153500
ALK (FILT.) | 0.5/1.4 | 0.5/1.4 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9.3 | 9.3 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT IN HOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 94930
KCl (mg/l) | 32032.6 | 31460.5 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 94930
CHLORIDES | 15000 | 14500 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 440000
CALCIUM | 240 | 240 | 8" DCS |  |  |  | HSI | [14 empty] | POB
OIL% | 4 | 4 | 9 1/2" DCS |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 40.618 |  |  | MPCL | 4
LUBE % | 2 | 2 | BHA ROT. HRS |  |  |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 24
SOLIDS % | 39.49 | 43.04 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. | 12.5 | 12.5 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 100 | 1 x 100 |  | 20" SURFACE CASING |  |  | 594 | 3890 |  | 1.43 |  | 99.8 |  |  | 0.35 |  | EMS |  | TOTAL | 117
DAILY WELL COST (US$) |  | 45073 | SHAKER-2 | 2 x 140 | 1 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4187 |  | 1 |  | - |  |  | - |  | TOTCO |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 10758634 | SHAKER-3 | 2 x 140 | 1 x 140 |  | 9 5/8" PRODUCTION CSG |  |  |  | 4395 |  | 1 |  | - |  |  | - |  | TOTCO |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 59.61% | MUD CLEANER | 1 x 170 + 2 x 140 |  |  | 7" LINER |  |  |  | 4525 |  | 0.75 |  | - |  |  | - |  | TOTCO |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI) | 234
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-05-18 | 2018-06-17 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 4519 |  | 975 / 1080 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-05-20 | 2018-06-19 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 4519 |  | 970 / 1070 |  | KAMLIAL | 1255
PIT DRILL | 2018-04-25 | 2018-05-25 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA | [14 empty] | MURREE | 1445
KICK DRILL | 2018-05-18 | 2018-06-17 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-05-18 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  | 611 |  | MUD LOSSES |  |  |  | 133 |  | SAKESAR
STRETCHER DRILL | 2018-05-20 | 2018-06-19 | NEXT BOP TEST DATE |  | 2018-06-08 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-06-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43258 | 43258.1146 | 2.75 | DRL | NPT-UP | POOH | CONT'D POOH FROM 2221M TO 2164M, MEANWHILE CHECKED STAGE COLLAR AND ACP. FOUND ACP, OK. L/DOWN STAGE COLLAR AND ACP.
43258.1146 | 43258.2292 | 2.75 | DRL | NPT-UP | CIR | DISCONNECTED CSG FILL UP TOOL, CONNECTED CIRCULATING SWEDGE AND TRIED TO ESTABLISH CIRCULATION, OBSERVED RETURNS. CIRCULATED TO CONDITION HOLE. WHILE CIRCULATING OBSERVED PIT GAIN = 50 BBL.
43258.2292 | 43258.2396 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED, WELL FLOWING.
43258.2396 | 43258.5417 | 7.25 | DRL | NPT-UP | WC | CLOSED BOP, SHUT IN THE WELL FOR RECORDING SIDPP & SICP PRESSURES. SIDPP = 520 & SICP = 380 @ 1300 HRS, MEANWHILE PREPARED 2.24 SG KILL MUD.
43258.5417 | 43258.7396 | 4.75 | DRL | NPT-UP | WC | STARTED KILLING THE WELL WITH 2.24 SG KILL MUD MEANWHILE CIRCULATED THROUGH CHOKE.
43258.7396 | 43259 | 6.25 | DRL | NPT-UP | WC | STOPPED CIRCULATION, SHUT IN THE WELL, CLOSED CHOKE & OBSERVED WELL, RECORDED SIDPP = (GRADUALLY INCREASED & STABILIZED AT 196 PSI @ 1900 HRS) SIDPP = 136 PSI, SICP = ZERO PSI @ 00:00 HRS. MEANWHILE PREPARED KILL MUD OF 2.32 SG.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-06-08
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43259 | 43259.0729 | 1.75 | DRL | NPT-UP | WC/ E/C | OBSERVED SICP = ZERO DURING SHUT IN, CHECKED SENSORS AT CHOKE MANIFOLD, FLUSHED CHOKE MANIFOLD BY DWL SCHL CEMENTING UNIT, CLOSED MANUAL & HCR VALVES AT CHOKE LINE. DISCONNECTED CO-FLEX HOSE (CHOKE LINE) TO CHECK POTENTIAL PLUGGING OF LINE. CIRCULATED THROUGH CO-FLEXIP BY CEMENT UNIT, FOUND NO PLUGGING. FLUSHED & CLEANED CO-FLEXIP.
43259.0729 | 43259.1146 | 1 | DRL | NPT-UP | P/T | CONNECTED CO-FLEX HOSE AND PRESSURE TESTED SAME AT 6500 PSI, OK.
43259.1146 | 43259.1875 | 1.75 | DRL | NPT-UP | E/C | OPENED MANUAL VALVE & HCR AT CHOKE LINE TO CHECK RETURN, OBSERVED NO RETURN, OPENED WING VALVE AT CHH, OBSERVED MINOR RETURN AND SEIZED. CONFIRMED SICP = ZERO.
43259.1875 | 43259.1979 | 0.25 | DRL | NPT-UP | SM | CONDUCTED PJSM.
43259.1979 | 43259.25 | 1.25 | DRL | NPT-UP | WC | STARTED KILLING WELL WITH 2.32 SP.GR MUD & IN PROGRESS AT 0600 HRS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | WELL KILLING IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D POOH 9 5/8'' CSG FROM 2221M TO 2164M MEANWHILE L/DOWN STAGE COLLAR AND ACP, ATTEMPTED TO ESTABLISH CIRCULATION, CIRCULATION RESUMED, CIRCULATED HOLE MEANWHILE GAIN OBSERVED, WELL FLOWING, SHUT IN THE WELL. WELL CONTROL IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | WELL CONTROL, POOH 9 5/8'' CSG TO SURFACE.
REMARKS
Formulas:
DHARIAN - 1 = [KCL LIGNOSULPHONATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14+7