## DDR#169
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 169
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-10-20
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4673.7 | 4673.7 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 168.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4673.7 | 4673.7 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-10-19 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 30 |  | BHA NO. |  |  | 32 | IN (M) |  | 4673.7 |  | OUT (M) |  |  | STRING (BBL) | 247.4
CHECK TIME |  | 22:00 | MD @ 00:00HR (M) |  |  |  | BIT NO.(CORE HEAD) |  |  | 17 RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 722.4
DEPTH, MD (M) |  | 4673.7 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 8 1/2" x 4" |  | CORE HEAD |  |  | 8.5 |  |  | HDT |  | 0.37 | 0.053 |  | PITS (BBL) | 498
MW IN (SG) |  | 1.7 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | HALLIBURTON |  | OUTER CORE BARREL |  |  | 6.75 | 5.375 |  | HDT |  | 11.08 | 1.3456 |  | ACT. SYS (BBL) | 1467.8
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | FC3843 |  | PBL SUB |  |  | 6.75 | 1.33 |  | 4 1/2 IF |  | 3.48 | 0.45576 |  | RESV. SYS (BBL) | 1768
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 12886217 |  | 15 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 138.86 | 18.186 |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  | M433 |  | HYD DRL JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.94 | 1.3018 |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 60 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 8 x PORTS |  | 3 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 27.78 | 3.6382 |  | TOTAL | 3235.8
PV |  | 42 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4673.7 |  | 12 x HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 111.43 | 8.1757 |  | DIESEL (LTR)
YIELD POINT |  | 25 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 107294
GEL ST. |  | 8/11 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 24634
WL (ml/30 min) |  | 4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 4457
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) |  | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 131928
ALK (FILT.) |  | 0.3/1.3 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 80000
KCl (%) |  | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 103500
KCl (mg/l) |  | 57201 | JAR | 66.22 | STAB - 1 | 66.22 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 111500
CHLORIDES (mg/l) |  | 29000 | 5" HWDPS | 66.22 | STAB - 2 | 61.97 | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 530000
HARDNESS (mg/l) |  | 320 | 6 1/2" DCS | 66.22 | STAB - 3 | 61.97 | TFA (IN²) |  |  | 1.77 | [12 empty] | POB
PENETREX % |  | 2 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 302.94 |  |  | MPCL | 5
OIL % |  | 0.5 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 25 |  |  | MPCL SERV | 18
SOLIDS % |  | 32.85 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. 16 |  |  | 0-3-BT-S-X-I-NO-PR |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 16 |  |  | SECURITY
M.B.T. (lb/bbl) |  | 5 | DAILY CIRC. HRS |  | 0.6 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 106
DAILY WELL COST (US$) |  | 30703 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 13460028.3504 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 67.62% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1945.7226
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (PI/P2) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4670 | 500/480 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4670 | 675/645 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-10-08 | 2019-11-07 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4670 | 850/780 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-10-07 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI | 4576/4576
STRETCHER DRILL | 2019-10-08 | 2019-11-07 | NEXT BOP TEST DATE |  | 2019-10-22 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR | 4667/4667
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43757 | 43757.2812 | 6.75 | DRL | PT-P | COR / POOH | CONT'D POOH FROM 2606M TO 302M (BHA TOP).
43757.2812 | 43757.2917 | 0.25 | DRL | PT-P | COR / FC | FLOW CHECKED, WELL STATIC.
43757.2917 | 43757.3542 | 1.5 | DRL | PT-P | COR / POOH | POOH TO SURFACE.
43757.3542 | 43757.4271 | 1.75 | DRL | PT-P | COR / BHA | HANDDLED CORE BARREL AT SURFACE. BROKE OUT & CHECKED INNER BARREL. FOUND ROTATING FREELY. L/D INNER BARREL ALONG WITH CORE. DRESSED CORE BARREL WITH NEW INNER BARREL. REPLACED CORE HEAD WITH RR- 8 1/2" x 4" CORE HEAD.
43757.4271 | 43757.5 | 1.75 | DRL | PT-P | COR / BHA | RIH WITH CORING ASSY AS PER BHA DOWN TO 302M.
43757.5 | 43758 | 12 | DRL | PT-P | COR / RIH | RIH CORING ASSEMBLY FROM 302M TO 4415M. BROKE CIRCULATION AFTER 1500M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-20
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43758 | 43758.0312 | 0.75 | DRL | PT-P | COR / RIH | CONT'D RIH CORING ASSEMBLY FROM 4415M TO 4629M.
43758.0312 | 43758.0729 | 1 | DRL | PT-P | COR / RW | REAMED / WASHED DOWN FROM 4629M TO 4673.7M.
43758.0729 | 43758.1562 | 2 | DRL | PT-P | COR / CIR | PUMPED & CIRCULATED OUT 40 BBL HI-VIS TILLL SHAKERS CLEAN.
43758.1562 | 43758.1875 | 0.75 | DRL | PT-P | COR / CIR | DROPPED 1.25" STEEL BALL INSIDE STRING & CHASED WITH MUD AT 120 GPM. OBSERVED PRESSURE INCREASE FROM 500 PSI TO 580 PSI. RECORDED SCR.
43758.1875 | 43758.25 | 1.5 | DRL | PT-P | COR | TAGGED BOTTOM & STARTED CUTTING CORE# 02. CUT CORE FROM 4673.7M TO 4674.4M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | SAKESSAR / LIMESTONE.
OPERATIONS AT 06:00 HRS |  |  | CORING IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH FROM 2606M TO SURFACE & RETRIEVED CORE. RIH AGAIN WITH CORING ASSY DOWN TO 4415M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CUT CORE# 02 IN SAKESSAR FORMATION. POOH TO SURFACE & RETRIEVE CORE.
REMARKS |  |  | 1.6M (94%) CORE RECOVERED. DEPTH ADJUSTED AS PER CORE RECOVERED.
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+15