## DDR#17
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 17
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-01-07
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR / MOHSIN / M. AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 1409 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 16.5833
RIG REP.: |  | SARDAR NAEEM / KHALID MEHMOOD |  |  | MD/TVD @ 06:00HRS: |  | 1440 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 125
2018-01-06 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 17.5 |  | BIT No. |  | 3 |  | BHA No. |  |  | 4 | IN (M) |  | 595 |  | OUT (M) |  |  | STRING (BBL) | 76.95
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 1409 |  | SIZE (IN) |  | 17.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1326.78
DEPTH, MD (M) | 1355 | 1409 | TVD @ 00:00HR (M) |  | 1409 |  | MANUFACTURER |  | NOV |  | 17 1/2" PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 | 0.35 |  | PITS (BBL) | 731
MW IN (SG) | 1.3 | 1.3 | DAILY PROGRESS (M) |  | 125 |  | TYPE |  | TFH519S |  | MUD MOTOR |  |  | 9.75 | 7.85 |  | 7 5/8 REG |  | 9.87 | 2.9 |  | ACT. SYS (BBL) | 2134.73
MW OUT (SG) | 1.3 | 1.3 | INST. ROP (M/HR) |  | 5.6 |  | SERIAL NO. |  | E244694 |  | FLOAT SUB |  |  | 9.5 | 2.5 |  | 7 5/8 REG |  | 0.62 | 0.2 |  | RESV. SYS (BBL) | 985
ECD (SG) | 1.3074 | 1.3074 | AVG. ROP (M/HR) |  | 5.78 |  | IADC CODE |  | S422 |  | STRING STAB |  |  | 17.375 | 2.9375 |  | 7 5/8 REG |  | 2.43 | 0.8 |  | KILL MUD (BBL) | 375
FL TEMP. °F | 129.2 | 129.2 | AVG. WOB (TON) |  | 4 - 8 |  | NOZZLES |  | 5X18/32" |  | LOWER SAVER SUB |  |  | 9.5 | 3.5 |  | 7 5/8 REG |  | 0.61 | 0.2 |  | KILL MW (SG) | 1.8
µ FUNNEL (SEC) | 58 | 56 | AVG. RPM SURFACE |  | 95 |  | DEPTH IN (M) |  | 595 |  | SLIM PULSE |  |  | 9.375 | 5 |  | 7 5/8 REG |  | 9.4 | 2.7 |  | TOTAL | 3494.73
PV | 29 | 27 | AVG. RPM DOWNHOLE |  | 195 |  | DEPTH OUT (M) |  |  |  | UPPER SAVER SUB |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 0.44 | 0.1 |  | DIESEL (LTR)
YIELD POINT | 28 | 30 | FLOWRATE (GPM) |  | 900 |  | METERAGE (M) |  | 814 |  | NMDC |  |  | 8.875 | 3.5 |  | 7 5/8 REG |  | 8.94 | 2.4 |  | RIG TANK | 117000
GEL ST. | 7/22 | 8/25 | PRESSURE (PSI) |  | 2250 - 2400 |  | RPM SURF. |  | 90 - 95 |  | 9 1/2" FILTER SUB |  |  | 9.5 | 3.875 |  | 7 5/8 REG |  | 2.21 | 0.71392 |  | CAMP TANK | 23100
WL (ml/30 min.) | 5 | 5 | TORQ. ON-BTM (KLB-FT) |  | 3 - 7 |  | RPM BTM. |  | 190 - 195 |  | 3 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 27.63 | 8.9256 |  | CONSUMED | 10200
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 2 - 3 |  | WOB (TON) |  | 2 - 8 |  | X/OVER |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 0.93 | 0.30043 |  | RECEIVED | 25000
ALK (MUD) | 0.8 | 0.6 | STRING WT. (TON) - ROT |  | 99 |  | AVG. ROP (M/HR) |  | 7.8164 |  | 2 X 8" DCS |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 18.57 | 4.1467 |  | TOTAL | 140100
ALK (FILT.) | 0.4 | 0.3 | PICK-UP WT. (TON) |  | 100 |  | BIT ROT HRS. |  | 104.14 |  | DRILLING JAR |  |  | 7.625 | 3 |  | 6 5/8 REG |  | 5.14 | 1.1478 |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 98 |  | K-REVS IN 24 HRS |  | 239 |  | 2 X 8" DCS |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 18.39 | 4.1065 |  | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 1152 |  | X/OVER |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 0.74 | 0.16524 |  | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 24.98 |  | 6 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 56.18 | 4.1816 |  | CONSUMED | 119500
KCl (mg/l) | 51480.9 | 51480.9 | JAR | 130.33 | NMDC | 130.33 | JET VELOCITY (M/SEC) |  | 69.5 | [12 empty] | RECEIVED | 114500
CHLORIDES | 24000 | 24000 | 5" HWDPS | 216.6 | STAB - 1 | 130.33 | TFA (IN²) |  | 1.2425 | [12 empty] | TOTAL | 440000
CALCIUM | 140 | 180 | 8" DCS | 229.9 | STAB - 2 |  | HSI |  | 1.1 | [12 empty] | POB
OIL% | 2 | 2 | 9 1/2" DCS | 229.9 | SPSA | 130.33 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 162.46 |  |  | MPCL | 4
SAND % |  |  | BHA ROT. HRS |  | 229.9 |  | BIT No. 3 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 27 |  |  | MPCL SERV | 18
SOLIDS % | 9.74 | 9.74 | ON BOTTOM HRS |  | 104.14 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 19 |  |  | SECURITY | -
M.B.T. | 10 | 10 | CIRC. HRS |  | 129.05 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 48
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 35 | 2 X 35 |  | 20" SURFACE CASING |  |  | 594 | 1308 |  | 1.11 |  | 329.64 |  |  | 0.18 |  | MWD |  | TOTAL | 107
DAILY WELL COST (US$) |  | 54059.81 | SHAKER-2 | 1 X 80 | 2 X 80 |  | 13 3/8" INTERMEDIATE CSG |  |  |  | 1337 |  | 0.92 |  | 330.44 |  |  | 0.2 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 2588423.1752 | SHAKER-3 | 1 X 80 | 2 X 80 |  | 9 5/8" PRODUCTION CSG |  |  |  | 1366 |  | 0.66 |  | 325.97 |  |  | 0.28 |  | MWD |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 14.34% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 1394 |  | 0.46 |  | 323.9 |  |  | 0.22 |  | MWD |  | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 423
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | RONGSHENG | 20.75 | 3000 | P-1 - F-1600HL | 6 1/2" |  | 12" | 3980 PSI | 97% |  | 0.119 |  | 30 / 40 |  | 1328 |  | 250 / 320 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | RONGSHENG | 20.75 | 3000 | P-2 - F-1600HL | 6 1/2" |  | 12" | 3980 PSI | 97% |  | 0.119 |  | 30 / 40 |  | 1328 |  | 250 / 320 |  | CHINJI | 342
FIRE DRILL | 2018-01-03 | 2018-01-17 | BLIND RAMS | RONGSHENG | 20.75 | 3000 | P-3 - F-1600HL | 6 1/2" |  | 12" | 3980 PSI | 97% |  | 0.119 | [7 empty] | KAMLIAL | 1255
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE
KICK DRILL |  |  | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2017-12-31 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-01-03 | 2018-01-17 | NEXT BOP TEST DATE |  | 2018-01-14 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-06
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43106 | 43107 | 24 | DRL | PT-P | DM | DRILLED 17 1/2" HOLE FROM 1284M TO 1409M IN ROTARY MODE. REAMED, CIRCULATED & RECORDED MWD SURVEYS AT EACH CONNECTION. WHILE DRILLING PUMPED 20 BBL BRIDGING PILL AFTER EVERY 15M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43107 | 43107.0417 | 1 | DRL | PT-P | DM | DRILLED 17 1/2" HOLE FROM 1409M TO 1414M IN ROTARY MODE. REAMED, CIRCULATED & RECORDED MWD SURVEY AT CONNECTION. WHILE DRILLING PUMPED 20 BBL BRIDGING PILL AFTER EVERY 15M.
43107.0417 | 43107.0521 | 0.25 | DRL | NPT-P | RS | SERVICED TDS.
43107.0521 | 43107.25 | 4.75 | DRL | PT-P | DM | DRILLED 17 1/2" HOLE FROM 1414M TO 1440M IN ROTARY MODE. WHILE DRILLING PUMPED 20 BBL BRIDGING PILL AFTER EVERY 15M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KAMLIAL (60% CLAYSTONE & 40% SANDSTONE)
OPERATIONS AT 06:00 HRS |  |  | DRILLING 17 1/2" HOLE
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 17 1/2" HOLE SECTION FROM 1284M TO 1409M IN ROTARY MODE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 17 1/2" HOLE SECTION.
REMARKS
Formulas:
DHARIAN - 1 = [DATE]+14
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14