## DDR#171
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 171
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-10-22
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4682.7 | 4682.7 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 170.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4687 | 4687 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-10-21 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 31 |  | BHA NO. |  |  | 32 | IN (M) |  | 4682.7 |  | OUT (M) |  |  | STRING (BBL) | 260.9
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO.(CORE HEAD) |  |  | 17 RR1 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 706
DEPTH, MD (M) | 4682.7 | 4682.7 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 8 1/2" x 4" |  | CORE HEAD |  |  | 8.5 |  |  | HDT |  | 0.37 | 0.053 |  | PITS (BBL) | 497
MW IN (SG) | 1.7 | 1.7 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | HALLIBURTON |  | OUTER CORE BARREL |  |  | 6.75 | 5.375 |  | HDT |  | 11.08 | 1.3456 |  | ACT. SYS (BBL) | 1463.9
MW OUT (SG) | 1.7 | 1.7 | INST. ROP (M/HR) |  |  |  | TYPE |  |  | FC3843 |  | PBL SUB |  |  | 6.75 | 1.33 |  | 4 1/2 IF |  | 3.48 | 0.45576 |  | RESV. SYS (BBL) | 1730
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 12886217 |  | 15 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 138.86 | 18.186 |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  | M433 |  | HYD DRL JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.94 | 1.3018 |  | KILL MW (SG)
µ FUNNEL (SEC) | 60 | 56 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 8 x PORTS |  | 3 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 27.78 | 3.6382 |  | TOTAL | 3193.9
PV | 41 | 43 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4682.7 |  | 12 x HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 111.43 | 8.1757 |  | DIESEL (LTR)
YIELD POINT | 25 | 24 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 98701
GEL ST. | 9/11 | 11/16 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 23720
WL (ml/30 min) | 4 | 4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 4307
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 122421
ALK (FILT.) | 0.3/1.2 | 0.3/1.2 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 85000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 75500
KCl (mg/l) | 57201 | 57201 | JAR | 77.1 | STAB - 1 | 57.56 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 105500
CHLORIDES (mg/l) | 29000 | 29000 | 5" HWDPS | 77.1 | STAB - 2 | 53.31 | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 535000
HARDNESS (mg/l) | 320 | 320 | 6 1/2" DCS | 77.1 | STAB - 3 | 53.31 | TFA (IN²) |  |  | 1.77 | [12 empty] | POB
PENETREX % | 2 | 2 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 302.94 |  |  | MPCL | 5
OIL % | 0.5 | 0.5 | DAILY BHA ROT. HRS |  | 1.88 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 25 |  |  | MPCL SERV | 20
SOLIDS % | 32.85 | 32.85 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. 17 RR |  |  | 0-2-BT-G-X-I -NO-CP |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 16 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 2.38 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 56
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 114
DAILY WELL COST (US$) |  | 32577.2233 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 13544743.4817 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 68.04% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1945.7226
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4680 | 545/550 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4680 | 725/735 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-10-08 | 2019-11-07 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4680 | 900/895 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-10-20 | 2019-11-19 | LAST BOP TEST DATE |  | 2019-10-07 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI | 4576/4576
STRETCHER DRILL | 2019-10-08 | 2019-11-07 | NEXT BOP TEST DATE |  | 2019-10-22 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR | 4667/4667
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43759 | 43759.1875 | 4.5 | DRL | PT-P | COR / POOH | CONT'D POOH FROM 1942M TO 302M (BHA TOP).
43759.1875 | 43759.1979 | 0.25 | DRL | PT-P | COR / FC | FLOW CHECKED, WELL STATIC.
43759.1979 | 43759.2708 | 1.75 | DRL | PT-P | COR / BHA | POOH CORING BHA FROM 302M TO SURFACE.
43759.2708 | 43759.3438 | 1.75 | DRL | PT-P | COR / BHA | HANDLED CORE BARREL AT SURFACE. BROKE OUT & L/D INNER BARREL ALONG WITH CORE. DRESSED CORE BARREL WITH NEW INNER BARREL & SPACED OUT. CHECKED & FOUND PROPER SPACING OF INNER BARREL. ROTATING FREE (INSIDE CORE HEAD). INSPECTED CORE HEAD. FOUND OK.
43759.3438 | 43759.4062 | 1.5 | DRL | PT-P | COR / BHA | RIH WITH CORING ASSY AS PER BHA DOWN TO 302M.
43759.4062 | 43759.8438 | 10.5 | DRL | PT-P | COR / RIH | RIH CORING ASSEMBLY FROM 302M TO 4473M. BROKE CIRCULATION AFTER EVERY 1500M.
43759.8438 | 43759.8854 | 1 | DRL | NPT-P | RS | HELD PJSM. CUT & SLIPPED 103FT DRILL LINE. RESET ACS & CROWN-O-MATIC. FUNCTION TESTED ACS. FOUND OK.
43759.8854 | 43759.9062 | 0.5 | DRL | PT-P | COR / RIH | RESUMED RIH FROM 4473M TO 4602M.
43759.9062 | 43760 | 2.25 | DRL | PT-P | COR / RW | REAMED DOWN FROM 4602M TO BOTTOM.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-22
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43759 | 43759.0729 | 1.75 | DRL | PT-P | COR / CIR | CIRCULATED FOR BOTTOMS UP. (MAX TRIP GAS: 6.97%)
43759.0729 | 43759.0938 | 0.5 | DRL | PT-P | COR / CIR | DROPPED 1.25" STEEL BALL INSIDE STRING & CHASED WITH MUD AT 220 GPM. OBSERVED PRESSURE INCREASE FROM 950 PSI TO 1080 PSI. RECORDED SCR.
43759.0938 | 43759.25 | 3.75 | DRL | PT-P | COR | TAGGED BOTTOM & STARTED CUTTING CORE# 03. CUT CORE FROM 4682.7M TO 4687M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | SAKESSAR / LIMESTONE.
OPERATIONS AT 06:00 HRS |  |  | CORING IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH FROM 1942M TO SURFACE & RETRIEVED CORE. RIH AGAIN WITH CORING ASSY DOWN TO BOTTOM.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CUT CORE# 03 IN SAKESSAR FORMATION. POOH TO SURFACE & RETRIEVE CORE.
REMARKS |  |  | 8.5M (95%) CORE# 02 RECOVERED.
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+15