## DDR#172
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 172
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-10-23
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4692.2 | 4692.2 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 171.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4692.2 | 4692.2 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 9.5
2019-10-22 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 8.5 |  | RUN NO. |  |  | 31 |  | BHA NO. |  |  | 32 | IN (M) |  | 4682.7 |  | OUT (M) | 4692.2 |  | STRING (BBL) | 7.7
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 4692.2 |  | BIT NO.(CORE HEAD) |  |  | 17 RR1 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1054.5
DEPTH, MD (M) | 4692.2 | 4692.2 | TVD @ 00:00HR (M) |  | 4692.2 |  | SIZE (IN) |  |  | 8 1/2" x 4" |  | CORE HEAD |  |  | 8.5 |  |  | HDT |  | 0.37 | 0.053 |  | PITS (BBL) | 420
MW IN (SG) | 1.7 | 1.7 | DAILY PROGRESS (M) |  | 9.5 |  | MANUFACTURER |  |  | HALLIBURTON |  | OUTER CORE BARREL |  |  | 6.75 | 5.375 |  | HDT |  | 11.08 | 1.3456 |  | ACT. SYS (BBL) | 1482.2
MW OUT (SG) |  |  | INST. ROP (M/HR) |  | - |  | TYPE |  |  | FC3843 |  | PBL SUB |  |  | 6.75 | 1.33 |  | 4 1/2 IF |  | 3.48 | 0.45576 |  | RESV. SYS (BBL) | 1677
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 1.2633 |  | SERIAL NO. |  |  | 12886217 |  | 15 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 138.86 | 18.186 |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 1-6 |  | IADC CODE |  |  | M433 |  | HYD DRL JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.94 | 1.3018 |  | KILL MW (SG)
µ FUNNEL (SEC) | 61 | 60 | AVG. RPM SURFACE |  | 55-65 |  | NOZZLES (1/32") |  |  | 8 x PORTS |  | 3 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 27.78 | 3.6382 |  | TOTAL | 3159.2
PV | 43 | 42 | AVG. RPM DOWNHOLE |  | 55-65 |  | DEPTH IN (M) |  |  | 4682.7 |  | 12 x HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 111.43 | 8.1757 |  | DIESEL (LTR)
YIELD POINT | 25 | 26 | FLOWRATE (GPM) |  | 250 |  | DEPTH OUT (M) |  |  | 4692.2 | [12 empty] | RIG TANK | 139903
GEL ST. | 10/15 | 11/16 | PRESSURE (PSI) |  | 1390-1430 |  | METERAGE (M) |  |  | 9.5 | [12 empty] | CAMP TANK | 23259
WL (ml/30 min) | 4 | 4.2 | TORQ. ON-BTM (KLB-FT) |  | 2-7 |  | RPM SURF. |  |  | 55-65 | [12 empty] | CONSUMED | 7259
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 1-2 |  | RPM BTM. |  |  | 55-65 | [12 empty] | RECEIVED | 48000
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 173 |  | WOB (TON) |  |  | 1-6 | [12 empty] | TOTAL | 163162
ALK (FILT.) | 0.3/1.2 | 0.3/1.1 | PICK-UP WT. (TON) |  | 175 |  | AVG. ROP (M/HR) |  |  | 1.2633 | [12 empty] | WATER (LTR)
pH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 170 |  | BIT ROT HRS. |  |  | 7.52 | [12 empty] | RIG STORAGE | 430000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  | 28.53 | [12 empty] | CAMP STORAGE | 70000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  | 28.53 | [12 empty] | CONSUMED | 113900
KCl (mg/l) | 57201 | 57201 | JAR | 88.6 | STAB - 1 |  | ANN. VEL. (M/MIN) |  |  | 45.1 | [12 empty] | RECEIVED | 78900
CHLORIDES (mg/l) | 29000 | 29000 | 5" HWDPS | 88.6 | STAB - 2 |  | JET VELOCITY (M/SEC) |  |  | 13.9 | [12 empty] | TOTAL | 500000
HARDNESS (mg/l) | 300 | 320 | 6 1/2" DCS | 88.6 | STAB - 3 |  | TFA (IN²) |  |  | 1.77 | [12 empty] | POB
PENETREX % | 2 | 2 |  |  |  |  | HSI |  |  | 0.07 |  | TOTAL LENGTH (M) | [7 empty] | 302.94 |  |  | MPCL | 5
OIL % | 0.5 | 0.5 | DAILY BHA ROT. HRS |  | 11.5 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 25 |  |  | MPCL SERV | 21
SOLIDS % | 32.85 | 32.85 | DAILY ON BOTTOM HRS |  | 7.52 |  | BIT NO. 17 RR1 |  |  | 1-2-BT-G-X-I-NO-BHA |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 16 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 12.1 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 56
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 115
DAILY WELL COST (US$) |  | 43777.37 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 13588520.8517 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 68.26% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1945.7226
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4680 | 545/550 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4680 | 725/735 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-10-08 | 2019-11-07 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4680 | 900/895 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-10-20 | 2019-11-19 | LAST BOP TEST DATE |  | 2019-10-07 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI | 4576/4576
STRETCHER DRILL | 2019-10-08 | 2019-11-07 | NEXT BOP TEST DATE |  | 2019-10-22 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR | 4667/4667
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-22
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43760 | 43760.0729 | 1.75 | DRL | PT-P | COR / CIR | CIRCULATED FOR BOTTOMS UP. (MAX TRIP GAS: 6.97%)
43760.0729 | 43760.0938 | 0.5 | DRL | PT-P | COR / CIR | DROPPED 1.25" STEEL BALL INSIDE STRING & CHASED WITH MUD AT 220 GPM. OBSERVED PRESSURE INCREASE FROM 950 PSI TO 1080 PSI. RECORDED SCR.
43760.0938 | 43760.4062 | 7.5 | DRL | PT-P | COR | TAGGED BOTTOM & STARTED CUTTING CORE# 03. CUT CORE FROM 4682.70M TO 4692.2M. BROKE CORE BY APPLYING 15 TON OVER PULL.
43760.4062 | 43760.4896 | 2 | DRL | PT-P | COR / CIR | CIRCULATED FOR BOTTOMS UP TO COLLECT SAMPLE.
43760.4896 | 43760.5 | 0.25 | DRL | PT-P | COR / FC | FLOW CHECKED, WELL STATIC.
43760.5 | 43760.5417 | 1 | DRL | PT-P | COR / RW | PUMPED OUT TO 4544M (INSIDE CSG SHOE) TO AVOID SWABBING.
43760.5417 | 43760.5521 | 0.25 | DRL | PT-P | COR / FC | FLOW CHECKED, WELL STATIC.
43760.5521 | 43760.9896 | 10.5 | DRL | PT-P | COR / POOH | PUMPED SLUG & POOH FROM 4544M TO 302M (BHA TOP).
43760.9896 | 43761 | 0.25 | DRL | PT-P | COR / FC | FLOW CHECKED, WELL STATIC.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43761 | 43761.0833 | 2 | DRL | PT-P | COR / BHA | POOH CORING BHA FROM 302M TO SURFACE. L/D JAR & PBL SUB.
43761.0833 | 43761.1354 | 1.25 | DRL | PT-P | COR / BHA | HELD PJSM. HANDLED CORE BARREL AT SURFACE. BROKE OUT & L/D INNER BARREL ALONG WITH CORE. SOFT BROKE OUTER BARREL CONNECTIONS. L/D CORE HEAD.
43761.1354 | 43761.25 | 2.75 | DRL | PT-P | BOPT | HELD PJSM. M/U COMBINATION TOOL ASSY & RETRIEVED WEAR BUSHING. RIH 2x5" DP STDS. M/UP TEST PLUG ASSY & SET TEST PLUG INSIDE 11" THS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP @ 500/4500 PSI FOR 5/10 MIN - OK. P/TESTED ROTARY HOSE & STANDPIPE MANIFOLD @ 500/6000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER VARIABLE PIPE RAM BOP (4.5" - 7"), HYD & MANUAL IBOP, FOSV, HCR & MANUAL VALVES @ KILL & CHOKE LINE, CHOKE MANIFOLD MASTER VALVE, CO-FLEXIP HOSE @ 500/9000 PSI FOR 5/10 MIN - OK. PRESSURE TEST LOWER PIPE RAMS IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | SAKESSAR / LIMESTONE.
OPERATIONS AT 06:00 HRS |  |  | BOP PRESSURE TEST IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATED AT BOTTOM. CUT CORE# 03 IN SAKESSAR FORMATION FROM 4682.7M TO 4692.2M. POOH TO 302M (BHA TOP).
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | PERIODIC BOP PRESSURE TEST. L/DOWN RACKED BACK BHA FOR INSPECTION. P/UP NEW 8 1/2" PDC BIT & RIH WITH INSPECTED ROTARY BHA FOR DRILLING.
REMARKS |  |  | 9M (100%) CORE# 03 RECOVERED.
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+15